## Queue
Interconnection Requests for New England Control Area | [5 empty] | As of: 4/18/2024 12:00:00 AM |  |  | ISO-NE Public
Generation, Elective Transmission Upgrade and Transmission Service Requests
Jurisdiction: | All | Status: | All
Cluster | Position | Updated | Type | Requested | Alternative Name | Unit | Fuel Type | Net MW | Summer MW | Winter MW | County | State | Op Date | Sync Date | W/ D Date | Interconnection Location | Serv | SIS Complete | I39 | TO Report | Dev | Zone | FS | SIS | OS | FAC | IA | Project Status
TCS | 1090 | 2025-10-17 14:19 | G | 2021-01-13 | Park City Offshore Wind CNR | WT | WND | 0 | 838.2 | 838.2 | NA | MA | 2029-12-31 | 2029-05-01 |  | Eversource (NSTAR) 345kV West Barnstable | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed | Under Study
TCS | 1116 | 2025-10-17 14:19 | G | 2021-04-13 | SouthCoast Wind 1 | WT | WND | 1200 | 1200 | 1200 | NA | MA | 2031-12-31 | 2030-05-01 |  | Brayton Point making use of QP 837 to connect | CNR | TRUE | TRUE | ISO-NE | PD | RI | Document Posted | Document Posted |  |  | Executed | Under Study
TCS | 1123 | 2025-10-17 14:19 | G | 2021-04-21 | Naugatuck Avenue Battery Storage CNR Only (see QP1089) | OT | BAT | 0 | 205.32 | 205.32 | New Haven | CT | 2027-05-31 | 2027-04-15 |  | devon 115kV substation | CNR | FALSE | FALSE |  | PD | SWCT | [5 empty] | Under Study
TCS | 1148 | 2025-10-17 14:19 | G | 2021-07-13 | Lite Brite Battery Storage | OT | BAT | 305.624 | 305.624 | 305.624 | Suffolk | MA | 2028-05-26 | 2028-04-30 |  | Electric Avenue 115 kV substation (bus number 110926), Zone MA_NST | CNR | TRUE | TRUE | ISO-NE |  | BOST | Document Posted | Document Posted |  |  | Executed | Under Study
TCS | 1171 | 2025-10-17 14:20 | G | 2021-10-25 | Twin Energy Wind | WT | WND | 18.3 | 20 | 20 | Oxford | ME | 2026-09-21 | 2026-08-21 |  | Roxbury Substation | CNR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed | Under Study
TCS | 1238 | 2025-11-12 16:42 | G | 2022-03-22 | Battery Storage | OT | BAT | 300 | 301.26 | 301.26 | Norfolk | MA | 2028-04-28 | 2027-11-30 |  | West Medway 345kV station | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted |  |  |  |  | Under Study
TCS | 1252 | 2025-10-17 14:20 | G | 2022-04-21 | Battery Storage | OT | BAT | 314.7 | 314.7 | 314.7 | Essex | MA | 2032-08-01 | 2032-07-01 |  | Ward Hill 345 kV Substation | CNR | TRUE | TRUE |  | PD | BOST | Document Posted | Document Posted | Not Required | Not Required | In Progress | Under Study
TCS | 1365 | 2025-11-12 16:42 | G | 2023-03-09 | Battery Storage | OT | BAT | 250 | 254.2 | 254.2 | Hampden | MA | 2029-06-30 | 2029-01-29 |  | Connect to South Agawam 115 kV switchyard | CNR | FALSE | FALSE |  | PD | WMA | Document Posted |  |  |  |  | Under Study
TCS | 1412 | 2025-11-12 16:43 | G | 2023-06-20 | Battery Storage | OT | BAT | 168 | 169.843 | 169.843 | Bristol | MA | 2027-09-30 | 2027-09-15 |  | Direct tap into the Pottersville Substation in Somerset, MA | CNR | FALSE | FALSE |  | PD | SEMA | [5 empty] | Under Study
TCS | 1427 | 2025-11-12 16:45 | G | 2023-07-21 | Solar | PV | SUN | 180 | 183.3176 | 183.3176 | York | ME | 2029-12-30 | 2029-12-01 |  | Lebanon, Maine Line 391 Buxton Sub (CMP) to Scobie Pond (Eversource). GPS coordinates of the POI: 43°22'51.59"N, 70°55'57.74"W. ** This new tap is located approximately 27.8 miles southwest of Buxton substation and approx. 39.9 miles northeast of the Scobie Pond substation. | CNR | FALSE | FALSE |  | PD | ME | Document Posted |  |  |  |  | Under Study
TCS | 1428 | 2025-11-12 16:46 | G | 2023-07-25 | Solar | PV | SUN | 100 | 101.549 | 101.549 | Rockingham | NH | 2028-12-30 | 2028-12-01 |  | A tap at existing 115 kV line between Eversource 115kV Scobie Pond - Pulpit Rock Line A184 115kV. * The new tap will be located at approx. 42.9292184N, -71.2567898W and along a ~6 mile segment of Line A184 (approx. 4.9 miles northeast of Scobie Pond and approx. 1.1 miles southwest of Pulpit Rock). | CNR | FALSE | FALSE |  | PD | NH | [5 empty] | Under Study
TCS | 1460 | 2025-11-12 16:39 | G | 2023-10-12 | Battery Storage | OT | BAT | 350 | 353.535 | 353.535 | Bristol | MA | 2027-09-30 | 2027-09-15 |  | Customer built substation with a tap into the west-most 345kV line exiting the NG 345kV Brayton Point substation | CNR | FALSE | FALSE |  | PD | RI | [5 empty] | Under Study
TCS | 1495 | 2025-10-17 14:14 | G | 2024-02-22 | Battery Storage | OT | BAT | 19.3 | 19.3 | 19.3 | Windsor | VT | 2026-07-01 | 2026-06-01 |  | Direct connection to VELCO 115kV Windsor substation (43.48988, -72.40858) | CNR | FALSE | FALSE |  | PD | VT | [5 empty] | Under Study
TCS | 1502 | 2025-10-17 14:14 | G | 2024-03-28 | Battery Storage | OT | BAT | 19.3 | 19.3 | 19.3 | Franklin | VT | 2026-07-01 | 2026-06-01 |  | Direct connection to VELCO 115kV Highgate substation (44.943833, -73.058515) | CNR | FALSE | FALSE |  | PD | VT | [5 empty] | Under Study
TCS | 1513 | 2025-11-12 16:49 | G | 2024-04-08 | Battery Storage | OT | BAT | 300 | 318.268 | 318.268 | Worcester | MA | 2028-08-30 | 2028-05-31 |  | Bear Swamp- Pratts Junction 230kV | CNR | FALSE | FALSE |  | PD | CMA | [5 empty] | Under Study
TCS | 1515 | 2025-11-12 16:49 | G | 2024-04-09 | Battery Storage | OT | BAT | 290 | 295.8 | 295.8 | Berkshire | MA | 2028-08-30 | 2028-05-31 |  | Alps-Berkshire 345kV line | CNR | FALSE | FALSE |  | PD | WMA | [5 empty] | Under Study
TCS | 1518 | 2025-11-12 16:50 | G | 2024-04-09 | Battery Storage | OT | BAT | 136 | 139.5 | 139.5 | Berkshire | MA | 2028-08-30 | 2028-05-31 |  | Eversource, Partridge 115kV Substation | CNR | FALSE | FALSE |  | PD | WMA | [5 empty] | Under Study
| 1 |  | G | 1996-06-07 | Millennium+K117 | CC | DFO NG |  |  |  | Worcester | MA | 2001-04-06 |  |  | W 123 Line | ES | TRUE | TRUE | NGRID |  | WMA
| 2 |  | G | 1996-11-08 | EMI-Tiverton | CC | NG |  |  |  | Newport | RI | 2000-08-18 |  |  | Near Tiverton 115 kV Substation | ES | TRUE | TRUE | NGRID |  | SEMA
| 3 |  | G | 1997-02-13 | Androscoggin Energy Center | CC | DFO NG |  |  |  | Franklin | ME | 2000-12-28 |  |  | Jay 115 kV Substation | ES | TRUE | TRUE | CMP |  | ME
| 4 |  | G | 1997-04-10 | EMI Dighton Power Project | CC | NG |  |  |  | Bristol | MA | 1999-08-01 |  |  | U6 Line | ES | TRUE | TRUE | NGRID |  | SEMA
| 5 |  | G | 1997-05-09 | Brayton Pt | [5 empty] | Bristol | MA | 2001-12-31 |  |  | Brayton Point 345 kV Station | MIS | TRUE | TRUE | NGRID |  | RI
| 6 |  | G | 1997-06-12 | Rumford Power Associates | CC | NG |  |  |  | Oxford | ME | 2000-10-16 |  |  | Rumford 115 kV Substation |  | TRUE | TRUE | CMP |  | ME
| 7 |  | G | 1997-06-25 | Bridgeport Harbor Station | CC | NG |  |  |  | Fairfield | CT | 1999-07-24 |  |  | Pequonnock 115 kV Substation |  | TRUE | TRUE | UI |  | SWCT
| 8 | 2009-10-02 | G | 1997-07-15 | ANP Bellingham Energy Project Unit 1 | CC | NG |  |  |  | Norfolk | MA | 2002-10-24 |  |  | Sectionalize Line 303 | MIS | TRUE | TRUE | NGRID |  | RI
| 8 | 2009-10-02 | G | 1997-07-15 | ANP Bellingham Energy Project Unit 2 | CC | NG |  |  |  | Norfolk | MA | 2002-12-28 |  |  | Sectionalize Line 303 | MIS | TRUE | TRUE | NGRID |  | RI
| 8 | 2009-10-02 | G | 1997-07-15 | ANP Blackstone Energy Project Unit 1 | CC | NG |  |  |  | Worcester | MA | 2001-06-07 |  |  | Sectionalize 336 Line | MIS | TRUE | TRUE | NGRID |  | RI
| 8 | 2009-10-02 | G | 1997-07-15 | ANP Blackstone Energy Project Unit 2 | CC | NG |  |  |  | Worcester | MA | 2001-07-13 |  |  | Sectionalize 336 Line | MIS | TRUE | TRUE | NGRID |  | RI
| 9 |  | G | 1997-07-22 | IDC Bellingham | [5 empty] | Norfolk | MA | 2002-12-31 |  |  | Sectionalize 336 Line | MIS | TRUE | TRUE | NSTAR |  | RI
| 10 |  | G | 1997-07-24 | Maine Independence | CC | NG |  |  |  | Penobscot | ME | 2000-05-01 |  |  | Located at Graham Station in Veazie, ME |  | TRUE | TRUE | CMP |  | BHE
| 11 |  | G | 1997-08-05 | Wareham | [5 empty] | Plymouth | MA | 2001-02-28 |  |  | Adjacent to the Tremont Substation |  | FALSE | FALSE |  |  | SEMA
| 12 |  | G | 1997-08-15 | Berkshire Power | CC | NG |  |  |  | Hampden | MA | 2000-06-19 |  |  | South Agawam Jct. 115 kV Station | ES | TRUE | TRUE | NU |  | WMA
| 13 |  | G | 1997-08-22 | Summit Power | [5 empty] | Hampden | MA | 2001-03-31 |  |  | 1302 Line |  | FALSE | FALSE |  |  | WMA
| 13 | 2009-10-02 | G | 1997-08-22 | Milford Power Unit 1 | CC | DFO NG |  |  |  | New Haven | CT | 2004-02-12 |  |  | Devon 115 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | SWCT
| 13 | 2009-10-02 | G | 1997-08-22 | Milford Power Unit 2 | CC | DFO NG |  |  |  | New Haven | CT | 2004-05-03 |  |  | Devon 115 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | SWCT
| 14 |  | G | 1997-09-30 | Cabot Power | [5 empty] | Middlesex | MA | 2000-06-30 |  |  | Mystic 345 kV Station | ES | TRUE | TRUE | NSTAR |  | BOST
| 15 |  | G | 1997-10-09 | South Norwalk | [5 empty] | Fairfield | CT | 2000-01-01 |  |  | Norwalk 115 kV Substation |  | TRUE | FALSE | ISO-NE |  | NOR
| 16 |  | G | 1997-10-24 | ANP Gorham | [5 empty] | Cumberland | ME | 2000-07-01 |  |  | S. Gorham 345 kV Substation | MIS | TRUE | TRUE | CMP |  | ME
| 17 |  | G | 1997-12-12 | SEI Newington (ConEd) | CC | JF NG |  |  |  | Rockingham | NH | 2002-09-18 |  |  | Newington 345 kV Station | MIS | TRUE | TRUE | NU |  | NH
| 17 | 2009-10-02 | G | 1997-12-12 | Lake Road Generating Units 1&2 | CC | DFO NG |  |  |  | Windham | CT | 2002-03-15 |  |  | Line 347 | MIS | TRUE | TRUE | ISO-NE |  | RI
| 17 | 2009-10-02 | G | 1997-12-12 | Lake Road Generating Unit 3 | CC | DFO NG |  |  |  | Windham | CT | 2002-05-22 |  |  | Line 347 | MIS | TRUE | TRUE | ISO-NE |  | RI
| 18 |  | G | 1998-01-13 | Versaille Energy Center | [5 empty] | New London | CT | 2000-12-31 |  |  | Tunnel 115 kV Substation |  | FALSE | FALSE |  |  | CT
| 18 |  | G | 1998-01-13 | White Mountain Cogen.Center | [5 empty] | Coos | NH | 2000-12-31 |  |  | Lost Nation 115 kV Substation |  | FALSE | FALSE |  |  | NH
| 18 |  | G | 1998-01-13 | Sprague Newington (Piscataqua Power) | [5 empty] | Rockingham | NH | 2000-01-01 |  |  | Newington 345 kV Station | MIS | FALSE | FALSE |  |  | NH
| 19 |  | G | 1998-01-14 | Livermore Falls | [5 empty] | Androscoggin | ME | 2000-12-01 |  |  | Livermore Falls 115 kV Substation |  | FALSE | FALSE |  |  | ME
| 20 |  | G | 1998-01-20 | Housatonic Power | [5 empty] | Fairfield | CT | 2001-01-01 |  |  | 398 Line |  | FALSE | FALSE |  |  | CT
| 21 | 2009-10-02 | G | 1998-02-11 | Wallingford Power Units 1&3 | GT | NG |  |  |  | New Haven | CT | 2001-12-31 |  |  | Wallingford 115 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | SWCT
| 21 | 2009-10-02 | G | 1998-02-11 | Wallingford Power Unit 4 | GT | NG |  |  |  | New Haven | CT | 2002-01-23 |  |  | Wallingford 115 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | SWCT
| 21 | 2009-10-02 | G | 1998-02-11 | Wallingford Power Units 2&5 | GT | NG |  |  |  | New Haven | CT | 2002-02-07 |  |  | Wallingford 115 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | SWCT
| 21 |  | G | 1998-02-11 | AES Londonderry (Granite Ridge) | CC | DFO NG |  |  |  | Rockingham | NH | 2003-04-01 |  |  | N. Litchfield 230 kV Station and Watts Brook 115 k | MIS | TRUE | TRUE | ISO-NE |  | NH
| 22 |  | G | 1998-02-16 | Meriden Power | [5 empty] | New Haven | CT | 2003-06-30 |  |  | Sectionalize 362 Line | MIS | TRUE | TRUE | ISO-NE |  | CT
| 23 |  | ETU | 1998-02-19 | HQ-Surowiec | [5 empty] | Cumberland | ME | 2002-12-31 |  |  | Surowiec 345 kV or MEPCO | MIS | TRUE | FALSE | CMP |  | ME
| 24 |  | G | 1998-02-25 | Orrington Generation | [5 empty] | Penobscot | ME | 2001-06-30 |  |  | Orrington 345 kV Station |  | FALSE | FALSE |  |  | ME
| 25 |  | G | 1998-02-27 | Patriot Power | [5 empty] | Bristol | MA | 2001-03-31 |  |  | Bridgewater 345 kV Line |  | FALSE | FALSE |  |  | SEMA
| 26 |  | G | 1998-03-06 | S&P Cogeneration | [5 empty] | Essex | MA | 2001-12-31 |  |  | Lynn 115 kV |  | TRUE | FALSE |  |  | BOST
| 27 |  | G | 1998-03-13 | AES Carpenter | [5 empty] | Hartford | CT | 2001-12-31 |  |  | Southington 345 kV Substation | MIS | FALSE | FALSE |  |  | CT
| 28 |  | G | 1998-03-18 | Newington Energy Center | [5 empty] | Rockingham | NH | 2001-03-31 |  |  | Newington 345 kV Station |  | FALSE | FALSE |  |  | NH
| 29 |  | G | 1998-03-24 | Bucksport Energy, L.P. | CC | DFO NG |  |  |  | Hancock | ME | 2001-01-01 |  |  | Belfast 115 kV bus | MIS | TRUE | TRUE | CMP |  | BHE
| 30 |  | G | 1998-03-25 | Norwich Power Station | [5 empty] | New London | CT | 2000-12-31 |  |  | Bean Hill Substation |  | TRUE | FALSE | NU |  | CT
| 30 |  | ETU | 1998-03-25 | Engage Energy LTF PtP | [5 empty] | N/A |  | 2000-12-31 |  |  | Import from New Brunswick via MEPCO | ES | TRUE | FALSE | CMP
| 31 |  | G | 1998-03-26 | North Smithfield | [5 empty] | Providence | RI | 2002-06-30 |  |  | W. Farnum 345 kV | MIS | TRUE | FALSE | NGRID |  | RI
| 32 |  | G | 1998-03-30 | Towantic Energy | [5 empty] | New Haven | CT | 2002-12-31 |  |  | Beacon Falls 115 kV | MIS | TRUE | TRUE | ISO-NE |  | CT
| 33 |  | G | 1998-03-31 | Sithe Framingham Station Expansion | [5 empty] | Middlesex | MA | 2001-12-31 |  |  | Framingham 230 kV |  | FALSE | FALSE |  |  | BOST
| 33 |  | G | 1998-03-31 | Sithe Medway | [5 empty] | Norfolk | MA | 2001-12-31 |  |  | Existing Medway Station 345 kV | MIS | TRUE | TRUE | NSTAR |  | RI
| 33 |  | G | 1998-03-31 | Westbrook Power | CC | NG |  |  |  | Cumberland | ME | 2001-04-13 |  |  | Spring St. 115 kV Substation | MIS | TRUE | TRUE | CMP |  | SME
| 33 |  | G | 1998-03-31 | Sithe Edgar Station Expansion (Fore River) | CC | NG |  |  |  | Norfolk | MA | 2003-08-04 |  |  | Holbrook 345 kV | MIS | TRUE | TRUE | NSTAR |  | SEMA
| 33 | 2009-10-02 | G | 1998-03-31 | Sithe Mystic Station Expansion Unit 8 | CC | NG |  |  |  | Suffolk | MA | 2003-04-13 |  |  | Mystic 345 kV | ES | TRUE | TRUE | NSTAR |  | BOST
| 33 | 2009-10-02 | G | 1998-03-31 | Sithe Mystic Station Expansion Unit 9 | CC | NG |  |  |  | Suffolk | MA | 2003-06-11 |  |  | Mystic 345 kV | ES | TRUE | TRUE | NSTAR |  | BOST
| 34 |  | G | 1998-04-01 | WEG-Norwich | [5 empty] | New London | CT | 2005-06-30 |  |  | Montville 115 kV Substation |  | FALSE | FALSE |  |  | CT
| 35 |  | G | 1998-04-02 | Mason | [5 empty] | Lincoln | ME | 2000-12-31 |  |  | Mason 345 kV Substation | MIS | FALSE | FALSE |  |  | ME
| 35 |  | G | 1998-04-02 | Wyman A | [5 empty] | Cumberland | ME | 2000-01-02 |  |  | Wyman 115 kV Station | MIS | FALSE | FALSE |  |  | SME
| 35 |  | G | 1998-04-02 | Wyman B | [5 empty] | Cumberland | ME | 2000-01-03 |  |  | Wyman 115 kV Station |  | FALSE | FALSE |  |  | SME
| 36 |  | G | 1998-04-14 | FPL Energy (Bedford) | [5 empty] | Bristol | MA | 2000-11-30 |  |  | Industrial Park 115 kV Substation | MIS | FALSE | FALSE |  |  | SEMA
| 37 |  | G | 1998-04-29 | FPLE RISE, LLC (R.I. Hope Energy) | CC | NG |  |  |  | Providence | RI | 2002-11-05 |  |  | S 171 and S 172 Lines | MIS | TRUE | TRUE | NGRID |  | RI
| 38 |  | G | 1998-05-08 | Rocky River Power | [5 empty] | Litchfield | CT | 2001-07-31 |  |  | Long Mountain 345 kV Station | MIS | FALSE | FALSE |  |  | CT
| 39 |  | ETU | 1998-05-28 | CVPS/GMP LTF PtP | [5 empty] | Clinton | NY | 2001-12-31 |  |  | Import from NY via PV20 | MIS | FALSE | FALSE |  |  | VT
| 39 |  | ETU | 1998-05-28 | HQ Highgate2 HVDC | [5 empty] | Franklin | VT | 2001-12-31 |  |  | Located on the Hydro Quebec sys. N. near Highgate, | MIS | FALSE | FALSE |  |  | VT
| 40 |  | G | 1998-06-01 | Glen Charlie Unit One | [5 empty] | Plymouth | MA | 2001-03-31 |  |  | Wareham 115 kV Substation |  | FALSE | FALSE |  |  | SEMA
| 41 |  | G | 1998-06-04 | Canal 2 Repowering | [5 empty] | Barnstable | MA | 2001-06-30 |  |  | Canal 345 kV Station | MIS | FALSE | FALSE |  |  | SEMA
| 42 |  | G | 1998-06-05 | Wiscassett | [5 empty] | Lincoln | ME | 2001-10-01 |  |  | Maine Yankee 345 KV | MIS | FALSE | FALSE |  |  | ME
| 43 |  | ETU | 1998-06-08 | Tractebel LTF PtP | [5 empty] | N/A |  | 2002-12-31 |  |  | Import from the New Brunswick System |  | FALSE | FALSE
| 44 |  | G | 1998-07-10 | Brockton Power Project | [5 empty] | Plymouth | MA | 2001-01-31 |  |  | Industrial Blvd. | MIS | TRUE | TRUE | NGRID |  | SEMA
| 45 |  | G | 1998-07-17 | Kendall Repowering Project | CC | NG |  |  |  | Suffolk | MA | 2002-12-18 |  |  | Kendall Station in Cambridge | MIS | TRUE | TRUE | NSTAR |  | BOST
| 46 |  | G | 1998-08-18 | Campello Power Co. | [5 empty] | Plymouth | MA | 2002-06-30 |  |  |  | MIS | FALSE | FALSE |  |  | SEMA
| 47 |  | G | 1998-08-26 | Nickel Hill Energy Project | [5 empty] | Middlesex | MA | 2001-06-30 |  |  | Tewksbury 230 kV Substation | MIS | FALSE | FALSE |  |  | BOST
| 48 |  | G | 1998-09-09 | Bennington Energy Park | [5 empty] | Bennington | VT | 2001-11-30 |  |  | TBD |  | FALSE | FALSE |  |  | VT
| 48 |  | G | 1998-09-09 | Rutland Energy Park | [5 empty] | Rutland | VT | 2001-11-30 |  |  | TBD |  | FALSE | FALSE |  |  | VT
| 49 |  | ETU | 1998-09-14 | Irving Oil LTF PtP | [5 empty] | N/A |  | 2001-04-01 |  |  | Import from NB Via MEPCO | ES | FALSE | FALSE
| 50 |  | G | 1998-10-29 | Patriot Cabot Street Station | [5 empty] | Hampden | MA | 2001-12-31 |  |  | Holyoke Substation |  | FALSE | FALSE |  |  | WMA
| 51 |  | ETU | 1998-10-30 | MEPCO-New England Interface Expansion | [5 empty] | N/A |  | 2000-01-01 |  |  | Import Capability from MEPCO | MIS | FALSE | FALSE |  |  | ME
| 52 |  | G | 1998-11-13 | Haddam Station | [5 empty] | Middlesex | CT | 2002-12-31 |  |  | Site of the Former CT Yankee Plant | MIS | FALSE | FALSE |  |  | CT
| 52 |  | G | 1998-11-13 | Haddam Station Phase II | [5 empty] | Middlesex | CT | 2002-12-31 |  |  | Site of the Former CT Yankee Plant |  | FALSE | FALSE |  |  | CT
| 53 |  | ETU | 1998-11-30 | Tractebel LTF Int + Internal PtP | [5 empty] | N/A |  | 2002-05-01 |  |  | Import from the New Brunswick System | ES | FALSE | FALSE
| 54 |  | G | 1999-01-05 | Redington Mountain Wind Farm | [5 empty] | Franklin | ME | 2002-12-31 |  |  | Bigelow 115 kV Substation | MIS | FALSE | FALSE |  |  | ME
| 55 |  | ETU | 1999-01-21 | Cross Sound Cable | NA | N/A |  |  |  | New Haven | CT | 2003-09-01 |  |  | HVDC terminal adjacent to East Shore 345kV Substat | MIS | TRUE | TRUE | TEUS |  | CT
| 56 |  | ETU | 1999-02-25 | New York Interface Import Expansion | [5 empty] | N/A |  | 1999-05-01 |  |  | Increase Import Capability from New York |  | FALSE | FALSE
| 57 |  | G | 1999-06-04 | Norwich Power Station | [5 empty] | New London | CT | 2002-01-01 |  |  | Bean Hill Substation | MIS | FALSE | FALSE |  |  | CT
| 58 |  | ETU | 1999-08-05 | CPS LTF Pt to Pt In Svc. | [5 empty] | N/A |  | 1999-11-01 |  |  | Increase Import Capability from NY |  | FALSE | FALSE
| 59 |  | G | 1999-08-18 | Milford Power Uprate | [5 empty] | New Haven | CT | 2001-06-30 |  |  | Increase Existing Unit Capacity | MIS | FALSE | FALSE |  |  | SWCT
| 59 |  | G | 1999-08-18 | Berkshire Power Uprate | [5 empty] | Hampden | MA | 2001-06-30 |  |  | Increase Existing Unit Capacity | MIS | FALSE | FALSE |  |  | WMA
| 60 |  | ETU | 1999-09-01 | Sithe LTF Pt to Pt In Svce. | [5 empty] | N/A |  | 2000-03-01 |  |  | Increase Import Capability from NY |  | FALSE | FALSE
| 61 |  | ETU | 1999-09-15 | New York Interface Import Expansion | [5 empty] | N/A |  | 1999-12-01 |  |  | Increase Import Capability from NY |  | FALSE | FALSE
| 62 |  | ETU | 1999-10-05 | New York Interface Import Expansion | [5 empty] | N/A |  | 2000-01-01 |  |  | Increase Import Capability from NY | MIS | FALSE | FALSE
| 63 |  | ETU | 1999-11-04 | WESC LTF Pt to Pt In Svce | [5 empty] | N/A |  | 2000-02-01 |  |  | Increase Import Capability from NY |  | FALSE | FALSE
| 64 |  | G | 1999-11-08 | West Springfield Station | ST | NG RFO |  |  |  | Hampden | MA | 2002-06-07 |  |  | West Springfield 115 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | WMA
| 64 |  | G | 1999-11-08 | Seabrook Unit One Uprate | [5 empty] | Rockingham | NH | 2002-05-01 |  |  | Increase Existing Unit Capacity | MIS | FALSE | FALSE |  |  | NH
| 65 |  | ETU | 1999-12-02 | EPMI LTF Pt to Pt In Svce. | [5 empty] | N/A |  | 2002-01-01 |  |  |  |  | FALSE | FALSE
| 66 |  | G | 1999-12-20 | AEC Expansion | [5 empty] | Franklin | ME | 2001-06-30 |  |  | Riley Road 115 kV Substation | MIS | FALSE | FALSE |  |  | ME
| 67 |  | G | 2000-02-25 | Lowell Power Expansion | [5 empty] | Middlesex | MA | 2001-05-01 |  |  | Lowell Power 115 kV Station | MIS | TRUE | TRUE | NGRID |  | CMA
| 68 |  | ETU | 2000-03-09 | Bridgeport Long Island HVDC | [5 empty] | Fairfield | CT | 2003-05-01 |  |  | HVDC to Long Island, NY from Bridgeport, CT | MIS | FALSE | FALSE |  |  | SWCT
| 69 |  | ETU | 2000-04-20 | Neptune HVDC Cable Project | [5 empty] | N/A |  | 2004-03-31 |  |  | HVDC from Maine/ Maritimes to Boston Area and CT S | MIS | FALSE | FALSE
| 70 |  | ETU | 2000-04-25 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2003-07-31 |  |  | Increase Export Capability to New York | MIS | FALSE | FALSE
| 71 |  | G | 2000-05-22 | New Haven Harbor | [5 empty] | New Haven | CT | 2003-06-01 |  |  | East Shore Substation | MIS | FALSE | FALSE |  |  | CT
| 71 |  | G | 2000-05-22 | Bridgeport Harbor Station | [5 empty] | Fairfield | CT | 2003-06-01 |  |  | Pequonnock 115 kV Substation | MIS | FALSE | FALSE |  |  | SWCT
| 72 |  | G | 2000-06-28 | Tewksbury Power | [5 empty] | Middlesex | MA | 2004-06-30 |  |  | Tewksbury 345 kV Station | MIS | FALSE | FALSE |  |  | CMA
| 73 |  | G | 2000-07-07 | Norwalk Harbor A | [5 empty] | Fairfield | CT | 2003-12-31 |  |  | Norwalk 115 kV Station | MIS | FALSE | FALSE |  |  | NOR
| 73 |  | G | 2000-07-07 | Norwalk Harbor B | [5 empty] | Fairfield | CT | 2004-06-30 |  |  | Norwalk 115 kV Station | MIS | FALSE | FALSE |  |  | NOR
| 73 |  | G | 2000-07-07 | Devon A | [5 empty] | New Haven | CT | 2003-12-31 |  |  | Devon 115 kV Substation | MIS | FALSE | FALSE |  |  | SWCT
| 73 |  | G | 2000-07-07 | Middletown A | [5 empty] | Middlesex | CT | 2003-12-31 |  |  | Middletown Station | MIS | FALSE | FALSE |  |  | CT
| 73 |  | G | 2000-07-07 | Middletown B | [5 empty] | Middlesex | CT | 2005-12-31 |  |  | Middletown Station | MIS | FALSE | FALSE |  |  | CT
| 73 |  | G | 2000-07-07 | Montville A | [5 empty] | New London | CT | 2004-09-30 |  |  | Montville Station | MIS | FALSE | FALSE |  |  | CT
| 73 |  | G | 2000-07-07 | Somerset Diversity | [5 empty] | Bristol | MA | 2004-03-31 |  |  | Somerset 115 kV Station | MIS | FALSE | FALSE |  |  | SEMA
| 73 |  | G | 2000-07-07 | Somerset A | [5 empty] | Bristol | MA | 2003-12-31 |  |  | Somerset 115 kV Station | MIS | FALSE | FALSE |  |  | SEMA
| 74 | 2011-02-22 | G | 2000-07-24 | South Norwalk Repowering | IC | DFO NG | 48.9 | 48.9 | 48.9 | Fairfield | CT | 2011-06-01 | 2011-04-15 | 2011-02-22 | Norwalk 115 kV Substation | NA | TRUE | TRUE | ISO-NE |  | NOR
| 75 |  | ETU | 2000-08-16 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2001-01-01 |  |  | Increase Export Capability to New York | MIS | TRUE | TRUE | ISO-NE
| 76 |  | ETU | 2000-08-31 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2001-01-01 |  |  | Increase Export Capability to New York | MIS | FALSE | FALSE
| 77 | 2011-05-31 | G | 2000-10-02 | Berkshire Wind Power Project | WT | WND | 15 | 15 | 15 | Berkshire | MA | 2011-05-28 | 2011-05-06 |  | WMECO at Brodie Mt. In Lanesboro MA | NA | TRUE | TRUE | NU |  | WMA
| 78 |  | ETU | 2000-12-13 | Norwalk-Northport HVDC | [5 empty] | Fairfield | CT | 2003-06-30 |  |  | HVDC Norwalk CT and Northport NY | MIS | FALSE | FALSE |  |  | NOR
| 79 |  | ETU | 2000-12-18 | Milford CT - New York HVDC | [5 empty] | New Haven | CT | 2003-06-30 |  |  | HVDC Devon CT 115 kV | MIS | FALSE | FALSE |  |  | SWCT
| 80 |  | G | 2000-12-27 | Berlin Energy Project | [5 empty] | Coos | NH | 2002-01-01 |  |  | Berlin 115 kV Substation (PSNH) | MIS | FALSE | FALSE |  |  | NH
| 81 |  | G | 2001-01-02 | Berwick Energy Center | [5 empty] | York | ME | 2002-01-01 |  |  | Dover 115 kV Substation | MIS | FALSE | FALSE |  |  | NH
| 82 |  | G | 2001-02-14 | Cape Cod Offshore Wind Project | [5 empty] | Barnstable | MA | 2004-12-31 |  |  | South of Barnstable 115kV Substation | MIS | FALSE | FALSE |  |  | SEMA
| 83 |  | ETU | 2001-03-12 | Neptune Phase3 Boston Import from NB or NS | [5 empty] | Suffolk | MA | 2004-03-31 |  |  | Kingston St. 115/345 kV and K St. 115 kV Substatio | MIS | FALSE | FALSE |  |  | BOST
| 83 |  | ETU | 2001-03-12 | Neptune Phase4 CT Import from NB or NS | [5 empty] | Fairfield & New Haven | CT | 2004-03-31 |  |  | Glenbrook 115 kV and E. Shore St. 115/345 kV (sep. | MIS | FALSE | FALSE |  |  | NOR
| 83 |  | ETU | 2001-03-12 | Neptune Phase5 ME Yankee Export to Boston, CT or N | [5 empty] | Lincoln | ME | 2004-03-31 |  |  | Maine Yankee 345 kV (Bi-Polar HVDC Terminal) | MIS | FALSE | FALSE |  |  | ME
| 83 |  | ETU | 2001-03-12 | Neptune Phase7 Wyman Export to Boston, CT, NYC or | [5 empty] | Cumberland | ME | 2004-03-31 |  |  | Wyman 345 kV (Bi-Polar HVDC Terminal) | MIS | FALSE | FALSE |  |  | SEMA
| 84 |  | G | 2001-03-13 | Phase 1 - Nantucket Shouls Wind | [5 empty] | Barnstable | MA | 2007-12-31 |  |  | Near Barnstable 115kV Substation | MIS | FALSE | FALSE |  |  | SEMA
| 84 |  | G | 2001-03-13 | Phase 2 - Nantucket Shouls Wind | [5 empty] | Barnstable | MA | 2008-12-31 |  |  | Near Barnstable 115kV Substation | MIS | FALSE | FALSE |  |  | SEMA
| 84 |  | G | 2001-03-13 | Phase 3 - Nantucket Shouls Wind | [5 empty] | Barnstable | MA | 2009-12-31 |  |  | Near Barnstable 115kV Substation | MIS | FALSE | FALSE |  |  | SEMA
| 84 |  | G | 2001-03-13 | Phase 4 - Nantucket Shouls Wind | [5 empty] | Barnstable | MA | 2010-12-31 |  |  | Near Barnstable 115kV Substation | MIS | FALSE | FALSE |  |  | SEMA
| 84 |  | G | 2001-03-13 | Phase I - Nantucket Sound Wind Project | [5 empty] | Barnstable | MA | 2004-12-31 |  |  | Near Barnstable 115kV Substation | MIS | FALSE | FALSE |  |  | SEMA
| 84 |  | G | 2001-03-13 | Phase 2 - Nantucket Sound Wind | [5 empty] | Barnstable | MA | 2005-12-31 |  |  | Near Barnstable 115kV Substation | MIS | FALSE | FALSE |  |  | SEMA
| 85 |  | G | 2001-04-04 | Pilgrim Power Uprate | ST | NUC |  |  |  | Plymouth | MA | 2003-08-01 |  |  | Increase Existing Unit Capacity | MIS | TRUE | TRUE | NSTAR |  | SEMA
| 86 |  | ETU | 2001-05-21 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2002-01-01 |  |  | Increase Export Capability to New York | MIS | FALSE | FALSE
| 87 |  | ETU | 2001-05-24 | Stage II Cross Sound Cable HVDC Interconnection | [5 empty] | New Haven | CT | 2003-07-01 |  |  | HVDC terminal adjacent to East Shore 345kV Substat | MIS | FALSE | FALSE |  |  | CT
| 88 | 2017-04-21 06:48 | ETU | 2001-06-01 | Increase Orrington South Transfer Limit | NA | N/A |  |  |  | N/A |  | 2007-12-01 |  | 2008-01-02 | N/A | MIS | TRUE | TRUE | BHE |  | ME
| 89 | 2017-01-13 08:33 | G | 2001-06-06 | Cape Wind Turbine Generators | WT | WND | 454 | 454 | 454 | N/A | MA | 2018-12-31 | 2018-10-01 | 2017-01-12 | Near Barnstable 115 kV Substation | NR | TRUE | TRUE | ISO-NE |  | SEMA | Document Posted | Document Posted | Document Posted |  | Executed
| 90 |  | G | 2001-06-08 | Cabot Station CUO Uprate | HD | WAT |  |  |  | Franklin | MA | 2004-05-01 |  |  | Increase generating capacity from 53.0 MW to 61.8 | MIS | TRUE | TRUE | NU |  | WMA
| 91 |  | ETU | 2001-06-12 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2002-06-01 |  |  | Increase Export Capability to New York | MIS | FALSE | FALSE
| 91 |  | ETU | 2001-06-12 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2003-06-01 |  |  | Increase Export Capability to New York | MIS | FALSE | FALSE
| 92 |  | ETU | 2001-06-26 | Sithe Mystic 4,5,6 Reconfiguration of Interconnect | [5 empty] | Middlesex | MA | 2003-03-31 |  |  | Reconfigure Mystic 4,5,6 Interconnection from Myst | MIS | FALSE | FALSE |  |  | BOST
| 93 |  | ETU | 2001-07-06 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2002-01-01 |  |  | Increase Export Capability to New York | MIS | FALSE | FALSE
| 93 |  | ETU | 2001-07-06 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2002-01-01 |  |  | Increase Export Capability to New York | MIS | FALSE | FALSE
| 93 |  | ETU | 2001-07-06 | HVDC Interconn. betw. Norwalk Stat, CT & Shore Rd | [5 empty] | N/A | CT | 2004-05-01 |  |  | Interconnection between Norwalk Stat, CT & Shore R | MIS | FALSE | FALSE |  |  | NOR
| 93 |  | ETU | 2001-07-06 | HVDC Interconn. betw. Norwalk Stat, CT & Shore Rd | [5 empty] | N/A | CT | 2004-05-01 |  |  | Interconnection between Norwalk Stat, CT & Shore R | MIS | FALSE | FALSE |  |  | NOR
| 94 |  | G | 2001-07-17 | CPV New Britain LLC | [5 empty] | Hartford | CT | 2005-07-01 |  |  | Interconnection South New Britain CT 115 kV Corrid | MIS | FALSE | FALSE |  |  | CT
| 95 | 2011-07-12 | G | 2001-11-21 | Kleen Energy Project | CC | DFO NG | 619.8 | 619.8 | 620 | Middlesex | CT | 2011-07-12 | 2011-05-03 |  | Sectionalize 353 Line | CNR | TRUE | TRUE | ISO-NE |  | CT
| 96 |  | G | 2001-12-12 | Great Northern - Millinocket | HW | WAT |  | 126 | 126 | Penobscot | ME | 2003-05-20 |  |  | 115 kV connection to Chester 115 kV Substation | MIS | TRUE | TRUE | BHE |  | BHE
| 97 |  | ETU | 2001-12-26 | Western Maine Area Export Enhancement | [5 empty] | N/A |  |  |  |  | Increase Export Capability from Rumford Power Asso | MIS | FALSE | FALSE |  |  | ME
| 98 |  | G | 2002-06-03 | Redington Wind Farm Phase II | [5 empty] | Franklin | ME | 2005-12-01 |  |  | Bigelow 115 kV Substation | MIS | FALSE | FALSE |  |  | ME
| 99 |  | G | 2002-08-08 | Millstone 2 Upgrade7 | ST | NUC |  | 897.5 | 905.7 | New London | CT | 2004-03-10 |  |  | Increase Existing Unit Capacity | MIS | TRUE | TRUE | ISO-NE |  | CT
| 99 |  | G | 2002-08-08 | Millstone 3 Upgrade7 | ST | NUC |  | 1195 | 1207.4 | New London | CT | 2006-05-08 |  |  | Increase Existing Unit Capacity | MIS | TRUE | TRUE | ISO-NE |  | CT
| 100 |  | G | 2002-12-12 | VT Yankee Nuclear Power Station Upgrade7 | ST | NUC |  | 634.5 | 641.5 | Windham | VT | 2006-05-08 |  |  | Increase Existing Unit Capacity | MIS | TRUE | TRUE | ISO-NE |  | VT
| 101 |  | G | 2003-01-15 | Seabrook Power Uprate7 | ST | NUC |  | 1265 | 1265 | Rockingham | NH | 2006-10-31 |  |  | Increase Existing Unit Capacity | MIS | TRUE | TRUE | ISO-NE |  | NH
| 102 | 2008-10-14 | G | 2003-02-04 | Peabody Power | GT | DFO NG |  | 97.2 | 97.2 | Essex | MA | 2008-05-01 | 2008-02-01 | 2008-10-14 | C155 & B154 - 115 kV Lines | MIS | TRUE | TRUE | NGRID |  | BOST
| 103 |  | G | 2003-03-04 | Waterside Power | GT |  |  |  |  | Fairfield | CT | 2003-06-01 |  |  | Waterside 115 kV | MIS | TRUE | TRUE | ISO-NE |  | NOR
| 104 | 2010-07-16 | G | 2003-03-06 | Waterside Power - 180 MW | GT | DFO NG | 203.9 | 203.9 | 207.2 | Fairfield | CT | 2011-12-31 | 2011-09-30 | 2010-07-12 | Waterside 115 kV | CNR | TRUE | TRUE | ISO-NE | PD | NOR |  |  |  | Document Posted
| 105 |  | G | 2003-03-10 | Evergreen Wind Power - Bagley Mountain | [5 empty] | Penobscot | ME | 2004-07-01 |  |  | Chester 115 kV | MIS | FALSE | FALSE |  |  | BHE
| 105 |  | G | 2003-03-10 | Evergreen Wind Power - Blueberry Barrens | [5 empty] | Washington | ME | 2004-10-01 |  |  | Deblois 115 kV | MIS | FALSE | FALSE |  |  | BHE
| 106 | 2009-10-02 | G | 2003-03-18 | Ridgewood RI Generation Phase I | IC | LFG |  | 4.2 | 4.2 | Providence | RI | 2004-02-18 |  |  | Johnston Substation Distribution System | MIS | TRUE | TRUE | NGRID |  | RI
| 106 | 2009-10-02 | G | 2003-03-18 | Ridgewood RI Generation Phase II | IC | LFG |  | 4.2 | 4.2 | Providence | RI | 2005-11-20 |  |  | Johnston Substation Distribution System | MIS | TRUE | TRUE | NGRID |  | RI
| 107 |  | G | 2003-04-07 | SNEW Summer '03 Temporary Generator | GT | NG |  | 19.445 |  | Fairfield | CT | 2003-06-01 |  |  | Norwalk 27.6 kV | MIS | TRUE | TRUE | ISO-NE |  | NOR
| 108 | 2012-12-27 | G | 2003-05-12 | Hoosac Wind Project | WT | WND | 28.5 | 28.5 | 28.5 | Berkshire & Franklin | MA | 2012-12-27 | 2012-12-05 |  | Line Y25S | NR | TRUE | TRUE | NGRID |  | WMA
| 109 | 2008-12-31 | G | 2003-06-12 | AWT Fitchburg Wind Project | WT | WND | 12 |  |  | Worcester | MA | 2004-10-01 |  | 2008-12-31 | Ashburnham No. 610 - 13.8 kV | MIS | FALSE | FALSE |  |  | WMA
| 110 |  | G | 2003-07-07 | UCONN COGEN Facility |  | NG |  | 24.9 | 24.9 | Tolland | CT | 2005-10-19 |  |  | Mansfield 69 kV | MIS | TRUE | TRUE | ISO-NE |  | CT
| 111 |  | G | 2003-07-21 | GLHA James River/Fraser Paper7 |  | WAT |  | 25 | 25 | Coos | NH | 2004-06-22 |  |  | Berlin 115 kV | MIS | TRUE | TRUE | ISO-NE |  | NH
| 112 |  | G | 2003-09-15 | NECCO Cogen | IC | DFO |  |  |  | Suffolk | MA | 2003-10-01 |  |  | Everett 23 kV | MIS | TRUE | FALSE | NGRID |  | BOST
| 113 |  | G | 2003-09-29 | Sheffield Wind Power Project | [5 empty] | Caledonia | VT | 2005-12-31 |  |  | TBD | MIS | FALSE | FALSE |  |  | VT
| 114 |  | G | 2003-10-02 | Waterside Power, LLC | GT | DFO |  | 69.3 | 74.1 | Fairfield | CT | 2004-06-01 |  |  | Waterside 115 kV | MIS | TRUE | TRUE | ISO-NE |  | NOR
| 115 | 2008-12-31 | G | 2003-10-27 | SNEW Summer '04 Temporary Generator | GT | DFO | 0 | 23.8 |  | Fairfield | CT | 2004-06-01 |  | 2008-12-31 | Norwalk 27.6 kV | MIS | FALSE | FALSE |  |  | NOR
| 116 | 2012-06-11 | G | 2003-11-10 | East Haven Wind Farm | WT | WND | 6 |  |  | Essex | VT | 2012-10-30 |  |  | Village of Lyndonville Elec. Dept. Distribution Sy | NA | FALSE | FALSE |  |  | VT
| 117 |  | G | 2003-12-08 | Waterside Power - 23 MW | [5 empty] | Fairfield | CT | 2004-06-01 |  |  | Waterside 115 kV - Norwalk/Stamford | MIS | FALSE | FALSE |  |  | NOR
| 118 |  | G | 2003-12-29 | Bridgeport Harbor Units 5 & 6 | [5 empty] | Fairfield | CT | 2005-05-01 |  |  | Paquonnock 115 kV Substation | MIS | FALSE | FALSE |  |  | SWCT
| 118 |  | G | 2003-12-29 | New Haven Harbor Units 2 & 3 | [5 empty] | New Haven | CT | 2005-05-01 |  |  | East Shore 115 kV Substation | MIS | FALSE | FALSE |  |  | SWCT
| 119 | 2007-10-19 | G | 2004-01-16 | Ridgebury Power | [5 empty] | Fairfield | CT | 2004-06-01 |  | 2007-10-19 | CL&P Distribution System | MIS | FALSE | FALSE |  |  | SWCT
| 120 |  | G | 2004-05-10 | Univ. of NH - CHP | [5 empty] | Strafford | NH |  |  |  | PSNH Dist. Sys./Madbury 115 kV | MIS | FALSE | FALSE |  |  | NH
| 121 |  | G | 2004-06-22 | Third Taxing District Units 1, 2 & 3 |  | DFO |  | 6 | 6 | Fairfield | CT | 2005-03-28 |  |  | CL&P 27.6 kV Distribution System/Norwalk 115kV | MIS | FALSE | TRUE | N/A |  | NOR
| 122 |  | G | 2004-07-20 | Rand-Whitney Co-Gen |  | DFO NG |  | 11.866 | 14.858 | New London | CT | 2005-01-03 |  |  | CL&P Distribution System/Montville 115 kV | MIS | TRUE | TRUE | ISO-NE |  | CT
| 123 |  | G | 2004-10-04 | GenPower Athens | [5 empty] | Somerset | ME | 2006-06-01 |  |  | Gorbell Tap of CMP's Detroit-Wyman Hydro 66 - 115 | MIS | FALSE | FALSE |  |  | ME
| 124 |  | G | 2004-10-27 | Hardscrabble Mountain Project | [5 empty] | Caledonia | VT | 2006-03-31 |  |  | St. Johnsbury- Irasburg 115 kV Line | MIS | FALSE | FALSE |  |  | VT
| 125 | 2008-02-18 | G | 2004-11-02 | Cos Cob Redevelopment | GT | KER |  | 36 | 45.8 | Fairfield | CT | 2008-05-31 |  |  | Cos Cob 115 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | NOR
| 125 | 2010-02-16 | G | 2004-11-02 | Norwalk Harbor Station Redevelopment | GT | KER | 322.5 | 322.5 | 330 | Fairfield | CT | 2013-02-28 | 2012-12-31 | 2010-02-16 | Norwalk 345 kV Station | CNR | TRUE | FALSE | ISO-NE | BL | NOR
| 125 |  | G | 2004-11-02 | Devon Station Redevelopment | [5 empty] | New Haven | CT | 2010-07-15 |  |  | Devon 115 kV Substation | MIS | FALSE | FALSE |  |  | SWCT
| 126 |  | G | 2004-11-09 | Biomass | ST | WDS |  | 40 |  | Cheshire | NH | 2007-07-01 |  |  | N-186, 115kV line between Vernon Road Tap and bor | MIS | FALSE | FALSE |  |  | NH
| 127 | 2009-05-22 | G | 2004-11-15 | Lempster | WT | WND | 24 | 24 | 24 | Sullivan | NH | 2008-11-10 | 2008-09-04 |  | PSNH 34.5 kV circuit from Newport Substation | MIS | TRUE | TRUE | NU |  | NH
| 128 |  | G | 2005-02-11 | Biomass | ST | WDS |  | 39 | 42 | Litchfield | CT | 2007-07-31 | 2007-05-31 |  | TBD | MIS | FALSE | FALSE
| 129 |  | G | 2005-02-28 | Georgia Pacific | ST | WDS |  | 16 | 16 | Penobscot | ME | 2005-04-04 |  |  | BHE's Line 5 - 46kV | MIS | TRUE | TRUE | ISO-NE |  | BHE
| 130 |  | G | 2005-05-24 | Wind Project | WT | WND |  | 53 | 53 | Caledonia | VT | 2007-09-01 | 2007-08-01 | 2006-09-22 | Irasburg - St. Johnsbury 115 kV | MIS | FALSE | FALSE |  |  | VT
| 131 | 2008-02-18 | G | 2005-06-21 | Wind Project | WT | WND |  | 90 | 90 | Franklin | ME | 2010-12-31 | 2010-06-01 | 2008-09-25 | Bigelow Substation | MIS | TRUE | TRUE | ISO-NE |  | ME
| 132 | 2008-06-30 | G | 2005-07-21 | Wind Project | WT | WND |  | 9 | 9 | Bennington | VT | 2007-12-31 | 2007-06-01 | 2008-06-30 | Bennington - Brattleboro 46 kV | MIS | FALSE | FALSE |  |  | VT
| 133 |  | G | 2005-08-01 | Combined Cycle | CC | DFO |  | 115 | 124 | Orleans | VT | 2010-01-31 | 2009-12-31 |  | Newport 115 kV Substation | MIS | FALSE | FALSE |  |  | VT
| 134 | 2008-02-18 | G | 2005-08-03 | Wind Project | WT | WND |  | 45 | 45 | Bennington | VT | 2010-12-30 | 2010-09-29 | 2008-08-19 | Y-25 North, 69 kV line between Searsburg and Benni | MIS | FALSE | FALSE | ISO-NE |  | VT
| 135 | 2012-04-24 | G | 2005-08-19 | Russell Biomass | ST | WDS | 55 | 55 | 55 | Hampden | MA | 2015-08-01 | 2015-03-01 | 2012-03-15 | Blanford - Southwick - Elm 115 kV line | CNR | TRUE | TRUE | ISO-NE |  | WMA | Document Posted
| 136 | 2007-04-03 | G | 2005-08-19 | Biomass | ST | WDS |  | 39 | 40 | Somerset | ME | 2008-12-31 | 2008-09-30 | 2007-04-03 | Gorbell Tap of CMP's Detroit-Wyman Hydro 66 - 115 | MIS | FALSE | FALSE | ISO-NE |  | ME
| 137 | 2011-07-07 | G | 2005-09-23 | Rumford Hydro Configuration Modification | HD | WAT | 0 |  |  | Oxford | ME | 2011-06-21 | 2011-05-20 |  | CMP 115 kV Line 218 | NA | TRUE | TRUE | ISO-NE |  | ME |  |  |  | Document Posted
| 138 | 2009-11-02 | G | 2005-09-26 | Kibby Wind Project | WT | WND | 65 | 65 | 65 | Franklin | ME | 2009-10-30 | 2009-09-30 |  | Bigelow Substation | CNR | TRUE | TRUE | ISO-NE |  | ME
| 138 | 2010-10-26 | G | 2005-09-26 | Kibby Wind Project | WT | WND | 65.5 | 65.5 | 65.5 | Franklin | ME | 2010-10-26 | 2010-09-15 |  | Bigelow Substation | CNR | TRUE | TRUE | ISO-NE |  | ME
| 139 | 2009-05-15 | G | 2005-10-14 | Lowell Power Generators | GT | NG | 99 | 99 | 99 | Middlesex | MA | 2010-06-01 | 2010-04-01 | 2009-04-29 | J162 115kV line between Tewksbury and Perry Street | MIS | TRUE | TRUE | ISO-NE |  | CMA |  | Document Posted
| 140 | 2007-09-30 | G | 2005-12-13 | A. L. Pierce | GT | DFO NG |  | 89.35 | 99.56 | New Haven | CT | 2007-10-01 |  |  | Wallingford Electrical Division, East Street Subst | MIS | TRUE | TRUE | ISO-NE |  | SWCT
| 141 | 2007-02-07 | G | 2005-12-14 | Gas Turbine | GT | DFO NG |  | 200 | 200 | Middlesex | MA | 2009-09-30 | 2009-08-31 | 2007-02-07 | 115 kV O 167 line between Everett and Mystic Subst | MIS | FALSE | FALSE | ISO-NE |  | BOST |  | Document Posted
| 142 |  | G | 2005-12-21 | Wind Project | WT | WND |  | 48 | 48 | Windham | VT | 2008-05-31 | 2008-03-31 | 2006-04-13 | CVPS Londonderry Substation 46 kV | MIS | FALSE | FALSE |  |  | VT
| 143 |  | G | 2006-01-16 | Land Fill Gas | IC | LFG |  | 25 | 25 | Providence | RI | 2007-06-30 | 2007-06-01 | 2006-04-25 | Johnston Substation Distribution System | MIS | FALSE | FALSE |  |  | RI
| 144 |  | G | 2006-02-06 | Biomass | ST | WDS |  | 25 | 27.5 | Windsor | VT | 2009-04-30 | 2009-02-28 |  | VELCO Coolidge Substation | MIS | FALSE | FALSE |  |  | VT
| 145 | 2007-08-31 | G | 2006-02-13 | Wind Project | WT | WND |  | 51 | 51 | Windham | CT | 2009-12-31 | 2009-12-01 | 2008-06-20 | CL&P 115 kV 1607 line | MIS | FALSE | FALSE | ISO-NE |  | CT
| 146 |  | G | 2006-02-21 | Devon 10 | GT | JF KER |  | 17 | 20 | New Haven | CT | 2006-06-29 |  |  | CL&P Devon Substation | MIS | TRUE | TRUE | ISO-NE |  | SWCT
| 147 | 2007-08-31 | G | 2006-02-28 | Gas Turbine | GT | DFO |  | 168.2 | 168.2 | Suffolk | MA | 2010-06-01 | 2010-04-01 | 2007-11-02 | NSTAR Chelsea Substation | MIS | FALSE | FALSE | ISO-NE |  | BOST
| 148 | 2013-04-16 14:35 | G | 2006-03-06 | Comerford Unit #1 | HD | WAT | -17 | 24.3 | 24.5 | Grafton | NH | 2009-11-30 | 2009-11-30 |  | NGRID Comerford Substation | CNR | TRUE | TRUE | ISO-NE |  | NH
| 148 | 2011-03-21 | G | 2006-03-06 | Comerford Unit #3 | HD | WAT | 8.3 | 48.2 | 38.5 | Grafton | NH | 2011-03-25 | 2011-02-15 |  | NGRID Comerford Substation | CNR | TRUE | TRUE | ISO-NE |  | NH
| 148 | 2012-03-28 | G | 2006-03-06 | Comerford Unit #2 | HD | WAT | 8.4 | 48.3 | 48.5 | Grafton | NH | 2012-03-12 | 2012-02-27 |  | NGRID Comerford Substation | CNR | TRUE | TRUE | ISO-NE |  | NH
| 148 | 2013-03-26 12:23 | G | 2006-03-06 | Comerford Unit #4 | HD | WAT | 8.3 | 48.2 | 48.5 | Grafton | NH | 2013-03-22 | 2012-12-25 |  | NGRID Comerford Substation |  | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | Executed | In Service
| 149 | 2017-04-21 06:48 | ETU | 2006-03-10 | Transmission Expansion | NA | N/A |  |  |  | N/A | CT | 2006-11-01 |  | 2007-12-04 | N/A | N/A | FALSE | FALSE | ISO-NE |  | CT
| 150 | 2013-12-12 09:30 | G | 2006-05-25 | Plainfield Renewable Energy Project | ST | WDS | 37.5 | 37.5 | 38.5 | Windham | CT | 2013-12-12 | 2013-11-07 |  | CLP Fry Brook Substation | CNR | TRUE | TRUE | ISO-NE |  | CT |  | Document Posted |  |  | Executed | In Service
| 151 |  | G | 2006-05-30 | Fitchburg Renewable Energy | IC | LFG |  | 7.2 | 7.2 | Worcester | MA | 2007-08-29 |  |  | NGRID E. Westminster Substation 13.8 kV | MIS | TRUE | TRUE | NGRID |  | CMA
| 152 |  | G | 2006-05-30 | MATEP (Medical Area Total Energy Project) | OT | DFO NG |  | 42 | 42 | Suffolk | MA |  |  |  | NSTAR Brighton Substation | MIS | FALSE | TRUE | NSTAR |  | BOST
| 153 | 2007-10-08 | G | 2006-05-30 | Fuel Cell | FC | NG |  | 8 | 8 | Fairfield | CT | 2007-05-31 | 2007-05-31 |  | CL&P Cedar Heights Substation | MIS | FALSE | FALSE |  |  | SWCT
| 154 |  | G | 2006-05-31 | Gas Turbine (Additional Capacity) | GT | DFO |  | 29 | 0 | Suffolk | MA | 2008-08-01 | 2008-06-01 |  | NSTAR Chelsea Substation | MIS | FALSE | FALSE |  |  | BOST
| 155 | 2009-04-16 | G | 2006-06-02 | Gas Turbine |  | DFO NG | 160 | 120 | 130 | Middlesex | MA | 2011-05-01 | 2011-03-01 |  | NSTAR Mystic Substation | MIS | FALSE | FALSE | ISO-NE |  | BOST
| 155 | 2009-05-22 | G | 2006-06-02 | Fairfield University |  | NG |  | 5 | 5 | Fairfield | CT | 2007-12-11 |  |  | UI Ash Creek Substation | MIS | FALSE | FALSE |  |  | SWCT
| 155 | 2009-02-11 | G | 2006-06-16 | Fuel Cell | FC | NG | 14.4 | 14.4 | 14.4 | Fairfield | CT | 2009-06-01 | 2009-06-01 |  | UI Pequonnock Substation | MIS | FALSE | FALSE |  |  | SWCT
| 156 | 2011-05-26 | G | 2006-06-13 | Salem Harbor Unit 1 Exciter Replacement | ST | BIT |  |  |  | Essex | MA | 2006-11-26 |  |  | Salem Switchyard | MIS | TRUE | TRUE | ISO-NE |  | BOST |  | Document Posted
| 156 |  | G | 2006-06-13 | Brayton Point Unit 3 Voltage Regulator Replacement | ST | BIT |  |  |  | Bristol | MA | 2006-05-26 |  |  | Brayton Switchyard | MIS | FALSE | FALSE |  |  | RI
| 157 | 2009-12-29 | G | 2006-06-21 | Billerica Power | GT | NG WO | 311 | 311 | 341 | Middlesex | MA | 2011-06-15 | 2011-05-15 | 2009-12-29 | J-162 line to Tewksbury Substation | CNR | TRUE | TRUE | ISO-NE |  | CMA |  | Document Posted
| 158 | 2009-05-22 | G | 2006-06-21 | UTC - P&WA |  | NG |  | 7.5 | 7.5 | Middlesex | CT | 2007-12-21 |  |  | CL&P P&WA Substation | MIS | TRUE | TRUE | NU |  | CT
| 159 | 2008-11-12 | G | 2006-06-30 | Gas Turbine | GT | NG | 325 | 325 | 375 | Fairfield | CT | 2010-09-30 | 2010-06-30 | 2008-10-22 | UI 345 kV Singer Substation | MIS | TRUE | TRUE | ISO-NE |  | SWCT
| 159 |  | G | 2006-06-30 | Fuel Cell | FC | NG |  | 30 | 30 | Fairfield | CT | 2008-12-31 | 2008-03-31 | 2006-10-25 | NU Triangle Substation 11A | MIS | FALSE | FALSE |  |  | SWCT
| 159 |  | G | 2006-06-30 | Fuel Cell | FC | NG |  | 30 | 30 | Fairfield | CT | 2008-12-31 | 2008-03-31 | 2006-10-25 | UI Congress Street Substation 2C | MIS | FALSE | FALSE |  |  | SWCT
| 160 | 2008-11-26 | G | 2006-06-30 | Gas Turbine | GT | DFO NG | 82.2 | 82.2 | 94.8 | Middlesex | CT | 2011-05-31 | 2011-04-30 | 2008-11-26 | CL&P Middletown Substation | MIS | TRUE | FALSE | ISO-NE |  | CT
| 161 | 2010-07-16 | G | 2006-07-05 | Devon Units 15, 16, 17, 18 | GT | KER NG | 196.8 | 196.8 | 196.8 | New Haven | CT | 2010-06-09 | 2010-04-01 |  | Devon Substation | CNR | TRUE | TRUE | ISO-NE |  | SWCT
| 161 | 2011-06-27 | G | 2006-07-05 | Middletown 12, 13, 14 and 15 | GT | JF KER NG | 215 | 215 | 211 | Middlesex | CT | 2011-06-24 | 2011-04-05 |  | CL&P Middletown Substation or CL&P Scovill Rock Su | CNR | TRUE | TRUE | ISO-NE |  | CT
| 161 | 2011-02-15 | G | 2006-07-05 | Middletown 11 | GT | JF KER NG | 107.5 | 107.5 | 110 | Middlesex | CT | 2011-06-01 | 2011-04-01 | 2011-02-10 | CL&P Middletown Substation | CNR | TRUE | TRUE | ISO-NE |  | CT
| 161 | 2009-04-15 | G | 2006-07-05 | Combined Cycle | CC | NG | 223 | 630 | 690 | New London | CT | 2013-05-31 | 2013-02-01 | 2009-04-07 | Montville Substation | MIS | FALSE | FALSE | ISO-NE |  | CT
| 161 | 2007-03-28 | G | 2006-07-17 | Combustion Turbine |  | NG |  |  |  |  | CT | 2008-04-30 |  |  | CL&P Rocky River Substation | MIS | FALSE | FALSE |  |  | SWCT
| 162 | 2009-05-22 | G | 2006-07-18 | Vernon Repowering | HD | WAT |  | 32 | 32 | Windham | VT | 2008-03-13 |  |  |  | MIS | TRUE | TRUE | ISO-NE |  | VT
| 163 | 2009-07-16 | G | 2006-07-24 | Mirant Kendall Jet 2 | GT | JF | 18 | 18 | 22 | Middlesex | MA | 2010-01-31 | 2010-01-15 | 2009-07-14 | Kendall Station in Cambridge | MIS | TRUE | TRUE | NSTAR |  | BOST | Document Posted | Document Posted
| 164 | 2009-12-15 | G | 2006-08-01 | Combined Cycle( see # 201) | GT | NG | 320 | 158 | 196 | Providence | RI | 2012-06-01 | 2011-12-31 | 2009-12-14 | 345 kV RISE Substation | CNR | FALSE | FALSE |  | BL | RI
| 165 | 2009-04-17 | G | 2006-08-03 | Combined Cycle( See # 226) | CC | NG | 563 | 563 | 616 | Rockingham | NH | 2013-06-30 | 2012-12-31 | 2009-04-10 | 345 kV Seabrook Substation | MIS | FALSE | FALSE | ISO-NE |  | NH
| 166 | 2015-06-15 15:07 | G | 2006-08-09 | Granite Reliable Power | WT | WND | 94.5 | 94.5 | 94.5 | Coos | NH | 2012-02-15 | 2011-10-24 |  | PSNH W-179 115 kV line | CNR | TRUE | TRUE | ISO-NE |  | NH | Document Posted | Document Posted
| 167 | 2009-02-11 | G | 2006-08-10 | Fuel Cell | FC | NG | 16 | 16 | 16 | New Haven | CT | 2009-12-31 | 2009-12-31 |  | CL&P Cherry Street 13 kV substation | MIS | FALSE | FALSE |  |  | SWCT
| 168 | 2009-10-01 | G | 2006-08-11 | Wind Project-Phase 2( MPS Queue # 2&3) | WT | WND |  | 250 | 250 | N/A |  | 2012-09-30 |  | 2009-09-16 | Maine Public Service System, upgrades include tap | MIS | FALSE | FALSE | MPS
| 168 | 2009-10-01 | G | 2006-08-11 | Wind Project-Phase 3( MPS Queue # 4) | WT | WND |  | 250 | 250 | N/A |  | 2011-09-30 |  | 2009-09-16 | Maine Public Service System, upgrades include tap |  | FALSE | FALSE | MPS
| 169 |  | ETU | 2006-08-15 | Transmission Expansion | NA | N/A |  |  |  | N/A | VT | 2009-06-30 |  |  | VELCO Coolidge Substation | N/A | FALSE | FALSE |  |  | VT
| 169 |  | G | 2006-08-15 | Biomass | ST | WDS |  | 25 | 27.5 | Windsor | VT | 2009-06-30 | 2009-04-30 | 2006-11-02 | New Ludlow 115 kV Substation | MIS | FALSE | FALSE |  |  | VT
| 170 | 2009-04-16 | G | 2006-08-25 | Gas Turbine Capacity Increase (see #155) |  | DFO NG | 0 | 40 | 55 | Middlesex | MA | 2011-05-01 | 2011-03-01 | 2009-04-09 | NSTAR Mystic Substation | MIS | FALSE | FALSE | ISO-NE |  | BOST
| 171 | 2009-06-30 | G | 2006-08-29 | Thomas A. Watson Generating Station | GT | DFO NG | 108 | 108 | 115 | Norfolk | MA | 2009-06-23 | 2009-03-01 |  | 115 kV Potter Substation | CNR | TRUE | TRUE | ISO-NE |  | SEMA | Document Posted | Document Posted |  |  |  | In Service
| 172 | 2011-10-19 | G | 2006-08-29 | Sheffield Wind Project | WT | WND | 40 | 40 | 40 | Caledonia | VT | 2011-10-19 | 2011-09-19 |  | Irasburg - St. Johnsbury 115 kV | CNR | TRUE | TRUE | ISO-NE |  | VT
| 173 | 2009-02-11 | G | 2006-09-21 | Wind Project | WT | WND | 60 | 60 | 60 | Rutland | VT | 2010-10-30 | 2010-09-15 | 2009-01-21 | 115 kV West Rutland substation | MIS | FALSE | FALSE |  |  | VT
| 174 | 2012-08-09 | G | 2006-10-13 | Combined Cycle | CC | DFO NG | 280 | 280 | 280 | Hampden | MA | 2015-07-01 | 2015-05-01 | 2012-08-10 | 345 kV Stony Brook Substation | CNR | TRUE | TRUE | ISO-NE | BL | WMA
| 175 | 2009-05-15 | G | 2006-10-20 | Gas Turbine | GT | DFO NG | 175 | 175 | 203.6 | Fairfield | CT | 2010-06-01 | 2010-02-01 | 2009-05-13 | 345 kV line # 321 | MIS | FALSE | FALSE | ISO-NE |  | SWCT
| 176 | 2008-12-31 | G | 2006-10-20 | Wind | WT | WND | 145.5 | 145.5 | 145.5 | Coos | NH | 2008-12-30 | 2008-11-30 | 2008-12-29 | PSNH 115 kV Whitefield substation | MIS | FALSE | FALSE | ISO-NE |  | NH
| 177 | 2008-12-31 | G | 2006-10-23 | Gas Turbine | GT | DFO NG | 190 | 190 | 190 | Worcester | MA | 2011-06-01 | 2011-03-01 | 2008-12-23 | 115 kV bus at Millbury substation | MIS | FALSE | FALSE | ISO-NE |  | CMA |  | Document Posted
| 178 | 2017-05-25 09:42 | G | 2006-11-02 | Brockton Combined Cycle | CC | DFO NG | 332 | 332 | 371 | Plymouth | MA | 2019-05-31 | 2019-01-25 | 2017-05-25 | 115 kV F19 and E20 lines | NR | TRUE | TRUE | ISO-NE |  | SEMA | Document Posted | Document Posted |  | Document Posted
| 179 | 2009-05-22 | G | 2006-11-06 | Red Shield( Georgia Pacific/Old Town) | ST | WDS |  | 16 | 16 | Penobscot | ME | 2006-11-01 |  |  | BHE's Line 5 - 46 kV | MIS | FALSE | FALSE | ISO-NE |  | BHE
| 180 | 2017-04-21 06:49 | ETU | 2006-11-08 | Transmission Expansion | NA | N/A |  |  |  | N/A | CT |  |  | 2007-05-31 | CL&P Killingly 115 kV Substation | N/A | FALSE | FALSE |  |  | CT
| 180 | 2007-02-16 | ETU | 2006-11-08 | Transmission Expansion | NA | N/A |  |  |  | N/A | CT |  |  |  | CL&P Card 345 kV Substation | N/A | FALSE | FALSE |  |  | CT
| 181 | 2017-04-21 06:49 | ETU | 2006-11-09 | Transmission Expansion | NA | N/A | 0 |  |  | N/A | CT |  |  | 2009-09-02 | Lake Road 345 kV Substation | N/A | TRUE | FALSE | ISO-NE |  | CT
| 182 | 2009-05-15 | G | 2006-10-20 | Gas Turbine Capacity Increase ( See queue position | GT | DFO NG | 0 | 0 | 18.4 | Fairfield | CT | 2010-06-01 | 2010-02-01 | 2009-05-13 | 345 kV line # 321 | MIS | FALSE | FALSE | ISO-NE |  | SWCT
| 183 | 2010-10-01 | G | 2006-11-17 | Increase Existing Capacity | ST | NUC | 70 | 1225 | 1245 | New London | CT | 2008-11-01 | 2008-11-01 |  | CL&P Millstone 345 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | CT
| 184 | 2007-05-23 | G | 2006-11-17 | Gas Turbine Capacity Increase( #157) | GT | DFO NG |  | 140 | 140 | Middlesex | MA | 2008-12-01 | 2008-09-01 | 2007-05-23 | 337 Sandy Pond - Tewksbury 345 kV Line | MIS | FALSE | FALSE | ISO-NE |  | CMA
| 185 | 2013-02-21 | G | 2006-11-22 | Stetson Wind Phase I | WT | WND | 60 | 58.7 | 58.7 | Penobscot | ME | 2009-01-22 | 2008-12-01 |  | BHE Keene Road 115 kV substation | NR | TRUE | TRUE | ISO-NE |  | BHE
| 185 | 2013-02-05 | G | 2006-11-22 | Rollins Wind (Stetson Wind Phase II) | WT | WND | 27.8 | 27.8 | 27.8 | Penobscot | ME | 2011-07-26 | 2011-05-01 |  | BHE Keene Road 115 kV substation | NR | TRUE | TRUE | ISO-NE |  | BHE
| 186 | 2009-06-01 | G | 2006-12-01 | Gas Turbine | GT | DFO KER | 78 | 78 | 93 | New Haven | CT | 2011-12-31 | 2011-10-30 | 2009-05-29 | CL&P Shepaug 115 kV substation | MIS | FALSE | FALSE | ISO-NE |  | SWCT |  | Document Posted
| 186 | 2009-06-01 | G | 2006-12-01 | Hydro | HD | WAT | 6.5 | 48 | 48 | New Haven | CT | 2011-12-31 | 2011-10-30 | 2009-05-29 | CL&P Shepaug 115 kV substation | MIS | FALSE | FALSE | ISO-NE |  | SWCT
| 187 | 2009-02-11 | G | 2006-12-05 | Fuel Cell | FC | NG | 28.9 | 28.9 | 28.9 | Fairfield | CT | 2009-06-01 | 2009-06-01 | 2009-01-27 | UI Congress substation | MIS | FALSE | FALSE |  |  | SWCT
| 188 | 2007-02-01 | G | 2006-12-07 | Gas Turbine Capacity Increase( #178) | CC | DFO NG |  | 69 | 0 | Plymouth | MA | 2010-06-01 | 2010-04-01 | 2007-02-01 | 115 kV F19 and/or E20 lines | MIS | FALSE | FALSE |  |  | SEMA
| 189 | 2009-11-25 | G | 2006-12-15 | Covanta Haverhill Landfill Gas | IC | LFG |  | 1.6 | 1.6 | Essex | MA | 2007-12-05 |  |  | NGRID 23 kV circuit # 2371 from Ward Hill substati | MIS | TRUE | TRUE | ISO-NE |  | BOST |  | Document Posted |  |  |  | In Service
| 190 | 2009-05-15 | G | 2006-12-22 | Gas Turbine | GT | DFO KER NG | 156 | 156 | 200 | Hampden | MA | 2010-01-31 | 2009-10-30 | 2009-05-28 | W Mass. Mt. Tom 115 kV Substation | MIS | FALSE | FALSE |  |  | WMA
| 190 | 2009-05-12 | G | 2006-12-22 | Gas Turbine | GT | DFO KER NG | 39 | 39 | 50 | New London | CT | 2010-01-31 | 2009-10-30 | 2009-05-07 | CL&P Tunnel 115 kV Substation | MIS | TRUE | FALSE | ISO-NE |  | CT | Document Posted | Document Posted
| 190 | 2009-05-15 | G | 2006-12-22 | Gas Turbine | GT | DFO KER NG | 39 | 39 | 50 | Litchfield | CT | 2010-01-31 | 2009-10-30 | 2009-05-11 | CL&P Falls Village 69 kV Substation | MIS | TRUE | FALSE | ISO-NE |  | CT
| 190 | 2009-05-15 | G | 2006-12-22 | Gas Turbine | GT | DFO KER NG | 39 | 39 | 50 | New Haven | CT | 2010-01-31 | 2009-10-30 | 2009-05-07 | CL&P Stevenson 115 kV Substation | MIS | TRUE | FALSE | ISO-NE |  | SWCT |  | Document Posted
| 191 | 2007-05-14 | G | 2006-12-22 | Gas Turbine | GT | NG |  | 100 | 100 | Fairfield | CT | 2010-05-31 | 2010-03-31 | 2007-05-14 | UI 115 kV line #8909 | MIS | FALSE | FALSE |  |  | SWCT
| 191 | 2010-09-14 | G | 2006-12-22 | Biomass Project | ST | WDS | 26 | 26.25 | 26.75 | Litchfield | CT | 2013-03-01 | 2012-12-14 | 2010-09-13 | CL&P 115 kV line #1238 | CNR | TRUE | TRUE | ISO-NE |  | SWCT
| 192 | 2007-03-26 | G | 2006-12-28 | Combined Cycle | CC | DFO NG |  | 496 | 550 | Litchfield | CT | 2010-06-01 | 2010-04-01 | 2007-03-26 | CL&P Frostbridge Substation | MIS | FALSE | FALSE
| 192 | 2008-06-30 | G | 2006-12-28 | Combined Cycle | CC | DFO NG |  | 496 | 550 | Fairfield | CT | 2013-06-01 | 2013-04-01 | 2008-07-30 | CL&P Plumtree Substation | MIS | FALSE | FALSE |  |  | SWCT
| 192 | 2011-05-26 | G | 2007-01-03 | Salem Harbor Unit 3 Exciter Replacement | ST | BIT |  |  |  | Essex | MA | 2007-05-04 |  |  | Salem Switchyard | MIS | TRUE | TRUE | ISO-NE |  | BOST |  | Document Posted
| 193 | 2012-03-13 | G | 2007-01-05 | Ansonia Generation | CC | NG | 60 | 60 | 67 | New Haven | CT | 2013-09-09 | 2013-07-10 | 2012-03-13 | UI Ansonia 115 kV substation | CNR | TRUE | TRUE | ISO-NE |  | SWCT
| 194 | 2007-05-01 | G | 2007-01-08 | Gas Turbine | GT | NG |  | 177.1 | 189.3 | New Haven | CT | 2010-03-31 | 2010-01-15 | 2007-05-01 | UI 115 kV line # 8200 | MIS | FALSE | FALSE |  |  | SWCT
| 195 | 2009-09-25 | G | 2007-01-09 | Dartmouth Power Expansion | GT | KER NG | 24 | 24 | 24 | Bristol | MA | 2009-09-24 | 2009-08-14 |  | NSTAR 115 kV line #111 | CNR | TRUE | TRUE | ISO-NE |  | SEMA |  | Document Posted
| 196 | 2011-06-29 | G | 2007-01-16 | Northfield Mt Upgrade #3 | PS | WAT | 25 | 295 | 295 | Franklin | MA | 2011-06-17 | 2011-06-01 |  | W. Mass Northfield 345 kV substation | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | Executed | In Service
| 196 | 2012-06-06 | G | 2007-01-16 | Northfield Mt. Upgrade #2 | PS | WAT | 25 | 295 | 295 | Franklin | MA | 2012-05-25 | 2012-06-01 |  | W. Mass Northfield 345 kV substation | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | Executed | In Service
| 196 | 2014-05-21 10:18 | G | 2007-01-16 | Northfield Mt. Upgrade #4 | PS | WAT | 25 | 295 | 295 | Franklin | MA | 2014-05-21 | 2014-05-21 |  | W. Mass Northfield 345 kV substation | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | Executed | In Service
| 196 | 2016-02-22 09:43 | G | 2007-01-16 | Northfield Mt Upgrade #1 | PS | WAT | 25 | 295 | 295 | Franklin | MA | 2016-02-18 | 2015-08-31 |  | W. Mass Northfield 345 kV substation | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | Executed | In Service
| 196 | 2009-05-22 | G | 2007-01-26 | UMass Gas Turbine | GT | NG | 10.4 | 8.5 | 11.4 | Hampshire | MA | 2009-01-29 | 2008-05-06 |  | WMECO Podick substation 13.8 kV feeders | MIS | TRUE | TRUE | NU |  | WMA
| 197 | 2012-01-31 | G | 2007-01-31 | Record Hill Wind | WT | WND | 50.6 | 50.6 | 50.6 | Oxford | ME | 2012-01-31 | 2011-11-28 |  | 115kV Rumford Substation | CNR | TRUE | TRUE | ISO-NE |  | ME |  | Document Posted
| 198 | 2008-05-07 | G | 2007-02-08 | Biomass Project | ST | WDS |  | 56.4 | 67.5 | Coos | NH | 2009-06-01 | 2009-04-01 | 2008-05-07 | Near PSNH Lost Nation substation | MIS | FALSE | FALSE |  |  | NH
| 199 | 2010-03-19 | G | 2007-02-21 | Waterbury Generating Facility | GT | NG | 95.7 | 95.7 | 98.1 | New Haven | CT | 2009-06-26 | 2009-05-01 |  | CL&P Baldwin 115 kV substations | CNR | TRUE | TRUE | ISO-NE |  | SWCT
| 200 | 2013-08-12 09:00 | G | 2007-02-21 | Wind Project | WT | WND | 34 | 34 | 34 | Coos | NH | 2014-11-01 | 2014-08-01 | 2013-08-07 | New Hampshire Electric Coop 34.5 kV line | NA | FALSE | FALSE |  |  | NH
| 201 | 2009-12-15 | G | 2007-02-26 | Converts QP 164 to combined cycle facility and inc | CC | NG | 0 | 162 | 162 | Providence | RI | 2014-02-26 | 2013-12-31 | 2009-12-14 | 345 kV RISE Substation | CNR | FALSE | FALSE |  |  | RI
| 202 | 2010-10-22 | G | 2007-02-27 | Combined Cycle | CC | NG | 250 | 250 | 285 | Windham | CT | 2013-05-31 | 2013-01-31 | 2010-10-22 | CL&P 345 kV Lake Road substation | CNR | FALSE | FALSE |  | PD | RI
| 203 | 2009-07-01 | G | 2007-03-20 | Landfill Gas | IC | LFG | 6.3 | 6.3 | 6.3 | Coos | NH | 2008-12-31 | 2008-12-31 | 2009-07-01 | 34.5 kV feeder from Littleton | MIS | FALSE | FALSE |  |  | NH
| 204 | 2007-04-24 | G | 2007-03-30 | Gas Turbine | GT | DFO NG |  | 40 | 48 | Hartford | CT | 2009-12-31 | 2009-12-31 | 2007-04-27 | CL&P Windsor locks substation | MIS | FALSE | FALSE |  |  | CT
| 205 | 2007-10-03 | G | 2007-04-02 | Gas Turbine | GT | NG |  | 8.1 | 9.1 | Penobscot | ME | 2007-06-01 | 2007-06-01 | 2007-10-03 | BHE's Line 5 - 46 kV | MIS | FALSE | FALSE |  |  | ME
| 206 | 2009-05-22 | G | 2007-04-03 | Kimberly Clark-Unit 1 |  | NG |  | 28 | 28 | Litchfield | CT | 2008-05-05 |  |  | CL&P Rocky River Substation | MIS | TRUE | TRUE | NU |  | SWCT
| 206 | 2009-05-22 | G | 2007-04-03 | Kimberly Clark-Unit 2 |  | NG |  | 10.8 | 10.8 | Litchfield | CT | 2008-10-01 |  |  | CL&P Rocky River Substation | MIS | TRUE | TRUE | NU |  | SWCT
| 206 | 2009-05-22 | G | 2007-04-03 | Kimberly Clark-Unit 3 |  | NG | 4 | 4 | 4 | Litchfield | CT | 2009-01-05 | 2008-11-15 |  | CL&P Rocky River Substation | MIS | TRUE | TRUE | NU |  | SWCT
| 207 | 2012-01-30 | G | 2007-04-03 | Towantic Energy | CC | DFO NG | 452 | 452 | 540 | New Haven | CT | 2014-12-31 | 2014-06-30 | 2012-01-27 | CL&P 115 kV lines between Baldwin Junction and Bea | CNR | TRUE | TRUE | ISO-NE |  | SWCT
| 208 | 2007-12-12 | G | 2007-04-13 | Gas Turbine | GT | NG |  | 100 | 100 | Norfolk | MA | 2011-06-01 | 2010-12-31 | 2008-08-21 | 345 kV NEA Bellingham substation | MIS | FALSE | FALSE |  |  | RI
| 209 | 2009-05-22 | G | 2007-04-18 | Mount Tom Voltage Regulator Replacement | ST | BIT |  |  |  | Hampden | MA | 2007-06-30 |  |  | W Mass. Mt. Tom 115 kV Substation | MIS | FALSE | FALSE |  |  | WMA
| 210 | 2009-05-22 | G | 2007-04-30 | MATEP (Medical Area Total Energy Project)-modify i | OT | DFO NG |  |  |  | Suffolk | MA | 2007-12-11 |  |  | NSTAR Coburn Substation | MIS | FALSE | TRUE | NSTAR |  | BOST
| 211 | 2007-11-20 | G | 2007-05-08 | Combined Cycle | CC | DFO NG |  | 496 | 550 | Bristol | MA | 2010-06-01 | 2010-02-01 | 2007-11-20 | NSTAR 115 kV line #111 | MIS | FALSE | FALSE |  |  | SEMA
| 212 | 2020-06-09 08:18 | G | 2007-05-15 | Biomass Project | ST | WDS | 45 | 45 | 45 | Hillsborough | NH | 2010-02-28 | 2009-12-31 | 2009-05-28 | PSNH K-165 115 kV line | MIS | FALSE | FALSE |  |  | NH
| 213 | 2010-03-03 | G | 2007-05-15 | Gas Turbine | GT | NG | 159 | 158.5 | 184.7 | Worcester | MA | 2013-06-01 | 2013-02-01 | 2010-03-03 | ANP Blackstone 345 kV substation | CNR | FALSE | FALSE |  | PD | RI
| 213 | 2008-11-20 | G | 2007-05-15 | Gas Turbine | GT | NG | 159 | 158.5 | 184.7 | Worcester | MA | 2010-06-01 | 2010-02-01 | 2008-10-21 | ANP Milford 115 kV substation | MIS | FALSE | FALSE |  |  | RI
| 214 | 2007-10-15 | G | 2007-05-21 | Biomass Project | ST | WDS |  | 41 | 41 | Coos | NH | 2010-08-31 | 2010-06-30 | 2007-10-27 | PSNH 34.5 kV circuit from Lost Nation or Whitefiel | MIS | FALSE | FALSE |  |  | NH
| 214 | 2007-10-15 | G | 2007-05-21 | Biomass Project | ST | WDS |  | 41 | 41 | Coos | NH | 2010-08-31 | 2010-06-30 | 2007-10-15 | PSNH 115 kV S136 line | MIS | FALSE | FALSE |  |  | NH
| 215 | 2008-10-15 | G | 2007-05-30 | Combined Cycle | CC | DFO NG | 578 | 578 | 558 | Norfolk | MA | 2013-06-01 | 2013-02-01 | 2008-10-27 | NGRID 345 kV 344 Line | MIS | FALSE | FALSE |  |  | SEMA
| 215 | 2011-12-19 | G | 2007-05-24 | Longfellow Wind | WT | WND | 50 | 50 | 50 | Oxford | ME | 2013-12-01 | 2013-10-01 | 2011-12-14 | CMP 115 kV Rumford Substation | CNR | TRUE | TRUE | ISO-NE | PD | ME
| 216 | 2010-06-02 | G | 2007-06-08 | Combined Cycle | CC | DFO NG | 244 | 244 | 294 | Bristol | MA | 2013-12-31 | 2013-11-01 | 2010-05-28 | Cleary 115 kV substation | NR | TRUE | TRUE | ISO-NE | BL | SEMA |  | Document Posted
| 217 | 2010-04-09 | G | 2007-06-13 | Northfield Mt. Equipment Replacement | PS | WAT | 0 | 1180 | 1180 | Franklin | MA | 2008-10-20 | 2008-10-20 |  | W. Mass Northfield 345 kV substation | NA | TRUE | TRUE | ISO-NE |  | WMA
| 218 | 2009-02-12 | G | 2007-06-27 | Biomass Project ( Also see queue position #223) | ST | WDS | 62 | 41 | 48 | Berkshire | MA | 2010-12-01 | 2010-09-01 | 2009-01-30 | Doreen 115 kV substation or F132 115 kV line | MIS | FALSE | FALSE |  |  | WMA
| 219 | 2010-10-01 | G | 2007-07-06 | L'Energia | CC | DFO NG | 74 | 74 | 77 | Middlesex | MA | 2009-01-01 | 2008-11-15 |  | J162 115kV line between Tewksbury and Perry Street | MIS | TRUE | TRUE | ISO-NE |  | CMA
| 220 | 2009-05-22 | G | 2007-07-10 | Indeck Energy Alexandria | ST | WDS | 16.5 | 16.5 | 16.5 | Grafton | NH | 2009-01-31 | 2008-09-07 |  | 34.5 kV circuit from PSNH Peniwagewassett substat | MIS | TRUE | TRUE | NU |  | NH
| 221 | 2011-02-04 | G | 2007-07-18 | Wind Project | WT | WND | 34.9 | 34.9 | 34.9 | Penobscot | ME | 2012-12-30 | 2012-10-30 | 2011-02-04 | 115 kV line between Enfield and James River substa | NR | TRUE | TRUE | ISO-NE |  | BHE |  | Document Posted
| 222 | 2012-05-30 | G | 2007-07-16 | Meriden Gas Turbines | CC | DFO NG | 510 | 510 | 560 | New Haven | CT | 2015-06-01 | 2014-12-01 | 2012-05-30 | Haddam Neck-Southington 345 kV line | CNR | TRUE | TRUE | ISO-NE | BL | CT | Document Posted
| 223 | 2015-11-19 13:44 | G | 2007-07-25 | Increase to biomass project in queue position 218 | ST | WDS | 0 | 20.5 | 24 | Berkshire | MA | 2010-12-01 | 2010-09-01 | 2009-01-30 | Doreen 115 kV substation or F132 115 kV line | MIS | FALSE | FALSE |  |  | WMA
| 223 | 2007-11-07 | G | 2007-07-25 | Gas Turbine | GT | NG |  | 159 | 185 | New Haven | CT | 2010-05-06 | 2010-03-24 | 2007-11-07 | East Shore-Grand Ave 115 kV line | MIS | FALSE | FALSE |  |  | SWCT
| 224 | 2010-02-17 | G | 2007-08-10 | VPPSA Swanton Gas Turbine #1 | GT | DFO NG | 21 | 21.2 | 27.6 | Franklin | VT | 2010-02-12 | 2009-12-16 |  | Swanson Village 46 kV System | NA | TRUE | TRUE | ISO-NE |  | VT
| 224 | 2010-05-24 | G | 2007-08-10 | VPPSA Swanton Gas Turbine #2 | GT | DFO NG | 21 | 21.2 | 27.6 | Franklin | VT | 2010-05-24 | 2010-05-01 |  | Swanton Village 46 kV System | NA | TRUE | TRUE | ISO-NE |  | VT
| 225 | 2010-10-22 | G | 2007-08-13 | Combined Cycle Capacity Increase (See QP #202) | CC | NG | 161 | 411 | 412 | Windham | CT | 2013-05-31 | 2013-01-31 | 2010-10-22 | CL&P 345 kV Lake Road substation | CNR | FALSE | FALSE |  | PD | RI
| 225 | 2010-08-20 | G | 2007-09-04 | Wind Project-Phase 1( MPS Queue # 6) | WT | WND | 53.4 | 255 | 255 | N/A |  | 2010-09-01 |  |  | Maine Public Service System, upgrades include tap | NA | FALSE | FALSE | N/A
| 226 | 2009-07-23 | G | 2007-09-05 | Combined Cycle Capacity Increase/ Generator Change | CC | NG | 904 | 904 | 1010 | Rockingham | NH | 2013-06-30 | 2012-12-31 | 2009-07-14 | 345 kV Seabrook Substation | MIS | FALSE | FALSE |  |  | NH
| 227 | 2010-09-23 | G | 2007-09-26 | Bear Swamp Uprate - First Unit | PS | WAT | 43 | 333 | 333 | Berkshire | MA | 2012-03-31 | 2012-03-17 | 2010-09-23 | Bear Swamp 230 kV Substation | NR | TRUE | TRUE | ISO-NE |  | WMA
| 227 | 2010-09-23 | G | 2007-09-26 | Pump Storage Capacity Upgrade | PS | WAT | 43 | 333 | 333 | Berkshire | MA | 2013-03-30 | 2013-03-16 | 2010-09-23 | Bear Swamp 230 kV Substation | NR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted
| 227 | 2008-03-14 | ETU | 2007-09-28 | Increase Transfer South From Wyman Hydro | NA | N/A |  |  |  | N/A | ME |  |  |  | N/A | MIS | FALSE | FALSE |  |  | ME
| 228 | 2013-02-05 | G | 2007-10-09 | Dundee Wind | WT | WND | 27 | 27 | 30 | Penobscot | ME | 2011-07-26 | 2011-05-01 |  | BHE Keene Road Substation | NR | TRUE | TRUE | ISO-NE |  | BHE |  | Document Posted
| 229 | 2008-09-08 | G | 2007-10-15 | Biomass Project | ST | WDS |  | 41 | 41 | Coos | NH | 2013-12-31 | 2013-12-31 | 2008-09-08 | PSNH 34.5 kV circuit from Lost Nation or Whitefiel | MIS | FALSE | FALSE |  |  | NH
| 229 | 2011-10-19 | G | 2007-10-15 | CPD Berlin | ST | WDS | 29.5 | 29.5 | 29.5 | Coos | NH | 2013-08-31 | 2013-07-31 | 2011-10-11 | PSNH 115 kV Berlin Substation | CNR | TRUE | TRUE | ISO-NE | PD | NH | Document Posted | Document Posted |  | Document Posted
| 230 | 2009-08-20 | G | 2007-10-15 | GMP Essex Diesel | IC | DFO |  | 8 | 8 | Colchester | VT | 2007-10-30 |  |  | GMP Essex Substation | MIS | FALSE | TRUE | N/A |  | VT
| 231 | 2011-12-14 | G | 2007-10-25 | Brayton Point 3 Uprate( see 243) | ST | BIT | 30 | 642 | 663 | Bristol | MA | 2011-12-12 | 2011-12-11 |  | Brayton Point 345 kV Switchyard | NR | TRUE | TRUE | ISO-NE |  | RI
| 232 | 2008-01-29 | G | 2007-11-01 | Gas Turbine | GT | DFO NG |  | 250 | 275 | Hartford | CT | 2010-06-01 | 2010-04-01 | 2008-01-29 | CL&P 329 345 kV line or 1895 115 kV line | MIS | FALSE | FALSE |  |  | CT
| 233 | 2013-05-30 14:18 | G | 2007-11-02 | Rhode Island Landfill Gas Genco | CC | LFG | 27.9 | 32.6 | 36.8 | Providence | RI | 2013-05-25 | 2012-12-10 |  | NGRID 115 kV S171 line | CNR | TRUE | TRUE | NGRID |  | RI
| 234 | 2009-05-22 | G | 2007-11-07 | Moretown Landfill | IC | LFG | 4.8 | 4.8 | 4.8 | Washington | VT | 2008-09-04 | 2008-09-04 |  | Green Mountain Power 34 kV feeder | MIS | FALSE | FALSE |  |  | VT
| 235 | 2008-03-15 | G | 2007-11-15 | Gas Turbine | GT | NG |  | 58 | 65 | New Haven | CT | 2010-01-31 | 2010-01-01 | 2008-02-27 | CL&P 46 kV circuit from Baldwin Substation | MIS | FALSE | FALSE |  |  | SWCT
| 235 | 2008-06-30 | G | 2007-11-15 | Gas Turbine | GT | DFO NG |  | 170 | 196 | New London | CT | 2010-05-31 | 2010-05-01 | 2008-06-30 | CL&P Card Street substation | MIS | FALSE | FALSE |  |  | CT
| 236 | 2012-11-13 | G | 2007-11-30 | Pioneer Valley Energy Center | CC | DFO NG | 353 | 353 | 421 | Hampden | MA | 2015-09-28 | 2015-04-29 | 2012-11-01 | 115 kV line between Buck Pond and Pochassic substa | CNR | TRUE | TRUE | ISO-NE | BL | WMA |  | Document Posted |  |  | Executed
| 237 | 2010-01-14 | G | 2007-12-05 | Combined Cycle | CC | NG | 285 | 285 | 300 | Newport | RI | 2014-12-01 | 2014-08-01 | 2010-01-14 | 115 kV Tiverton Substation | CNR | FALSE | FALSE |  | PD | RI |  | Document Posted
| 238 | 2010-06-24 | G | 2007-12-07 | Barre Mass Landfill Gas | IC | LFG | 1.6 | 1.6 | 2 | Worcester | MA | 2011-03-11 | 2011-02-11 | 2010-06-17 | 13.8 kV distribution circuit | NR | TRUE | TRUE | ISO-NE |  | WMA
| 239 | 2008-11-12 | G | 2007-12-12 | Gas Turbine Capacity Increase ( See queue position | GT | DFO NG | 35 | 360 | 436 | Fairfield | CT | 2010-09-30 | 2010-06-30 | 2008-10-22 | UI 345 kV Singer Substation | MIS | FALSE | FALSE |  |  | SWCT
| 240 | 2010-10-27 | G | 2007-12-18 | Gas Turbine | GT | KER NG | 94 | 94 | 98 | New London | CT | 2013-06-01 | 2013-01-01 | 2010-10-27 | Montville Substation | CNR | FALSE | FALSE |  | BL | CT | Document Posted
| 241 | 2012-01-30 | G | 2007-12-31 | Towantic Energy increase | CC | DFO NG | 38 | 489 | 557 | New Haven | CT | 2014-12-31 | 2014-06-30 | 2012-01-27 | CL&P 115 kV lines between Baldwin Junction and Bea | CNR | TRUE | TRUE | ISO-NE |  | SWCT
| 242 | 2009-09-25 | G | 2008-01-03 | Biomass Project | ST | WDS | 20 | 20 | 20 | Cheshire | NH | 2013-10-30 | 2013-06-30 | 2009-09-18 | PSNH 115 kV N186 circuit | CNR | FALSE | FALSE |  |  | NH
| 243 | 2011-12-14 | G | 2008-01-04 | Increase to Steam Turbine Capacity Uprate (See QP | ST | BIT | 6 | 648 | 669 | Bristol | MA | 2011-12-12 | 2011-12-11 |  | Brayton Point 345 kV Switchyard | NR | TRUE | TRUE | ISO-NE |  | RI
| 244 | 2012-03-23 | G | 2008-01-03 | Wind | WT | WND | 117 | 117 | 117 | Somerset | ME | 2013-12-30 | 2013-10-01 | 2012-03-21 | CMP 115 kV Wyman substation | CNR | TRUE | TRUE | ISO-NE | BL | ME | Document Posted | Document Posted
| 245 | 2013-02-05 | G | 2008-01-11 | Stetson Wind II(Jimmey & Owl Mt.-UPC) See # 249 | WT | WND | 24 | 24 | 24 | Washington | ME | 2010-03-12 | 2010-01-15 |  | BHE Keene Road Substation | NR | TRUE | TRUE | ISO-NE |  | BHE
| 246 | 2008-12-31 | G | 2008-01-29 | Gas Turbine | GT | NG | 77 | 77 | 87 | Worcester | MA | 2011-06-01 | 2011-03-01 | 2008-12-31 | 115 kV bus at Millbury substation | MIS | FALSE | FALSE |  |  | CMA
| 247 | 2009-04-17 | G | 2008-01-31 | Reconnect Existing Hydro | HD | WAT | 0 | 4.1 | 4.1 | Orleans | VT | 2010-05-31 | 2010-05-01 | 2009-04-02 | VELCO Newport Substation 46 kV bus | MIS | FALSE | FALSE |  |  | VT
| 247 | 2009-04-17 | G | 2008-01-31 | Diesel generation | IC | DFO | 10.3 | 10.3 | 10.3 | Orleans | VT | 2009-05-01 | 2009-05-01 | 2009-04-02 | VELCO Newport Substation 46 kV bus | MIS | FALSE | FALSE |  |  | VT
| 248 | 2015-11-19 13:05 | G | 2008-02-07 | New Haven Harbor 2-4 | GT | DFO NG | 129.6 | 129.6 | 145.8 | New Haven | CT | 2012-05-23 | 2012-04-11 |  | UI East shore Substation 115 kV bus | CNR | TRUE | TRUE | ISO-NE | PD | CT | Document Posted
| 249 | 2013-02-05 | G | 2008-02-04 | Stetson Wind II(Jimmey & Owl Mt.-UPC) | WT | WND | 2.2 | 26.2 | 26.2 | Washington | ME | 2010-03-12 | 2010-01-15 |  | BHE Keene Road Substation | NR | TRUE | TRUE | ISO-NE |  | BHE
| 250 | 2011-11-30 | G | 2008-02-13 | Hamilton Sundstrand | GT | NG | 5 | 4.9 | 6.1 | Hartford | CT | 2011-10-01 | 2011-09-30 |  | CL&P Windsor Locks Substation | NA | FALSE | TRUE |  |  | CT
| 251 | 2014-06-18 10:37 | G | 2008-02-15 | Burgess BioPower | ST | WDS | 58.7 | 58.7 | 58.7 | Coos | NH | 2014-06-17 | 2013-10-25 |  | PSNH Eastside(Berlin) Substation | CNR | TRUE | TRUE | ISO-NE | PD | NH | Document Posted | Document Posted |  |  | Executed | In Service
| 252 | 2010-07-30 | G | 2008-02-13 | Foxwoods Central Plant | GT | NG | 13.2 | 13.2 | 17.6 | New London | CT | 2010-07-15 | 2010-04-30 |  | CL&P 23 kV feeders from Tunnel and Mystic Substati | NA | TRUE | TRUE | NU |  | CT
| 253 | 2009-06-17 | G | 2008-03-11 | Combined Cycle | CC | DFO | 269 | 269 | 310 | Fairfield | CT | 2011-06-01 | 2011-02-01 | 2009-06-01 | CL&P 115 kV 1876 line | MIS | FALSE | FALSE |  |  | SWCT
| 254 | 2009-08-31 | G | 2008-03-10 | Wind | WT | WND | 19.5 | 19.5 | 19.5 | Penobscot | ME | 2010-11-01 | 2010-11-01 | 2009-08-25 | CMP 115 kV line # 203 | CNR | FALSE | FALSE |  |  | ME
| 254 | 2015-09-03 08:36 | G | 2008-03-25 | Wind Project | WT | WND | 12.5 | 12.5 | 12.5 | Berkshire | MA | 2016-11-30 | 2016-10-31 | 2015-09-02 | WMECO Berkshire substation 23 kV circuit | NA | FALSE | FALSE |  |  | WMA
| 255 | 2009-12-03 | G | 2008-03-31 | Wind | WT | WND | 50 | 50 | 50 | Grafton | NH | 2010-12-31 | 2010-10-01 | 2009-09-30 | 115 kV Plymouth substation | CNR | FALSE | FALSE |  |  | NH
| 255 | 2012-11-13 | G | 2008-03-31 | Distribution Wind Alternative | WT | WND | 2 | 50 | 50 | Grafton | NH | 2012-12-31 | 2012-10-01 |  | PSNH Ashland 34.5 kV | NA | FALSE | FALSE |  |  | NH
| 256 | 2013-03-26 12:53 | G | 2008-04-04 | Steam Turbine | ST | WDS | 20 | 20 | 20 | Merrimack | NH | 2013-03-31 | 2012-12-30 | 2013-03-02 | Unitil 34.5kV line from PSNH Garvins station to UE | NA | FALSE | FALSE |  |  | NH
| 257 | 2013-09-16 10:20 | G | 2008-04-14 | Wind Project-Phase 4( MPS Queue # 8) | WT | WND | 250 | 250 | 250 | N/A | ME | 2013-09-01 |  | 2013-09-03 | Maine Public Service System, upgrades include tap | NA | FALSE | FALSE | MPS |  | BHE
| 257 | 2013-09-16 10:21 | G | 2008-04-14 | Wind Project-Phase 5( MPS Queue # 9) | WT | WND | 150 | 150 | 150 | N/A | ME | 2013-09-01 | 2013-09-03 | 2013-09-03 | Maine Public Service System, upgrades include tap | NA | FALSE | FALSE | MPS |  | BHE
| 258 | 2015-11-19 13:47 | G | 2008-04-15 | Merrimack Unit 2 Uprate | ST | BIT | 4.65 | 327.5 | 337 | Merrimack | NH | 2008-05-26 |  |  | PSNH Merrimack Substation | MIS | FALSE | FALSE |  |  | NH
| 259 | 2010-08-19 | G | 2008-05-07 | Combined Cycle | CC | NG | 27 | 551 | 616.3 | Providence | RI | 2012-06-01 | 2012-06-01 | 2010-08-11 | 115 kV RISE Substation | CNR | FALSE | FALSE |  | PD | RI
| 259 | 2009-02-12 | G | 2008-05-07 | Combined Cycle | CC | DFO NG | 27 | 303.3 | 340.2 | Norfolk | MA | 2010-06-01 | 2010-06-01 | 2009-01-28 | 345 kV NEA Bellingham Substation | MIS | FALSE | FALSE |  |  | RI
| 260 | 2009-03-19 | G | 2008-05-08 | Wind | WT | WND | 450 | 450 | 450 | N/A | RI | 2013-12-31 | 2012-06-30 | 2009-02-27 | Brayton Point 115 kV bus or Dexter 115 kV bus | MIS | FALSE | FALSE |  |  | RI
| 260 | 2009-03-19 | G | 2008-05-08 | Wind | WT | WND | 0 | 450 | 450 | N/A | RI | 2013-12-31 | 2012-06-30 | 2009-02-27 | Kent County 115 kV bus or Davisville 115 kV bus | MIS | FALSE | FALSE |  |  | RI
| 261 | 2008-11-07 | G | 2008-05-19 | Combined Cycle | CC | NG | 221.6 | 440 | 497 |  | ME | 2013-12-31 | 2013-06-30 | 2008-11-07 | Yarmouth Substation 115 kV bus | MIS | FALSE | FALSE |  |  | ME
| 262 | 2011-11-10 | G | 2008-05-23 | Rhode Island Landfill Gas Genco Increase (see QP # | CC | LFG | 6 | 45.9 | 50.1 | Providence | RI | 2013-09-01 | 2013-09-01 | 2011-11-09 | NGRID 115 kV S171 line | CNR | TRUE | TRUE | NGRID |  | RI |  | Document Posted
| 263 | 2010-03-25 | G | 2008-05-27 | Wind | WT | WND | 385 | 385 | 385 | Washington | RI | 2012-12-01 | 2011-06-01 | 2010-03-24 | West Kingston Substation | CNR | FALSE | FALSE |  | BL | RI
| 264 | 2008-07-10 | G | 2008-06-04 | Landfill Gas | IC | LFG | 0.8 | 0.8 | 0.8 |  | NH | 2008-11-30 | 2008-11-01 | 2008-07-10 | NHEC 12.5 kV circuit | MIS | FALSE | FALSE |  |  | NH
| 264 | 2009-09-28 | G | 2008-06-11 | Biomass Project | ST | WDS | 10 | 10 | 10 | Grafton | NH | 2010-06-01 | 2010-06-01 | 2009-09-28 | PSNH 34.5 kV circuit #343 | NA | FALSE | FALSE |  |  | NH
| 265 | 2013-12-05 09:09 | G | 2008-06-16 | MATEP - Third CTG | GT | DFO NG | 12.5 | 12.5 | 14 | Suffolk | MA | 2014-06-01 | 2014-05-01 | 2013-01-07 | NSTAR Brighton Substation | CNR | TRUE | TRUE | NSTAR |  | BOST
| 266 | 2009-05-01 | G | 2008-06-19 | Wind | WT | WND | 34 | 34 | 34 | Orleans | VT | 2011-12-31 | 2011-09-15 | 2009-04-13 | CVPS Lowell Substation | MIS | FALSE | FALSE |  |  | VT
| 267 | 2009-03-19 | G | 2008-06-24 | Gas Turbine Capacity Increase ( See queue position | GT | DFO NG | 175 | 175 | 222 | Fairfield | CT | 2011-06-01 | 2011-02-01 | 2009-03-09 | 345 kV line # 321 | MIS | FALSE | FALSE |  |  | SWCT
| 268 | 2009-05-01 | G | 2008-07-08 | Wind ( increase in queue position 266) | WT | WND | 8.5 | 8.5 | 8.5 | Orleans | VT | 2011-12-31 | 2011-09-15 | 2009-04-13 | CVPS Lowell Substation | MIS | FALSE | FALSE |  |  | VT
| 269 | 2011-08-03 | G | 2008-07-14 | Indian River Power | HD | WAT | 1.28 | 1.28 | 1.28 | Hampden | MA | 2011-08-02 | 2011-03-31 |  | WMELCO 23 kV circuit | NR | TRUE | TRUE | NU |  | WMA |  | Document Posted
| 270 | 2011-03-31 | G | 2008-07-17 | Pumped Storage Project | PS | WAT | 1000 | 1000 | 1000 | Wiscasset | ME | 2014-06-01 | 2014-06-01 | 2011-03-31 | Maine Yankee 345 kV substation | NR | FALSE | FALSE |  | BL | ME | Document Posted
| 271 | 2017-04-21 06:53 | ETU | 2008-07-30 | Two terminal, 1000 MW , 500 kV, dc line | NA | N/A | 0 |  |  | N/A |  | 2014-03-31 |  | 2009-05-12 | Hertel S/S in Quebec or Clay S/S in NY and Norwalk | N/A | FALSE | FALSE
| 271 | 2010-01-29 | ETU | 2008-07-30 | Two terminal, 1000 MW , 500 kV, dc line | NA | N/A | 0 |  |  | N/A |  | 2014-03-31 |  |  | Hertel S/S in Quebec or Clay S/S in NY and Glenbro | N/A | FALSE | FALSE
| 271 | 2010-07-16 | ETU | 2008-07-30 | Two terminal, 1000 MW , 500 kV, dc line | NA | N/A | 0 |  |  | N/A |  | 2014-03-31 |  |  | Hertel S/S in Quebec or Clay S/S in NY and Singer | N/A | FALSE | FALSE
| 271 | 2009-10-22 | TS | 2008-08-01 | MPS RNS Application | NA | N/A | 0 |  |  | Aroostoock | ME | 2010-10-01 |  |  | N/A | N/A | FALSE | FALSE |  |  | BHE
| 272 | 2009-06-17 | G | 2008-08-01 | Wind | WT | WND | 64 | 64 | 64 | Franklin | ME | 2012-08-01 | 2012-06-01 | 2009-06-15 | CMP Rumford or Bigelow Substation | MIS | FALSE | FALSE |  |  | ME | Document Posted | Document Posted |  |  | IA Filed Unexecuted
| 272 | 2008-10-03 | G | 2008-08-01 | Wind | WT | WND | 0 | 150 | 150 | Aroostoock | ME | 2011-08-01 | 2011-05-01 | 2008-10-03 | BHE Millinocket Substation | MIS | FALSE | FALSE |  |  | BHE
| 272 | 2009-04-15 | G | 2008-08-01 | Wind | WT | WND | 0 | 150 | 150 | Aroostoock | ME | 2011-08-01 | 2011-05-01 | 2009-03-10 | BHE Powersville Substation | MIS | FALSE | FALSE |  |  | BHE
| 272 | 2010-02-16 | G | 2008-08-01 | Wind | WT | WND | 85 | 85 | 85 | Somerset | ME | 2012-08-01 | 2012-06-01 | 2010-02-03 | CMP 115 KV LINE 222 | CNR | FALSE | FALSE |  | PD | ME | Document Posted
| 272 | 2009-05-01 | G | 2008-08-01 | Wind | WT | WND | 128 | 128 | 128 | Aroostoock | ME | 2013-12-31 | 2013-10-31 | 2009-04-21 | BHE 345 kV 396 line | MIS | FALSE | FALSE |  |  | BHE
| 272 | 2015-10-29 08:43 | G | 2008-08-01 | Oakfield II Wind - Keene Road | WT | WND | 135.5 | 135.5 | 135.5 | Aroostoock | ME | 2015-10-29 | 2015-07-29 |  | BHE Keene Road Substation | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed | In Service
| 273 | 2019-11-01 08:56 | G | 2008-08-03 | Palmer Renewable Energy | ST | WDS | 36.7 | 36.7 | 37 | Hampden | MA | 2020-07-15 | 2020-06-15 | 2019-10-16 | 115 kV line near E. Springfield substation | NR | TRUE | TRUE | ISO-NE | BL | WMA | Document Posted | Document Posted |  |  | Executed | Under Construction
| 274 | 2012-10-04 | G | 2008-08-07 | GMP Generator Replacement | GT | DFO NG | 29.5 | 41.5 | 48.7 | Chittenden | VT | 2014-06-01 | 2014-05-01 | 2012-10-14 | GMP Gorge Substation | CNR | TRUE | TRUE | ISO-NE |  | VT |  | Document Posted
| 274 | 2009-03-19 | TS | 2008-08-25 | Wind project point-to-point application | NA | N/A | 0 | 100 | 100 | Aroostoock | ME | 2011-10-01 |  |  | N/A | N/A | FALSE | FALSE |  |  | BHE
| 275 | 2017-04-21 06:54 | ETU | 2008-08-27 | Two terminal, 2000 MW , 500 kV, dc line | NA | N/A | 0 |  |  | N/A |  | 2014-03-31 |  | 2008-09-15 | Maine Yankee Substation, South Boston Substation | N/A | FALSE | FALSE
| 276 | 2014-09-19 13:18 | G | 2008-09-02 | Deerfield Wind | WT | WND | 30 | 30 | 30 | Bennington | VT | 2013-12-31 | 2013-10-01 | 2014-09-11 | Y-25 North, 69 kV line between Searsburg and Benni | NR | TRUE | TRUE | ISO-NE | BL | WMA | Document Posted | Document Posted |  |  | Executed
| 277 | 2009-03-19 | G | 2008-09-12 | Combined Cycle | CC | DFO NG | 695 | 695 | 695 | Fairfield | CT | 2013-06-01 | 2013-01-15 | 2009-02-13 | CL&P 345 KV 321 line | MIS | FALSE | FALSE |  |  | SWCT
| 277 | 2014-12-22 13:16 | G | 2008-09-22 | Combined Cycle (QP310 in NYISO Queue) | CC | NG | 1002 | 1002 | 1115 | Dutchess | NY | 2018-01-31 | 2017-07-01 | 2014-12-18 | Pleasant Valley - Long Mtn 345 kV | NA | FALSE | FALSE
| 278 | 2014-06-13 12:52 | ETU | 2008-09-26 | Two terminal, 1000 MW , 500 kV, dc line | NA | N/A | 0 |  |  | N/A | MA | 2017-03-31 | 2017-03-31 | 2014-06-13 | Maine Yankee Substation, South Boston Substation | N/A | FALSE | FALSE |  |  | BOST |  | Not Started
| 279 | 2009-03-19 | G | 2008-09-30 | Biomass | ST | WDS | 30 | 30 | 30 | Windsor | VT | 2011-05-01 | 2011-03-01 | 2009-02-20 | CVPS 46kV circuit in Springfield area | MIS | FALSE | FALSE |  |  | VT
| 280 | 2010-09-24 | G | 2008-10-02 | Wind | WT | WND | 180 | 180 | 180 | Coos | NH | 2011-09-01 | 2011-07-01 | 2010-09-24 | PSNH W-179 115 kV | CNR | FALSE | FALSE |  | PD | NH | Document Posted
| 281 | 2010-03-31 | G | 2008-10-06 | Wind | WT | WND | 85 | 85 | 85 | Rutland | VT | 2011-09-01 | 2011-07-01 | 2010-03-30 | VELCO 115 kV K34 line | CNR | FALSE | FALSE |  | BL | VT | Document Posted
| 281 | 2009-02-12 | G | 2008-10-07 | Equipment Addition | CC | NG | 45 |  |  | Windham | CT | 2009-01-30 | 2008-06-01 |  | CL&P 345 kV Lake Road substation | MIS | FALSE | FALSE |  |  | RI
| 282 | 2011-06-29 | G | 2008-10-15 | Biomass Project | ST | WDS | 49.7 | 49.7 | 51.5 | Franklin | MA | 2014-02-01 | 2013-11-01 | 2011-06-28 | 115 kV line near Montage or Fench King substations | CNR | FALSE | FALSE |  | BL | WMA
| 283 | 2015-02-17 08:16 | ETU | 2008-10-20 | 1100 MW HVDC Line | NA | N/A | 0 |  |  | N/A | MA | 2017-06-30 | 2017-03-30 | 2015-02-16 | Orrington ME and BostonMA | N/A | FALSE | FALSE |  |  | BOST |  | Not Started
| 284 | 2012-04-10 | G | 2008-10-22 | Seabrook LP Turbine Blade replacement | ST | NUC | 13 | 1257 | 1257 | Rockingham | NH | 2012-04-05 | 2010-12-31 |  | 345 kV Seabrook Substation | CNR | TRUE | TRUE | ISO-NE |  | NH |  |  |  |  | Executed
| 285 | 2012-08-29 | G | 2008-10-24 | Gas Turbine | GT | NG | 35 | 35 | 35 | Penobscot | ME | 2014-07-31 | 2014-06-30 | 2012-08-29 | BHE Powersville substation | CNR | TRUE | FALSE | ISO-NE | PD | BHE
| 286 | 2009-09-30 | G | 2008-12-05 | Gas Turbine | GT | NG | 187.5 | 187.5 | 199 | Worcester | MA | 2012-06-01 | 2012-02-01 | 2009-09-30 | 115 kV bus at Millbury substation | MIS | FALSE | FALSE |  |  | CMA
| 287 | 2015-09-16 16:49 | G | 2008-12-18 | Saddleback Ridge Wind Project | WT | WND | 33 | 33 | 33 | Franklin | ME | 2015-09-15 | 2015-08-15 |  | 115kV Line 229 | NR | TRUE | TRUE | ISO-NE | BL | ME |  | Document Posted |  |  | Executed | In Service
| 288 | 2009-09-25 | TS | 2008-12-18 | Local Service Application - 87 MW |  |  | 0 |  |  | Somerset | ME | 2009-09-01 |  |  | N/A | N/A | TRUE | FALSE | ISO-NE |  | ME |  | Document Posted
| 289 | 2013-08-05 15:02 | G | 2009-01-08 | Fuel Cell | FC | NG | 9 | 9 | 9 | New Haven | CT | 2012-06-15 | 2012-05-15 | 2013-08-05 | UI&#39;&#39;s Milvon substation | NA | TRUE | TRUE | UI |  | SWCT
| 289 | 2011-11-10 | G | 2009-01-08 | Sikorsky Aircraft | GT | NG | 10.265 | 10.265 | 10.265 | Fairfield | CT | 2011-10-05 | 2011-07-24 |  | UI's Trap Falls substation | NA | TRUE | TRUE | UI |  | SWCT
| 289 | 2010-06-02 | G | 2009-01-08 | Yale University - Sterling Power Plant | GT | NG | 17.6 | 17.6 | 17.6 | New Haven | CT | 2010-05-26 | 2010-05-01 |  | UI's Water Street substation | NA | TRUE | TRUE | UI |  | SWCT
| 290 | 2010-07-29 | G | 2009-01-15 | Wind | WT | WND | 18 | 18 | 18 | Oxford | ME | 2010-12-30 | 2010-09-30 | 2010-07-29 | CMP Woodstock Substation | CNR | TRUE | TRUE | ISO-NE | BL | ME
| 290 | 2011-12-21 | G | 2009-01-15 | Spruce Mountain Wind | WT | WND | 18 | 18 | 18 | Oxford | ME | 2011-12-21 | 2011-11-30 |  | CMP Woodstock substation | NA | TRUE | TRUE | ISO-NE |  | ME
| 291 | 2010-06-24 | G | 2009-01-21 | Merrimack Unit 2 Second Uprate | ST | BIT | 17.175 | 340 | 353.5 | Merrimack | NH | 2010-06-17 | 2010-06-01 |  | PSNH Merrimack Substation | CNR | TRUE | TRUE | ISO-NE | BL | NH
| 292 | 2010-02-01 | G | 2009-01-30 | Biomass Project | ST | WDS | 49.7 | 49.7 | 51.5 | Berkshire | MA | 2013-10-01 | 2013-07-01 | 2010-01-26 | Doreen 115 kV substation of F132 115 kV line | CNR | FALSE | FALSE |  | BL | WMA
| 293 | 2010-05-19 | G | 2009-01-30 | Red Shield Acquisition - Hydro | HD | WAT | 0 | 5 | 5 | Penobscot | ME | 2009-07-20 |  |  | BHE's Line 5 - 46 kV | CNR | FALSE | FALSE |  |  | ME
| 293 | 2010-05-19 | G | 2009-01-30 | Red Shield Acquisition - Biomass | ST | WDS | 0 | 13 | 16 | Penobscot | ME | 2009-07-20 |  |  | BHE's Line 5 - 46 kV | CNR | FALSE | FALSE |  |  | ME
| 294 | 2015-07-29 15:38 | G | 2009-02-05 | Wind | WT | WND | 20 | 20 | 20 | Washington | RI | 2012-06-30 | 2012-04-30 | 2009-05-07 | NGRID 34.5 kV 3302 line | NS | FALSE | FALSE |  |  | RI
| 295 | 2015-07-29 15:39 | G | 2009-02-09 | Combined Cycle | CC | NG | 898 | 898 | 1012 | Plymouth | MA | 2015-03-01 | 2014-09-01 | 2009-05-08 | 345 kV 322 Line | CNR | FALSE | FALSE |  |  | SEMA
| 296 | 2009-07-31 | G | 2009-02-20 | Biomass | ST | WDS | 30 | 30 | 30 | Windsor | VT | 2011-05-01 | 2011-03-01 | 2009-07-30 | CVPS 46 kV circuit in Springfield Area | MIS | FALSE | FALSE |  |  | VT
| 296 | 2010-05-19 | G | 2009-02-23 | Wind Farm | WT | WND | 12 | 12 | 12 | Chittenden | VT | 2010-12-31 | 2010-12-31 |  | CVPS 34.5 kV Fairfax - Milton line | NA | FALSE | FALSE |  |  | VT
| 296 | 2013-03-20 13:58 | G | 2009-03-20 | Salem Harbor 2 Exciter Replacement | ST | BIT | 0 | 0 | 0 | Essex | MA | 2009-11-15 | 2009-11-15 |  | Salem Switchyard | NA | TRUE | TRUE | ISO-NE |  | BOST |  |  |  |  | Executed
| 297 | 2012-01-11 | G | 2009-03-25 | Wind | WT | WND | 201.6 | 201.6 | 201.6 | Aroostook | ME | 2013-10-01 | 2013-07-01 | 2012-01-09 | MEPCO Line at Haynesville, ME | CNR | FALSE | FALSE |  | PD | BHE
| 298 | 2009-05-12 | G | 2009-04-15 | Wind Uprate (see QP290) | WT |  | 1.5 | 1.5 | 1.5 | Oxford | ME | 2010-11-30 | 2010-09-30 | 2009-05-12 | CMP Woodstock Station | NR | FALSE | FALSE |  |  | ME
| 299 | 2012-04-10 | G | 2009-05-11 | Seabrook PSS Enabling | ST | NUC | 0 | 0 | 0 | Rockingham | NH | 2009-11-01 | 2009-11-01 |  | 345 kV Seabrook substation | CNR | TRUE | TRUE | ISO-NE | BL | NH |  |  |  |  | Executed
| 300 | 2017-11-29 08:42 | G | 2009-05-14 | Canton Mountain Winds | WT | WND | 19.25 | 19.25 | 19.25 | Oxford | ME | 2017-11-29 | 2017-10-18 |  | 229 Line near Riley Substation | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed | In Service
| 301 | 2015-11-19 13:49 | G | 2009-05-28 | Dundee Wind Increase | WT | WND | 3.9 | 3.9 | 3.9 | Penobscot | ME | 2011-07-26 | 2011-05-01 |  | BHE Keene Rd Substation | NR | TRUE | TRUE | ISO-NE |  | BHE
| 302 | 2011-04-26 | G | 2009-06-16 | Wind Alternative (see 272) | WT | WND | 0 | 150 | 150 | Aroostook | ME | 2012-12-31 | 2012-09-01 | 2011-04-26 | BHE/MEPCO Line | CNR | FALSE | FALSE |  | PD | BHE
| 303 | 2009-08-20 | G | 2009-06-23 | Biomass | ST | WDS | 7.6 | 7.6 | 7.6 | Cumberland | ME | 2010-03-01 | 2010-02-16 | 2009-08-18 | Rigby/Pleasant Hill 34.5 kV Line | NR | FALSE | FALSE |  |  | SME
| 303 | 2009-09-28 | G | 2009-06-24 | Biomass | ST |  | 9.5 | 9.5 | 9.5 | Androscoggin | ME |  |  | 2009-07-10 | TBD | NR | FALSE | FALSE |  |  | ME
| 304 | 2009-09-28 | G | 2009-07-06 | Biomass | IC | WDS | 4.9 | 4.9 | 4.9 | Cumberland | ME | 2012-04-30 | 2012-01-30 | 2009-09-16 | CMP Moshers 34.5 kV | CNR | FALSE | FALSE |  |  | SME
| 305 | 2015-11-19 13:51 | G | 2009-07-10 | Internal Combustion | IC | DFO | 10 | 15.5 | 15.5 | Dukes | MA | 2013-05-31 | 2013-04-30 | 2009-10-20 | NSTAR 23 kV Edgartown0Vineyard Haven Rd Line | CNR | FALSE | FALSE |  |  | SEMA
| 305 | 2011-07-29 | G | 2009-07-10 | Wind | WT | WND | 66 | 66 | 66 | Grafton/Merrimack | NH | 2012-12-31 | 2012-10-01 | 2011-07-29 | Pemigewassett 115 kV Substation | CNR | FALSE | FALSE |  | PD | NH | Document Posted
| 305 | 2011-07-29 | G | 2009-07-10 | Wind (non-FERC alternative) | WT | WND | 0 | 66 | 66 | Grafton/Merrimack | NH | 2012-12-31 | 2012-10-01 |  | Pemigewassett 34.5 kV Substation | NA | FALSE | FALSE |  |  | NH
| 306 | 2010-08-04 | G | 2009-07-13 | Hydro | HD | WAT | 3.35 | 3.35 | 3.35 | Hampden | MA | 2014-04-01 | 2014-01-01 | 2010-08-04 | HG&E Prospect 24B substation | CNR | FALSE | FALSE |  |  | WMA
| 306 | 2013-01-18 | G | 2009-07-13 | Overflow #3 | HD | WAT | 0.5 | 0.5 | 0.5 | Hampden | MA | 2013-11-30 | 2013-10-31 |  | HG&E Holyoke Substation | CNR | FALSE | FALSE |  |  | WMA
| 307 | 2012-05-30 | G | 2009-07-14 | Diesel | IC | DFO | 9.125 | 9.125 | 9.125 | Essex | VT | 2013-05-30 | 2013-04-01 | 2012-05-30 | NGRID 34.5 kV Moore/Gilman Line | CNR | TRUE | FALSE | ISO-NE | CD | VT |  | Document Posted
| 307 | 2009-09-28 | G | 2009-07-14 | Wind Expansion | WT | WND | 45 | 45 | 45 | Franklin | ME | 2011-10-31 | 2011-09-01 | 2009-09-10 | Section 267 | NR | FALSE | FALSE |  |  | ME
| 308 | 2011-08-08 | G | 2009-08-28 | Wind | WT | WND | 28.8 | 28.8 | 28.8 | Washington | RI | 2012-12-31 | 2012-09-30 | 2011-08-08 | NGRID 3302 Feeder | NR | FALSE | FALSE |  | CD | RI |  | Document Posted
| 309 | 2009-09-28 | G | 2009-09-01 | Hydro Uprate | HD | WAT | 0.975 | 34.038 | 34.038 | Lewiston | ME | 2009-12-01 | 2009-11-01 | 2009-09-28 | CMP Gulf Island 115 kV | CNR | FALSE | FALSE |  |  | ME
| 310 | 2012-11-15 | G | 2009-09-10 | Kibby Wind Expansion | WT | WND | 33 | 33 | 33 | Franklin | ME | 2014-10-15 | 2014-09-01 | 2012-11-15 | Section 267 to CMP Bigalow | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 311 | 2012-11-19 | G | 2009-09-15 | Kingdom Community Wind | WT | WND | 61.5 | 61.5 | 61.5 | Orleans | VT | 2012-11-16 | 2012-08-29 |  | VEC Lowell 46 kV station | CNR | TRUE | TRUE | ISO-NE | PD | VT |  | Document Posted |  |  | IA Filed Unexecuted
| 312 | 2011-10-19 | G | 2009-09-18 | Biomass | ST | WDS | 20 | 20 | 20 | Cheshire | NH | 2013-10-30 | 2013-06-30 | 2011-10-18 | PSNH 34.5 kV to Winchester substation | CNR | FALSE | FALSE |  | CD | NH
| 313 | 2012-09-12 | G | 2009-10-08 | Gulf Island Unit 1 Increase | HW | WAT | 0.975 | 33.945 | 34.175 | Androscoggin | ME | 2012-08-24 | 2012-08-23 |  | CMP Gulf Island 115 kV | CNR | FALSE | TRUE |  |  | SME
| 313 | 2011-05-10 | G | 2009-10-08 | Gulf Island Unit 3 Increase | HW | WAT | 0.569 | 34.514 | 34.744 | Androscoggin | ME | 2011-04-26 | 2010-12-18 |  | CMP Gulf Island 115 kV | CNR | FALSE | TRUE |  |  | SME
| 314 | 2015-02-17 08:17 | ETU | 2009-10-16 | 400 MW 150 kV HVDC Line | NA | N/A |  |  |  | Colchester | VT | 2018-06-01 | 2018-06-01 | 2015-02-16 | NYPA 230.115 kV substation in Plattsburg, NY to near VELCO 345 kV New Haven Substation | N/A | FALSE | FALSE |  |  | VT |  | In Progress
| 314 | 2009-12-03 | G | 2009-10-16 | Combined Cycle | CC | NG | 410 | 410 | 455 | Plymouth | MA | 2015-05-01 | 2014-12-01 | 2009-12-02 | NSTAR 127 and 128 Lines or new 115 kV | CNR | FALSE | FALSE |  |  | SEMA
| 314 | 2010-01-27 | TS | 2009-10-16 | RNS Application | NA | N/A |  |  |  | Aroostook | ME | 2011-12-01 |  |  | N/A | N/A | FALSE | FALSE |  |  | BHE
| 315 | 2012-06-15 | G | 2009-10-20 | Cresent Hydroelectric Project Uprate | HD | WAT | 0.667 | 1.667 | 1.667 | Hampden | MA | 2012-06-08 |  |  | WMECO 19J1 23 kV line | CNR | FALSE | FALSE |  | BL | WMA |  |  |  |  | Executed
| 316 | 2011-01-10 | G | 2009-11-02 | Red Shield Acquisition #5 | GT | NG WDS | 9.5 | 26.15 | 27.25 | Penobscot | ME | 2010-10-04 | 2010-09-15 |  | BHE Line 5 - 46 kV | CNR | TRUE | TRUE | BHE |  | ME
| 317 | 2013-02-05 | G | 2009-11-04 | Bull Hill Wind Phase I | WT | WND | 34.485 | 34.485 | 34.485 | Hancock | ME | 2012-10-31 | 2012-10-04 |  | BHE Line 66 | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed
| 317 | 2011-08-22 | G | 2009-11-04 | Wind | WT | WND | 46.8 | 81 | 81 | Hancock | ME | 2013-12-31 | 2013-10-01 | 2011-08-22 | BHE Line 66 | CNR | FALSE | FALSE |  | PD | BHE |  | Document Posted
| 318 | 2010-05-13 | G | 2009-11-24 | Algonquin Power Windsor Locks Cogeneration Facilit | GT | DFO NG | 0 | 47.5 | 47.5 | Hartford | CT | 2010-04-14 | 2010-04-14 |  | CL&P Windsor Locks Substation | CNR | FALSE | FALSE |  |  | CT
| 319 | 2011-06-09 | G | 2009-12-14 | Power Station Increase | ST | NUC | 29 | 1253 | 1260 | New London | CT | 2011-11-30 | 2011-11-20 | 2011-06-09 | CL&P Millstone 345 kV substation | CNR | FALSE | FALSE |  | BL | CT
| 320 | 2011-11-01 | G | 2009-12-15 | Combined Cycle Repowering | CC | DFO NG | 0 | 0 | 0 | Fairfield | CT | 2014-06-01 | 2014-01-01 | 2011-10-31 | Norwalk Harbor 115 kV station | CNR | FALSE | FALSE |  | CD | NOR
| 321 | 2014-05-07 13:15 | G | 2009-12-24 | Rumford Falls Unit #3 increase | HD | WAT | 1.3 | 44.1 | 44.1 | Oxford | ME | 2010-06-01 | 2010-06-01 |  | CMP 115 kV Rumford Substation | CNR | FALSE | FALSE |  |  | ME
| 322 | 2011-06-29 | ETU | 2009-12-28 | 345 kV Tie Line | NA | N/A |  |  |  | N/A | ME | 2012-07-01 |  | 2011-06-29 | Houlton to MEPCO Line | N/A | FALSE | FALSE |  |  | BHE
| 323 | 2010-07-30 | G | 2010-01-21 | Wind Increase (see QP290) | WT | WND | 2 | 20 | 20 | Oxford | ME | 2010-12-30 | 2010-09-30 | 2010-07-29 | CMP Woodstock Substation | CNR | FALSE | FALSE |  |  | ME
| 323 | 2011-12-21 | G | 2010-01-21 | Spruce Mountain Wind Increase | WT | WND | 2 | 20 | 20 | Oxford | ME | 2011-12-21 | 2011-11-30 |  | CMP Woodstock substation | NA | FALSE | TRUE |  |  | ME
| 324 | 2015-02-17 08:18 | ETU | 2010-01-22 | 345kV Tie Line - Part 1 | NA | N/A |  |  |  | N/A | ME | 2016-12-01 | 2016-09-01 | 2015-02-16 | Houlton, ME to MEPCO Line | N/A | FALSE | FALSE |  |  | BHE
| 324 | 2015-02-17 08:19 | ETU | 2010-01-22 | 345 kV Tie Line - Part 2 | NA | N/A |  |  |  | N/A | ME | 2016-12-31 | 2016-09-01 | 2015-02-16 | MEPCO to Bridgewater, ME | N/A | FALSE | FALSE |  |  | BHE
| 325 | 2011-09-19 | G | 2010-02-10 | Wind | WT | WND | 535.5 | 535.5 | 535.5 | Washington | RI | 2015-12-31 | 2014-09-30 | 2011-09-19 | GRID Brayton Point 345 kV substation | NR | FALSE | FALSE |  | BL | RI
| 326 | 2010-07-19 | G | 2010-04-08 | Solar | PV | SUN | 19.92 | 19.92 | 19.92 | Hampden | MA | 2012-06-01 | 2012-04-01 | 2010-07-26 | GRID 69 kV N-14 Line | CNR | FALSE | FALSE |  |  | WMA
| 327 | 2014-08-26 11:52 | G | 2010-05-04 | Wind | WT | WND | 48 | 48 | 48 | Penobscot/Washington | ME | 2016-09-01 | 2016-06-01 | 2014-08-25 | BHE Keene Rd Substation | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | In Progress
| 328 | 2020-06-09 08:16 | G | 2010-05-06 | Douglas Woods Wind Units 1-11 | WT | WND | 27.5 | 27.5 | 27.5 | Worcester | MA | 2014-10-01 | 2014-08-01 | 2013-09-05 | GRID 69 kV S19 at E. Webster Substation | NR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted
| 328 | 2020-06-09 08:17 | G | 2010-05-06 | Douglas Woods Wind Unit 12 | WT | WND | 2.5 | 30 | 30 | Worcester | MA | 2014-10-01 | 2014-08-01 | 2013-09-05 | GRID 69 kV S19 at E. Webster Substation | NR | TRUE | TRUE | ISO-NE |  | WMA
| 329 | 2012-12-27 | G | 2010-05-07 | Georgia Mountain Community Wind | WT | WND | 10 | 10 | 10 | Chittenden | VT | 2012-12-31 | 2012-12-20 |  | CVPS 34.5 kV Fairfax - Milton Line | CNR | TRUE | TRUE | ISO-NE | BL | VT |  |  |  |  | Executed
| 330 | 2015-06-09 12:17 | G | 2010-05-10 | Fair Haven Biomass | ST | WDS | 33 | 33 | 33.3 | Rutland | VT | 2016-03-30 | 2016-01-29 | 2015-06-09 | CVPS 46 kV Castleton - Fair Haven | NR | TRUE | TRUE | ISO-NE | BL | VT |  | Document Posted |  |  | Executed
| 331 | 2011-01-10 | G | 2010-05-13 | Waterbury Generation Increase | GT | NG | 7.5 | 103.6 | 103 | New Haven | CT | 2010-10-12 | 2010-09-30 |  | CL&P Baldwin 115 kV substation | CNR | FALSE | TRUE |  |  | SWCT |  |  |  |  | Executed
| 331 | 2016-05-31 12:21 | G | 2010-05-13 | Kendall #3 Back Pressure Steam Turbine | ST | DFO NG | 7.5 | 28.5 | 28.4 | Middlesex | MA | 2016-05-31 | 2016-05-31 |  | 115 kV Line 875-539 to NSTAR 875 substation | CNR | FALSE | TRUE |  |  | BOST |  |  |  |  | Executed | In Service
| 332 | 2013-02-19 | G | 2010-05-13 | RISEP Increase | CC | NG | 66 | 613 | 625 | Providence | RI | 2012-11-12 | 2011-11-15 |  | 115 kV RISE substation | NR | TRUE | TRUE | ISO-NE | BL | RI |  | Document Posted |  |  | Executed | In Service
| 333 | 2016-12-13 14:28 | G | 2010-05-14 | Bingham Wind | WT | WND | 184.8 | 184.8 | 184.8 | Somerset | ME | 2016-12-13 | 2016-08-15 |  | CMP Guilford Substation | CNR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed | In Service
| 334 | 2011-03-21 | G | 2010-05-14 | Wind | WT | WND | 30 | 30 | 30 | Hampden | MA | 2012-12-31 | 2012-10-01 | 2011-03-17 | Section #175 115kV line from Palmer to Little Rest | CNR | FALSE | FALSE |  | BL | WMA
| 335 | 2011-06-30 | G | 2010-05-14 | Biomass | ST | WDS | 18.1 | 18.1 | 18.1 | Hancock | ME | 2012-03-01 | 2012-02-01 | 2011-06-30 | CMP 115 kV | CNR | TRUE | FALSE |  | CD | ME
| 336 | 2010-08-04 | G | 2010-05-14 | Manchester Street Station increase | CC | NG | 0 | 471 | 492 | Providence | RI | 2010-08-02 |  |  | GRID 115 kV Franklin substation | CNR | FALSE | FALSE |  |  | RI
| 337 | 2012-01-20 | G | 2010-05-14 | Verso Androscoggin Energy Cogen 1, 2, & 3 Increase | CC | KER NG | 26 | 147 | 180 | Franklin | ME | 2012-01-13 |  |  | CMP Section 227 | CNR | TRUE | TRUE | ISO-NE | BL | ME
| 338 | 2012-11-19 | G | 2010-05-14 | Wind | WT | WND | 0 | 18 | 18 | Hillsborough | NH | 2013-12-03 | 2013-11-02 | 2012-11-19 | PSNH 34.5 kV 3140 Circuit | NA | FALSE | FALSE |  |  | NH
| 339 | 2010-07-22 | G | 2010-06-09 | Exciter Upgrades | CC | NG | 0 | 441 | 492 | Providence | RI | 2011-03-07 | 2011-02-13 | 2010-07-21 | GRID 115 kV Franklin substation | NA | FALSE | FALSE |  |  | RI
| 340 | 2011-03-31 | G | 2010-06-24 | Biomass | ST | WDS | 33 | 33 | 33.3 | Bennington | VT | 2013-03-31 | 2012-12-31 | 2011-03-28 | CVPS East Pownal to Bennington 46 KV line | CNR | FALSE | FALSE |  | BL | VT
| 341 | 2013-11-15 11:53 | ETU | 2010-07-19 | HVDC Line | NA | N/A | 0 |  |  | N/A | MA | 2014-12-31 | 2014-12-31 | 2013-11-15 | MEPCO 345kV at Haynesville or MPC 345 kV/NSTAR 345 | N/A | FALSE | FALSE |  |  | BOST |  | Not Started
| 342 | 2011-06-09 | G | 2010-07-21 | Manchester Street Station Exciter Upgrades & incre | CC | NG | 12 | 483 | 510 | Providence | RI | 2011-06-14 | 2011-02-13 |  | GRID 115 kV Franklin substation | CNR | TRUE | TRUE | ISO-NE | CD | RI
| 343 | 2012-03-21 | G | 2010-08-10 | Operating change | ST | NUC | 0 | 0 | 0 | Plymouth | MA |  |  | 2012-03-21 | NSTAR 342 & 355 Line/345 switchyard | NA | FALSE | FALSE |  | BL | SEMA
| 344 | 2011-09-30 | G | 2010-09-07 | Mass Power Increase | CC | NG | 5 | 256.3 | 279.89 | Hampden | MA | 2011-09-30 | 2011-09-30 |  | NU 115 kV Shawanigan | CNR | FALSE | TRUE |  |  | WMA
| 345 | 2012-12-27 | G | 2010-09-08 | Groton Wind Farm | WT | WND | 48 | 48 | 48 | Grafton | NH | 2012-12-28 | 2012-10-31 |  | PSNH Beebe River 115 kV Substation | CNR | TRUE | TRUE | ISO-NE | PD | NH | Document Posted | Document Posted
| 346 | 2015-04-07 09:45 | G | 2010-10-01 | Burgess BioPower Increase | ST | WDS | 9 | 67.5 | 67.5 | Coos | NH | 2014-06-17 | 2013-10-25 |  | PSNH Eastside (Berlin) Substation | CNR | TRUE | TRUE | ISO-NE | PD | NH |  | Document Posted |  |  | Executed | In Service
| 347 | 2014-02-13 13:37 | G | 2010-10-07 | Bucksport G5 | ST | WDS | 25 | 25 | 25 | Hancock | ME | 2012-11-15 | 2012-10-25 |  | CMP 115 kV | NR | TRUE | TRUE | ISO-NE | BL | ME |  | Document Posted |  |  | Executed | In Service
| 348 | 2015-02-17 08:19 | ETU | 2010-10-13 | 1090 MW HVDC Tie - Import Only | NA | N/A |  |  |  | N/A | NH | 2018-06-01 | 2018-05-01 | 2015-02-16 | HQ Des Cantons substation to PSNH Deerfield substa | N/A | TRUE | TRUE | NU |  | NH |  | Document Posted
| 349 | 2016-12-16 13:14 | G | 2010-10-20 | Pisgah Mountain | WT | WND | 9 | 9 | 9 | Penobscot | ME | 2016-12-16 | 2016-11-01 |  | BHE Line 66 | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed | In Service
| 350 | 2015-10-01 10:54 | G | 2010-11-10 | Wind | WT | WND | 92.25 | 92.25 | 92.25 | Washington | ME | 2015-12-31 | 2015-10-01 | 2013-11-15 | BHE Washington County 115 kV substation | NR | FALSE | FALSE |  | PD | BHE | Document Posted | In Progress
| 350 | 2015-10-05 11:38 | G | 2010-11-10 | Wind | WT | WND | 96.9 | 96.9 | 96.9 | Somerset | ME | 2016-12-31 | 2016-10-01 | 2015-10-05 | CMP Wyman substation | NR | TRUE | FALSE | ISO-NE | PD | ME | Document Posted | In Progress |  |  |  | Under Study
| 351 | 2012-01-11 | G | 2010-12-03 | Gulf Island Unit 2 Increase | HW | WAT | 4.4 | 38.915 | 38.915 | Androscoggin | ME | 2011-04-26 | 2011-04-26 |  | CMP Gulf Island 115 kV | CNR | FALSE | TRUE |  |  | SME
| 352 | 2011-05-26 | G | 2010-12-14 | Salem Harbor Station Increase | ST | BIT RFO | 8 | 750.58 | 753.07 | Essex | MA |  |  |  | Salem Switchyard | CNR | FALSE | FALSE |  |  | BOST
| 353 | 2012-08-08 | G | 2010-12-21 | Wind | WT | WND | 9.9 | 9.9 | 9.9 | Plymouth | MA | 2013-12-31 | 2013-11-30 | 2012-08-08 | NSTAR 115 kV Valley substation | CNR | TRUE | FALSE | ISO-NE | BL | SEMA
| 353 | 2011-06-09 | G | 2010-12-21 | Wind | WT | WND | 14.9 | 14.9 | 14.9 | Barnstable | MA | 2012-11-30 | 2012-10-31 | 2011-06-07 | NSTAR 115 kV Valley substation | CNR | FALSE | FALSE |  |  | SEMA
| 354 | 2011-02-07 | G | 2011-01-12 | Combined Cycle Increase | CC | DFO NG | 20.2 | 157.3 | 185.2 | Berkshire | MA | 2011-04-01 |  | 2011-02-04 | WMECO Doreen 19A Substation | CNR | FALSE | FALSE |  |  | WMA
| 355 | 2012-12-04 | ETU | 2011-01-27 | HVDC Tie | NA | N/A |  |  |  | N/A |  | 2016-06-30 |  | 2012-12-04 | UI Singer 345 kV substation to LIPA Pt Jefferson 1 | N/A | FALSE | FALSE
| 356 | 2012-06-26 | G | 2011-02-04 | Altresco Increase (winter) | CC | DFO NG | 0 | 160 | 192.5 | Berkshire | MA | 2012-06-29 |  |  | WMECO Doreen 19A substation | CNR | TRUE | TRUE | ISO-NE | BL | WMA
| 357 | 2016-07-01 08:41 | G | 2011-02-24 | Passadumkeag Windpark | WT | WND | 39.975 | 39.975 | 39.975 | Penobscot | ME | 2016-05-23 | 2016-04-12 |  | BHE 115 kV between Enfield and James River Substat | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed | In Service
| 358 | 2011-11-17 | G | 2011-03-04 | Milford Hydro Expansion | HD | WAT | 2.5 | 8.9 | 8.9 | Penobscot | ME | 2011-11-04 | 2011-11-01 |  | BHE Milford Substation | CNR | TRUE | TRUE | BHE |  | BHE |  | Document Posted |  |  | Executed | In Service
| 358 | 2016-10-26 10:11 | G | 2011-03-04 | Medway Hydro Expansion | HD | WAT | 0.6 | 4.003 | 4.003 | Penobscot | ME | 2012-04-04 | 2012-04-04 |  | BHE Medway substation | CNR | TRUE | TRUE | BHE |  | BHE |  | Document Posted |  |  | Executed
| 358 | 2011-10-06 | G | 2011-03-04 | Hydro | HD | WAT | 2.274 | 2.274 | 2.274 | Penobscot | ME | 2012-08-15 | 2012-08-01 | 2011-10-05 | BHE Stillwater 12.5 kV substation | CNR | FALSE | FALSE |  |  | BHE |  | Document Posted
| 358 | 2011-04-12 | G | 2011-03-04 | Hydro | HD | WAT | 3.858 | 3.858 | 3.858 | Penobscot | ME | 2012-08-15 | 2012-08-01 | 2011-04-11 | BHE Orono 12.5 kV substation | CNR | FALSE | FALSE |  |  | BHE
| 359 | 2020-06-09 08:12 | G | 2011-03-07 | Bear Swamp AVR/PSS Unit 2 | PS | WAT | 0 | 0 | 0 | Franklin and Berkshire | MA | 2011-07-13 | 2011-06-30 |  | GRID Bear Swamp 230 kV substation | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted
| 359 | 2012-03-09 | G | 2011-03-07 | Bear Swamp AVR/PSS Unit 1 | PS | WAT | 0 | 0 | 0 | Franklin and Bershire | MA | 2012-03-08 | 2012-03-06 |  | Bear Swamp 230 kV substation | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted
| 360 | 2011-08-03 | G | 2011-03-14 | Indian River Power Supply CNR | HD | WAT | 0 | 1.3 | 1.3 | Hampden | MA | 2011-08-02 |  |  | WMECO 23 kV circuit | CNR | FALSE | FALSE |  |  | WMA
| 360 | 2015-01-13 12:47 | G | 2011-03-14 | Turners Falls Hydro CNR | HD | WAT | 0 | 0.95 | 0.95 | Franklin | MA | 2012-05-29 | 2012-05-29 |  | WMECO 13.8 kV | NR | FALSE | FALSE |  | BL | WMA
| 360 | 2012-01-11 | G | 2011-03-14 | Woronoco Hydro CNR | HD | WAT | 0 | 2.7 | 2.7 | Hampden | MA | 2012-01-06 |  |  | WMECO 23 kV | CNR | FALSE | FALSE |  |  | WMA
| 361 | 2014-05-19 15:34 | G | 2011-03-14 | Grandpas Knob Wind | WT | WND | 20 | 20 | 20 | West Rutland | VT | 2016-12-31 | 2016-09-30 | 2014-05-19 | VELCO W Rutland 115 kV Substation | NR | TRUE | TRUE | ISO-NE | BL | VT |  | Document Posted |  |  | Executed
| 362 | 2011-11-17 | G | 2011-03-22 | Milford Hydro Expansion Increase (Q358) | HD | WAT | 0.183 | 9.083 | 9.083 | Penobscot | ME | 2011-11-04 | 2011-11-01 |  | BHE Milford substation | CNR | TRUE | TRUE | BHE |  | BHE |  | Document Posted
| 363 | 2011-07-29 | G | 2011-03-31 | Solar | PV | SUN | 6 | 6 | 6 | Bristol | MA | 2012-12-31 | 2012-09-30 | 2011-07-29 | NSTAR 115 kV or 13.2 kV | CNR | FALSE | FALSE |  |  | SEMA
| 364 | 2011-05-26 | G | 2011-04-07 | Solar | PV | SUN | 4.92 | 4.92 | 4.92 | Hampden | MA | 2012-03-31 | 2012-03-01 | 2011-05-18 | GRID 69kV N-14 Line | CNR | FALSE | FALSE |  |  | WMA
| 365 | 2011-11-14 | G | 2011-04-27 | Bridgeport Harbor #3 CNR Increase | ST | DFO SUB | 5 | 385 | 385 | Fairfield | CT | 2011-10-31 |  |  | UI Pequonnock 115 kV substation | CNR | FALSE | TRUE |  |  | SWCT
| 366 | 2016-03-30 07:54 | G | 2011-05-23 | Wyman Hydro Uprate U1 | HW | WAT | 2.5 | 30 | 30 | Somerset | ME | 2016-03-30 | 2016-03-24 |  | CMP 115 kv Wyman | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed | In Service
| 366 | 2015-03-25 15:11 | G | 2011-05-23 | Wyman Hydro Uprate U2 | HW | WAT | 0 | 29.9 | 29.9 | Somerset | ME | 2015-03-23 | 2015-03-23 |  | CMP 115 kV Wyman | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 366 | 2016-03-30 07:55 | G | 2011-05-23 | Wyman Hydro Uprate U3 | HW | WAT | 4.3 | 30 | 30 | Somerset | ME | 2016-03-30 | 2016-03-24 |  | CMP 115 kV Wyman | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed | In Service
| 367 | 2012-11-19 | G | 2011-05-26 | Kingdom Community Wind Increase (see Q311) | WT | WND | 3.075 | 64.575 | 64.575 | Orleans | VT | 2012-12-16 | 2012-08-29 |  | VEC Lowell 46 kV station | CNR | TRUE | TRUE | ISO-NE |  | VT |  | Document Posted |  |  | Executed
| 368 | 2014-06-10 14:22 | G | 2011-05-27 | Wind | WT | WND | 10 | 10 | 10 | Hillsborough | NH | 2012-09-30 | 2012-09-01 | 2011-08-23 | PSNH 7.2 kV to Milford Substation | CNR | FALSE | FALSE |  |  | NH |  | Document Posted |  |  |  | Under Study
| 368 | 2013-07-25 16:24 | G | 2011-05-27 | Wind | WT | WND | 16.1 | 16.1 | 16.1 | Hillsborough | NH | 2014-10-31 | 2014-10-01 | 2013-07-25 | PSNH 34.5 kV to Monadnock substation | CNR | TRUE | TRUE | ISO-NE | CD | NH |  | Document Posted
| 369 | 2011-11-29 | G | 2011-06-08 | Combined Cycle | CC | NG | 745 | 745 | 775 | Fairfield | CT | 2016-06-01 | 2016-01-01 | 2011-11-28 | NU 345 kV Line | CNR | FALSE | FALSE |  |  | NOR
| 370 | 2012-10-15 | G | 2011-07-01 | Shepaug AVR Upgrade | HW | WAT | 0 | 0 | 0 | New Haven | CT | 2012-10-16 | 2012-09-23 |  | CL&P 69 kV bus at Shepaug | CNR | TRUE | TRUE | ISO-NE |  | SWCT
| 371 | 2013-08-06 10:24 | G | 2011-08-01 | Wind | WT | WND | 33 | 33 | 33 | Hillsborough | NH | 2015-07-31 | 2015-06-30 | 2013-08-06 | PSNH L163 115 kV | CNR | TRUE | TRUE | ISO-NE | PD | NH |  | Document Posted
| 372 | 2014-01-07 15:52 | G | 2011-08-03 | Skelton Station Modernization Phase 1 | HD | WAT | 1.083 | 21.083 | 21.083 | York | ME | 2013-12-28 | 2013-12-19 |  | CMP 34.5 kV Louden substation | CNR | TRUE | TRUE | ISO-NE |  | ME |  | Document Posted |  |  | Executed | In Service
| 372 | 2014-01-07 15:52 | G | 2011-08-03 | Skelton Station Modernization Phase 2 | HD | WAT | 1.083 | 22.2 | 22.2 | York | ME | 2013-12-28 | 2013-12-14 |  | CMP 34.5 kV Louden substation | CNR | TRUE | TRUE | ISO-NE | BL | ME |  | Document Posted |  |  | Executed | In Service
| 373 | 2012-09-21 | G | 2011-08-12 | CC Administrative Increase | CC | DFO NG | 0 | 478 | 550 | Hampden | MA |  |  | 2012-09-21 | WMECO Ludlow 19S substation | CNR | FALSE | FALSE |  |  | WMA
| 374 | 2012-06-07 | G | 2011-08-24 | Brayton Pt. 1 Exciter Replacement | ST | BIT | 0 | 0 | 0 | Bristol | MA | 2012-05-20 | 2012-05-12 |  | GRID 345 kV Brayton Pt Switchyard | CNR | TRUE | TRUE | ISO-NE |  | RI |  | Document Posted |  |  | Executed | In Service
| 374 | 2014-01-28 08:10 | G | 2011-08-24 | Brayton Pt. 2 Exciter Replacement | ST | BIT | 0 | 0 | 0 | Bristol | MA | 2014-05-30 | 2014-05-22 | 2013-12-04 | GRID 345 kV Brayton Pt Switchyard | CNR | TRUE | TRUE | ISO-NE | BL | RI |  | Document Posted |  |  | Executed
| 375 | 2013-09-27 15:59 | G | 2011-09-07 | Wind | WT | WND | 80 | 80 | 80 | Merrimack/Grafton | NH | 2014-12-31 | 2014-09-30 | 2013-09-27 | GRID Comerford/Merrimack 230 kV Line | CNR | FALSE | FALSE |  | BL | NH
| 376 | 2012-07-30 | G | 2011-09-08 | Algonquin Power Windsor Locks CNR Increase | IC | NG | 0 | 0 | 0 | Hartford | CT | 2012-07-20 | 2012-06-28 |  | CL&P Windsor Locks 23 kV Substation | CNR | TRUE | TRUE | ISO-NE | BL | CT
| 377 | 2016-12-23 09:03 | G | 2011-09-14 | Harrington Street PV Project (QF) | PV | SUN | 9.75 | 9.75 | 9.75 | Worcester | MA | 2016-12-23 | 2016-02-08 |  | GRID 69 kV | NA | TRUE | TRUE | NGRID |  | WMA | [5 empty] | In Service
| 378 | 2013-11-15 11:53 | ETU | 2011-10-18 | HVDC Line | NA | N/A | 0 |  |  | N/A | MA | 2015-12-31 | 2015-12-31 | 2013-11-15 | MEPCO 345 kV at Haynesville or MPC 345 KV/GRID 115 | N/A | FALSE | FALSE |  |  | BOST |  | Not Started
| 379 | 2014-09-02 10:58 | G | 2011-10-19 | CornerStone Power Monson 2 | PV | SUN | 4.92 | 4.92 | 4.92 | Hampden | MA | 2014-11-01 | 2014-10-15 | 2014-08-12 | GRID 69 kV N14 Line | NR | TRUE | TRUE | ISO-NE | BL | WMA |  | Document Posted |  |  | Executed | Under Construction
| 379 | 2014-09-02 10:58 | G | 2011-10-19 | CornerStone Power Monson 3 | PV | SUN | 4.92 | 4.92 | 4.92 | Hampden | MA | 2014-11-01 | 2014-10-15 | 2014-08-12 | GRID 69 kV N14 Line | NR | TRUE | TRUE | ISO-NE | BL | WMA |  | Document Posted |  |  | Executed | Under Construction
| 380 | 2015-02-17 08:20 | ETU | 2011-11-10 | 1000 MW HVDC Line | NA | N/A |  |  |  | N/A | MA | 2020-06-01 | 2020-01-01 | 2015-02-16 | NSTAR Carver 345 kV | N/A | FALSE | FALSE |  |  | SEMA |  | Not Started
| 380 | 2015-02-17 08:21 | ETU | 2011-11-10 | 1000 MW HVDC Line | NA | N/A |  |  |  | N/A | MA | 2020-06-01 | 2020-01-01 | 2015-02-16 | NSTAR Barnstable 345 kV | N/A | FALSE | FALSE |  |  | SEMA |  | Not Started
| 381 | 2013-10-21 13:53 | G | 2011-11-14 | Wind | WT | WND | 11.9 | 11.9 | 11.9 | Lincoln | ME | 2017-09-15 | 2017-09-01 | 2013-10-21 | CMP 34.5 kV Boothbay Substation | CNR | TRUE | FALSE | CMP | BL | ME |  | Document Posted
| 382 | 2012-11-20 | G | 2011-12-05 | Wind | WT | WND | 79.86 | 79.86 | 79.86 | Oxford | ME | 2014-10-31 | 2014-07-31 | 2012-11-20 | CMP 115 kV Rumford to Livermore Line | CNR | FALSE | FALSE |  | PD | ME
| 383 | 2013-07-26 09:50 | G | 2011-12-22 | Wind | WT | WND | 198 | 198 | 198 | Franklin | ME | 2016-10-31 | 2015-10-31 | 2013-07-26 | CMP Roxbury substation | CNR | FALSE | FALSE |  | PD | ME | Document Posted
| 384 | 2018-05-21 09:52 | G | 2011-12-29 | CPV Towantic Energy Center | CC | DFO NG | 745 | 745 | 775 | New Haven | CT | 2018-05-21 | 2018-01-24 |  | CL&amp;P 115 kV | CNR | TRUE | TRUE | ISO-NE | PD | SWCT |  | Document Posted |  |  | Executed | In Service
| 385 | 2014-05-21 10:15 | G | 2012-01-06 | Wind | WT | WND | 60 | 60 | 60 | Calendonia and Essex | VT | 2015-12-01 | 2015-09-01 | 2014-05-21 | VELCO 115 kV Lyndonville substation | CNR | FALSE | FALSE |  | PD | VT | Document Posted | In Progress
| 386 | 2013-02-05 | G | 2012-01-12 | Westbrook Energy Center Expansion | CC | NG | 9.5 | 538 | 597 | York | ME | 2013-01-31 | 2013-01-31 |  | CMP 115 kV Westbrook Substation | CNR | TRUE | TRUE | ISO-NE | CD | SME |  |  |  |  | Executed
| 387 | 2013-03-26 12:27 | G | 2012-01-13 | Gas Turbine Increase | GT | NG | 13.5 | 250 | 250 | New Haven | CT | 2013-02-28 | 2013-02-28 | 2013-03-22 | CMEEC 115kV Wallingford Substation |  | FALSE | TRUE |  |  | SWCT |  | Document Posted |  |  | Executed | Under Construction
| 387 | 2018-05-31 09:57 | G | 2012-01-13 | Footprint Combined Cycle Unit | CC | NG | 715.6 | 715.6 | 715.6 | Essex | MA | 2018-05-31 | 2017-12-22 |  | NGRID 115 kV Salem Harbor Substation | CNR | TRUE | TRUE | NGRID | BL | BOST |  | Document Posted |  |  | Executed | In Service
| 388 | 2013-03-26 12:28 | G | 2012-01-13 | Combined Cycle | CC | NG | 680 | 680 | 700 | Fairfield | CT | 2016-05-31 | 2016-03-01 | 2013-03-19 | UI 115 kV or 345 kV |  | FALSE | FALSE |  | PD | SWCT
| 389 | 2012-03-23 | G | 2012-01-17 | Solar | PV | SUN | 5.04 | 5.04 | 5.04 | Fairfield | CT | 2013-05-31 | 2013-03-31 | 2012-03-23 | CL&P 115 kV Norwalk Harbor Substation | CNR | FALSE | FALSE |  |  | NOR
| 390 | 2017-04-11 10:11 | G | 2012-01-30 | Spruce Ridge Wind Farm | WT | WND | 50.82 | 50.82 | 50.82 | Grafton | NH | 2017-10-31 | 2017-09-18 | 2017-04-10 | NGRID 230 kV Comerford/Dunbarton Line | NR | TRUE | TRUE | ISO-NE | PD | NH |  | Document Posted |  |  | Executed
| 391 | 2015-10-09 14:25 | G | 2012-02-02 | Weston Station Uprate U4 | HD | WAT | 1.6 | 14.806 | 14.806 | Somerset | ME | 2015-07-31 | 2015-07-30 |  | CMP 34.5 kV Weston Substation | CNR | TRUE | TRUE | ISO-NE | BL | ME |  |  |  |  | Executed | In Service
| 391 | 2013-12-17 12:33 | G | 2012-02-02 | Weston Station GSU/AVR Replacement U1 | HD | WAT | 0 | 14.806 | 14.806 | Somerset | ME | 2013-12-14 | 2013-12-14 |  | CMP 34.5 kV Weston Substation | CNR | TRUE | TRUE | ISO-NE | BL | ME |  | Document Posted |  |  | Executed | In Service
| 391 | 2015-10-09 14:26 | G | 2012-02-02 | Weston Station AVR Replacement U2-4 | HD | WAT | 0 | 14.806 | 14.806 | Somerset | ME | 2015-07-31 | 2015-07-30 |  | CMP 34.5 kV Weston Substation | CNR | TRUE | TRUE | ISO-NE | BL | ME |  |  |  |  | Executed | In Service
| 392 | 2012-07-23 | G | 2012-03-28 | Wind | WT | WND | 2.7 | 2.7 | 2.7 | Coos | NH | 2012-10-29 | 2012-10-15 | 2012-07-11 | PSNH 12.47 kV | CNR | FALSE | FALSE |  |  | NH
| 393 | 2015-10-28 13:52 | G | 2012-05-07 | Wind | WT | WND | 84 | 84 | 84 | Somerset | ME | 2016-11-01 | 2016-10-01 | 2015-10-28 | CMP 115 kV W. S. Wyman Hydro Substation | NR | FALSE | FALSE |  | PD | ME | Document Posted
| 394 | 2013-12-23 10:12 | G | 2012-07-25 | Bridgeport Fuel Cell I | FC | NG | 5.6 | 5.6 | 5.6 | Fairfield | CT | 2013-12-22 | 2013-11-24 |  | UI 13.8 kV Ash Creek substation | NA | TRUE | TRUE | UI |  | SWCT |  | Document Posted |  |  | Executed | In Service
| 394 | 2013-12-23 10:12 | G | 2012-07-25 | Bridgeport Fuel Cell 2 | FC | NG | 5.6 | 5.6 | 5.6 | Fairfield | CT | 2013-12-22 | 2013-11-24 |  | UI 13.8 kV New Congress I substation | NA | TRUE | TRUE | UI |  | SWCT |  |  |  |  | Executed | In Service
| 394 | 2013-12-23 10:13 | G | 2012-07-25 | Bridgeport Fuel Cell 3 | FC | NG | 4.15 | 4.15 | 4.15 | Fairfield | CT | 2013-12-22 | 2013-11-24 |  | UI 13.8 kV New Congress II Substation | NA | TRUE | TRUE | UI |  | SWCT |  |  |  |  | Executed | In Service
| 395 | 2012-10-24 | G | 2012-07-30 | Solar | PV | SUN | 2.18 | 2.18 | 2.18 | Windham | VT | 2013-06-01 | 2013-05-15 | 2012-10-24 | CVPS 46 kV | CNR | FALSE | FALSE |  |  | VT
| 396 | 2020-01-07 13:43 | G | 2012-08-28 | Berkshire Wind Increase | WT | WND | 4.6 | 19.6 | 19.6 | Berkshire | MA | 2019-11-19 | 2019-09-25 |  | WMECO 23 kV from Partridge substation | NR | TRUE | FALSE | NU | BL | WMA |  | Document Posted |  |  | Executed | Under Construction
| 397 | 2016-12-14 15:47 | G | 2012-08-30 | Hancock Wind Project | WT | WND | 51 | 51 | 51 | Hancock | ME | 2016-12-14 | 2016-10-01 |  | BHE Line 66 - Bull Hill substation | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed | In Service
| 398 | 2013-11-15 16:35 | G | 2012-09-04 | Dighton Power Uprate | CC | NG | 5 | 180 | 197 | Bristol | MA | 2013-12-05 | 2013-12-05 |  | GRID 115 kV U6 Line | CNR | TRUE | TRUE | ISO-NE | CD | SEMA |  | Document Posted |  |  | Executed | In Service
| 399 | 2013-02-27 | G | 2012-10-01 | Wind Increase | WT | WND | 1.2 | 34.2 | 34.2 | Franklin | ME | 2014-08-15 | 2014-06-02 | 2013-02-27 | CMP Ludden Lane Substation | CNR | FALSE | FALSE |  |  | ME
| 400 | 2018-04-19 13:22 | G | 2012-10-03 | Downeast Wind | WT | WND | 90 | 90 | 90 | Washington | ME | 2019-10-03 | 2019-07-18 | 2018-04-19 | BHE Epping Substation | NR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  |  | Executed
| 401 | 2014-12-11 13:50 | G | 2012-10-05 | Wind | WT | WND | 19.8 | 19.8 | 19.8 | Washington | ME | 2014-12-31 | 2014-11-30 | 2014-08-14 | BHE Epping 115 kV substation or BHE 34.5 kV | CNR | FALSE | FALSE |  | PD | BHE | In Progress |  |  |  |  | Under Study
| 402 | 2014-01-17 14:03 | G | 2012-10-16 | Mechanicsville Hydro Increase | HD | WAT | 0.31 | 0.31 | 0.31 | Windham | CT | 2013-03-01 | 2013-03-01 |  | CL&amp;P 23 kV at Mechanicsville | CNR | FALSE | FALSE |  |  | CT |  |  |  |  | Executed
| 403 | 2016-12-16 13:15 | G | 2012-12-06 | Pisgah Mountain Increase (see Q349) | WT | WND | 0.075 | 9.075 | 9.075 | Penobscot | ME | 2016-12-16 | 2016-11-01 |  | BHE Line 66 | NR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed | In Service
| 404 | 2017-06-30 10:37 | G | 2013-01-08 | MATEP -3rd CTG | GT | DFO NG | 14.15 | 100 | 105.6 | Suffolk | MA | 2017-06-28 | 2016-12-01 |  | NSTAR Brighton substation | CNR | TRUE | TRUE | ISO-NE | BL | BOST |  | Document Posted |  |  | Executed | In Service
| 405 | 2016-12-09 11:05 | G | 2013-01-18 | Block Island Wind Farm | WT | WND | 29 | 29 | 29 | Washington | RI | 2016-12-09 | 2016-11-04 |  | Grid 34.5 kV | NA | TRUE | TRUE | NGRID |  | RI | [5 empty] | In Service
| 406 | 2017-11-29 08:43 | G | 2013-02-22 | Canton Increase and CNR (see Q300) | WT | WND | 3.55 | 22.8 | 22.8 | Oxford | ME | 2017-11-29 | 2017-10-18 |  | CMP Ludden Lane Substation | NR | FALSE | FALSE |  |  | ME |  |  |  |  | Executed | In Service
| 407 | 2015-09-16 16:50 | G | 2013-02-27 | Saddleback Increase and CNR (see Q287) | WT | WND | 1.2 | 34.2 | 34.2 | Franklin | ME | 2015-09-15 | 2015-08-15 |  | CMP Ludden Lane Substation | CNR | FALSE | FALSE |  |  | ME |  |  |  |  | Executed | In Service
| 408 | 2016-03-23 15:12 | G | 2013-02-28 | Gas Turbine | GT | DFO NG | 207.7 | 207.7 | 204.4 | Middlesex | MA | 2018-05-31 | 2018-02-01 | 2016-03-17 | NSTAR 345 kV Mystic Station | NR | TRUE | FALSE |  | PD | BOST |  | Document Posted
| 409 | 2015-03-02 11:49 | G | 2013-02-28 | Gas Turbine | GT | DFO NG | 207.7 | 207.7 | 204.4 | Norfolk | MA | 2018-05-31 | 2018-02-01 | 2015-03-02 | NSTAR 230 kV W. Medway Station | CNR | FALSE | FALSE |  | BL | BOST |  | In Progress |  |  |  | Under Study
| 410 | 2014-09-02 10:55 | G | 2013-02-28 | Wind CNR | WT | WND | 0 | 48 | 48 | Peneobscot/Washington | ME | 2016-08-01 | 2016-06-01 | 2014-08-25 | BHE Keene Rd | CNR | FALSE | FALSE |  |  | BHE |  |  |  |  | In Progress
| 411 | 2014-07-16 16:12 | G | 2013-02-28 | Gas Turbine Increase | GT | DFO NG | 10.9 | 39.4 | 45.8 | Essex | MA | 2013-12-31 | 2013-12-31 |  | Peabody B-154S line | NA | FALSE | TRUE |  |  | BOST | [5 empty] | In Service
| 412 | 2019-06-10 07:58 | G | 2013-02-28 | PSEG Bridgeport Harbor CCGT Expansion | CC | DFO NG | 509.6 | 509.6 | 532.6 | Fairfield | CT | 2019-06-10 | 2019-05-11 |  | UI 345 kV Singer | CNR | TRUE | TRUE | ISO-NE | BL | SWCT | Document Posted | Document Posted |  |  | Executed | In Service
| 413 | 2015-02-17 08:21 | ETU | 2013-03-04 | Keene Rd ETU | NA | N/A |  | 0 | 0 | Penobscot | ME | 2016-03-01 | 2015-11-01 | 2015-02-16 | BHE Keene Road Substation | N/A | FALSE | FALSE |  |  | BHE |  | In Progress |  |  |  | Under Study
| 414 | 2014-06-24 08:27 | G | 2013-03-26 | EP Newington Energy Capacity Increase | CC | NG | 21.2 | 568.2 | 594.8 | Rockingham | NH | 2014-06-17 | 2014-05-31 |  | PSNH Newington 345 kV substation | CNR | TRUE | TRUE | ISO-NE | BL | NH |  | Document Posted |  |  | Executed | In Service
| 415 | 2016-01-25 11:19 | G | 2013-04-12 | Jericho Wind | WT | WND | 8.55 | 8.55 | 8.55 | Coos | NH | 2016-01-23 | 2015-10-16 |  | PSNH Berlin Substation | CNR | TRUE | TRUE | ISO-NE | BL | NH |  | Document Posted |  |  | Executed | In Service
| 416 | 2013-11-12 13:49 | G | 2013-04-23 | Wind | WT | WND | 18 | 18 | 18 | Coos | NH | 2017-04-30 | 2017-04-12 | 2013-07-17 | Pontook Hydro | CNR | FALSE | FALSE |  |  | NH
| 417 | 2019-05-14 10:57 | G | 2013-04-25 | Number Nine Wind Farm | WT | WND | 250 | 250 | 250 | Aroostook | ME | 2021-10-31 | 2021-04-05 | 2019-05-13 | Pittsfield 345KV | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed
| 418 | 2014-02-14 16:36 | G | 2013-05-01 | Biomass | ST | DFO WDS | 37 | 37 | 37 | Windsor | VT | 2015-08-30 | 2015-06-30 | 2014-02-14 | GMP L97 Line | CNR | FALSE | FALSE |  | BL | VT |  | In Progress |  |  |  | Under Study
| 419 | 2014-07-03 10:45 | G | 2013-05-02 | Wind | WT | WND | 33 | 33 | 33 | Franklin | ME | 2016-11-01 | 2016-10-01 | 2014-07-02 | CMP 115 kV Bigalow Substation | NR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 420 | 2020-12-14 08:27 | G | 2013-07-15 | Weaver Wind | WT | WND | 72.6 | 72.6 | 72.6 | Hancock | ME | 2020-12-12 | 2020-10-13 |  | Bull Hill Switching Station | NR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  | Document Posted | Executed | In Service
| 421 | 2017-04-11 10:12 | G | 2013-07-18 | Spruce Ridge Wind CNR (see Q390) | WT | WND | 0 | 50.82 | 50.82 | Grafton | NH | 2017-10-31 | 2017-08-18 | 2017-04-10 | NGRID 230 kV Comerford/Dunbarton Line | NR | FALSE | FALSE |  |  | NH |  |  |  |  | Executed
| 422 | 2019-05-14 10:56 | G | 2013-07-26 | Number Nine Wind Farm CNR | WT | WND | 0 | 250 | 250 | Aroostook | ME | 2021-10-31 | 2021-04-05 | 2019-05-13 | MEPCO line in Haynesville, ME | NR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed
| 423 | 2014-03-12 12:26 | G | 2013-09-10 | Wind | WT | WND | 74.29 | 74.29 | 74.29 | Merrimack/Grafton | NH | 2016-12-31 | 2016-10-01 | 2014-03-12 | A201 Comerford - North Litchfield 230 kV line | CNR | FALSE | FALSE |  |  | NH |  | In Progress |  |  |  | Under Study
| 424 | 2013-11-06 08:12 | G | 2013-09-11 | Hydro Increase | HW | WAT | 0.1 | 0.65 | 0.65 | Hampden | MA | 2014-01-01 | 2014-01-01 | 2013-11-05 | HGE 115 kV North Canal substation | CNR | FALSE | FALSE |  |  | WMA
| 425 | 2015-02-17 08:22 | ETU | 2013-09-23 | 1000 MW HVDC Tie V1 | NA | N/A |  |  |  | Windsor | VT | 2018-12-31 | 2018-10-31 | 2015-02-16 | HQ 735 kV substation to Velco 345 kV Coolidge substation | N/A | FALSE | FALSE |  |  | VT |  | In Progress |  |  |  | Under Study
| 426 | 2015-02-17 08:23 | ETU | 2013-10-15 | 1000 MW HVDC Tie V2 (See Q425) | NA | N/A |  |  |  | Rutland | VT | 2018-12-31 | 2018-10-31 | 2015-02-16 | HQ 735 kV substation to Velco 345 kV W. Rutland Substation | N/A | FALSE | FALSE |  |  | VT
| 427 | 2015-02-17 08:23 | ETU | 2013-10-15 | 1000 MW HVDC Tie V3 (See Q425) | NA | N/A |  |  |  | Addison | VT | 2018-12-31 | 2018-10-31 | 2015-02-16 | HQ 735 kV substation to Velco 345 kV New Haven substation | N/A | FALSE | FALSE |  |  | VT
| 428 | 2015-02-17 08:24 | ETU | 2013-11-15 | 1200 MW AC to HVDC Tie | NA | N/A |  |  |  | Middlesex | MA | 2019-03-31 | 2019-01-01 | 2015-02-16 | NB 345 Keswick or St. Andre substation to GRID 345 kV Wakefield substation | N/A | FALSE | FALSE |  |  | BOST
| 429 | 2014-01-10 13:54 | G | 2013-12-02 | Offshore Wind | WT | WND | 12 | 12 | 12 | Lincoln | ME | 2017-11-06 | 2017-10-02 | 2014-01-10 | Central Maine Power, Bristol Substation, Bristol Maine | NR | FALSE | FALSE |  |  | ME
| 430 | 2015-02-17 08:25 | ETU | 2014-01-13 | Coos ETU | NA | N/A |  |  |  | Coos | NH | 2016-07-01 | 2016-07-01 | 2015-02-16 | TBD | N/A | FALSE | FALSE |  |  | NH
| 431 | 2014-01-29 08:07 | TS | 2014-01-14 | Local Transmission Service - 99 MW | NA | N/A | 0 | 0 | 0 | Coos | NH | 2015-01-01 | 2015-01-01 | 2014-01-28 | NA | N/A | FALSE | FALSE |  |  | NH
| 432 | 2017-03-28 15:56 | ETU | 2014-01-21 | 115 KV ETU | NA | N/A |  |  |  | Aroostook | ME | 2017-07-31 | 2017-07-31 | 2014-05-14 | MPS 69 kV Mullen substation to ME Gen Lead 115 kV line | N/A | FALSE | FALSE |  |  | BHE
| 433 | 2014-04-30 14:17 | G | 2014-01-24 | MATEP (Combined Cycle) Increase | CC | DFO NG | 1.7 | 62.083 | 66 | Suffolk | MA | 2014-04-21 | 2014-03-21 |  | At existing point of interconnection for MATEP (Combined Cycle) | CNR | FALSE | FALSE |  |  | BOST |  |  |  |  | Executed | In Service
| 434 | 2015-02-17 08:26 | ETU | 2014-01-29 | Expand Interface | NA | N/A |  |  |  | Aroostook | ME | 2017-11-01 | 2017-09-01 | 2015-02-16 | TBD | N/A | FALSE | FALSE |  |  | BHE
| 435 | 2018-01-19 16:33 | G | 2014-01-31 | Wind | WT | WND | 103.5 | 103.5 | 103.5 | Washington | ME | 2018-12-31 | 2018-09-30 | 2018-01-19 | Bangor Hydro Epping Substation, Columbia, Washington County, ME | NR | FALSE | FALSE |  | PD | BHE | Document Posted | In Progress |  |  |  | Under Study
| 436 | 2014-11-07 08:52 | G | 2014-02-05 | Gas Turbine (alt. to QP412) | GT | DFO NG | 0 | 335 | 335 | Fairfield | CT | 2018-05-31 | 2018-02-01 | 2014-11-07 | 345 kV generator side connection to the transmission grid. | CNR | TRUE | FALSE | ISO-NE | PD | SWCT |  | Document Posted
| 437 | 2022-06-15 12:48 | G | 2014-02-10 | Jericho Wind expansion | WT | WND | 3.5 |  |  | Coos | NH | 2016-01-23 | 2015-10-16 |  | PSNH Berlin Substation Bus 1 Breaker 3521. | CNR | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | Executed | In Service
| 438 | 2017-05-31 14:58 | G | 2014-02-24 | Potter Repowering | GT | NG | -21.2 | 63.27 | 65.25 | Norfolk | MA | 2019-05-22 | 2019-02-22 | 2017-05-31 | BELD Station 16 Switchyard | NR | TRUE | TRUE | ISO-NE |  | SEMA |  | Document Posted |  |  | Executed
| 439 | 2015-02-12 16:41 | G | 2014-02-24 | Simple Cycle | GT | NG | 478 | 478 | 483 | Essex | MA | 2018-05-01 | 2018-01-01 | 2015-02-12 | GRID Ward Hill – Tewksbury 345 kV line, approximately 1.8 miles from the Ward Hill | CNR | FALSE | FALSE |  |  | CMA | Document Posted | In Progress
| 440 | 2018-05-08 08:05 | G | 2014-02-24 | Wallingford Energy Center | GT | NG | 100 | 350 | 350 | New Haven | CT | 2018-05-09 | 2017-12-07 |  | CMEEC 115 kV Wallingford Substation Generating facility. | CNR | TRUE | TRUE | ISO-NE |  | SWCT | Document Posted | Document Posted |  |  | Executed | In Service
| 441 | 2018-11-26 08:21 | G | 2014-02-25 | Glendale Hydroelectric Expansion Project | HD | WAT | 0.2 | 0.1856 | 0.1856 | Berkshire | MA | 2018-11-13 | 2018-11-07 |  | GRID 13.8 kV | CNR | TRUE | FALSE | NGRID |  | WMA |  | Document Posted |  |  | Executed | In Service
| 442 | 2015-12-29 11:20 | G | 2014-02-26 | Combined Cycle | CC | DFO NG | 387.9 | 387.9 | 422.1 | Hampden | MA | 2019-03-01 | 2018-06-01 | 2015-12-28 | 115kV Line 1302 between Buck Pond and Pochassic substations, approximately 1 mile south of Buck Pond. | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | In Progress
| 443 | 2017-05-25 09:43 | G | 2014-03-03 | Brockton Combined Cycle CNR Increase | CC | NG | 0 | 354.9 | 383.9 | Plymouth | MA | 2019-05-31 | 2019-01-25 | 2017-05-25 | Grid 115 kV E20 and F19 Lines | NR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed
| 444 | 2019-05-02 14:12 | G | 2014-05-02 | Medway Peaker - SEMARI | GT | DFO NG | 207.7 | 207.7 | 207.7 | Norfolk | MA | 2019-03-14 | 2019-02-08 |  | Medway 115 kV station | CNR | TRUE | TRUE | ISO-NE | PD | SEMA |  | Document Posted |  |  | Executed | In Service
| 445 | 2015-03-02 11:50 | G | 2014-03-04 | Gas Turbine | GT | DFO NG | 103.5 | 103.5 | 103.5 | Norfolk | MA | 2018-05-31 | 2018-02-01 | 2015-03-02 | Edgar 115 kV Station | CNR | FALSE | FALSE |  | PD | SEMA |  | In Progress |  |  |  | Under Study
| 446 | 2014-04-01 09:59 | G | 2014-03-04 | Gas Turbine | GT | DFO NG | 47.5 | 59.5 | 59.5 | Chittenden | VT | 2018-05-31 | 2018-03-31 | 2014-03-31 | Gorge substation, No. 16, Breaker 3320. | CNR | FALSE | FALSE |  |  | VT
| 447 | 2024-08-29 14:17 | G | 2014-03-04 | Passadumkeag Windpark CNR Only | WT | WND | 0 | 39.975 | 39.975 | Penobscot | ME | 2016-07-01 | 2016-04-12 |  | 115kV line between James River and Enfield substations on Line 64 | NR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed | In Service
| 448 | 2014-06-11 16:03 | G | 2014-03-04 | Fuel Cell | FC | NG | 5.6 | 5.6 | 5.6 | New London | CT | 2018-05-31 | 2018-05-01 | 2014-06-11 | NU/CL&amp;P Montville substation, 4160V station service bus | CNR | FALSE | FALSE |  |  | CT
| 449 | 2019-06-17 08:00 | G | 2014-03-04 | Canal 3 | GT | DFO NG | 333 | 333 | 336.2 | Barnstable | MA | 2019-06-15 | 2019-04-01 |  | NU/NStar 345kV Canal Substation | CNR | TRUE | TRUE | ISO-NE |  | SEMA | Document Posted | Document Posted |  |  | Executed | In Service
| 450 | 2014-05-21 16:41 | G | 2014-03-04 | Combustion Turbine | GT | DFO | 245 | 245 | 245 | Fairfield | CT | 2018-05-31 | 2018-05-01 | 2014-05-21 | NU/CL&amp;P Norwalk Harbor 115kV Substation | CNR | FALSE | FALSE |  |  | NOR
| 451 | 2014-05-21 16:42 | G | 2014-03-04 | Combined Cycle | CC | DFO NG | 100 | 345 | 345 | Fairfield | CT | 2018-05-31 | 2018-05-01 | 2014-05-21 | NU/CL&amp;P Norwalk Harbor 115kV substation | CNR | FALSE | FALSE |  |  | NOR
| 452 | 2016-06-21 16:46 | G | 2014-03-04 | Wind | WT | WND | 85 | 85 | 85 | Somerset | ME | 2018-12-30 | 2018-11-30 | 2016-06-17 | Harris substation near the Town of Jackman and Misery Township Somerset County, Maine | NR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 453 | 2014-06-11 13:51 | G | 2014-03-31 | Offshore Wind | WT | WND | 10 | 10 | 10 | Lincoln | ME | 2017-11-13 | 2017-09-11 | 2014-06-11 | CMP Bristol Substation, Bristol Maine | NR | FALSE | FALSE |  |  | ME
| 454 | 2016-06-21 16:47 | G | 2014-04-07 | Wind Increase (see Q452) | WT | WND | 0.8 | 85.8 | 85.8 | Somerset | ME | 2018-12-30 | 2018-11-30 | 2016-06-17 | Harris substation near the Town of Jackman and Misery Township Somerset County, Maine | NR | FALSE | FALSE |  | PD | ME
| 455 | 2015-02-17 08:26 | ETU | 2014-04-17 | 1000 MW HVDC Tie | NA | N/A |  |  |  | Windsor | VT | 2017-12-31 | 2017-12-31 | 2015-02-16 | HQ to VELCO 345 kv Coolidge substation | N/A | FALSE | FALSE |  |  | VT
| 456 | 2015-02-13 07:53 | ETU | 2014-04-17 | 1200 MW HVDC Tie | NA | N/A |  |  |  | Middlesex | MA | 2017-12-31 | 2017-12-31 | 2015-02-12 | HQ to NSTAR 345 kV Mystic substation | N/A | FALSE | FALSE |  |  | BOST
| 457 | 2014-11-19 08:15 | ETU | 2014-04-17 | 500 MW HVDC Tie | NA | N/A |  |  |  | Chittenden | VT | 2017-12-31 | 2017-12-31 | 2014-11-18 | HQ to VELCO 115 kV Essex substation | N/A | FALSE | FALSE |  |  | VT
| 458 | 2018-04-12 09:21 | G | 2014-04-28 | Wind | WT | WND | 104 | 104 | 104 | Aroostook | ME | 2020-12-30 | 2020-09-15 | 2018-04-12 | Pittsfield 345KV | NR | FALSE | FALSE |  | PD | BHE |  | In Progress |  |  |  | Under Study
| 459 | 2018-04-12 09:26 | G | 2014-04-29 | Wind | WT | WND | 104 | 104 | 104 | Aroostook | ME | 2020-12-30 | 2020-09-15 | 2018-04-12 | Pittsfield 345KV | NR | FALSE | FALSE |  | PD | BHE |  | Not Started |  |  |  | Under Study
| 460 | 2018-04-12 09:29 | G | 2014-04-29 | Wind | WT | WND | 104 | 104 | 104 | Aroostook | ME | 2020-12-30 | 2020-09-15 | 2018-04-12 | Pittsfield 345KV | NR | FALSE | FALSE |  | PD | BHE |  | Not Started |  |  |  | Under Study
| 461 | 2018-04-12 09:32 | G | 2014-04-30 | Wind | WT | WND | 104 | 104 | 104 | Aroostook | ME | 2018-12-30 | 2018-09-15 | 2018-04-12 | Pittsfield 345KV | NR | FALSE | FALSE |  | PD | BHE |  | Not Started |  |  |  | Under Study
| 462 | 2018-04-12 09:35 | G | 2014-04-30 | wind | WT | WND | 104 | 104 | 104 | Aroostook | ME | 2020-12-30 | 2020-09-15 | 2018-04-12 | Pittsfield 345KV | NR | FALSE | FALSE |  | PD | BHE |  | Not Started |  |  |  | Under Study
| 463 | 2015-02-17 08:27 | ETU | 2014-04-30 | 425 MW HVDC Tie | NA | N/A |  |  |  | Franklin | VT | 2018-06-30 | 2018-01-30 | 2015-02-16 | HQ to VELCO Williston 115 kV substation | N/A | FALSE | FALSE |  |  | VT
| 464 | 2015-02-17 08:28 | ETU | 2014-05-12 | 1000 MW HVDC | NA | N/A |  |  |  | Suffolk | MA | 2019-06-30 | 2019-01-30 | 2015-02-16 | NMISA to NSTAR K Street 345 kV substation | N/A | FALSE | FALSE |  |  | BOST
| 465 | 2015-02-17 08:28 | ETU | 2014-05-13 | 425 MW HVDC Tie | NA | N/A |  |  |  | Addison | VT | 2018-06-30 | 2018-01-30 | 2015-02-16 | VELCO 345 kV New Haven substation | N/A | FALSE | FALSE |  |  | VT
| 466 | 2015-02-17 08:29 | ETU | 2014-05-14 | AC Tie | NA | N/A |  |  |  | Aroostook | ME | 2016-07-31 | 2016-02-28 | 2015-02-16 | NMISA to Emera Keene Rd Substation | N/A | FALSE | FALSE |  |  | BHE
| 467 | 2020-06-09 08:14 | G | 2014-05-29 | MASSPOWER CNR Recovery | CC | NG | 0 | 256.1 | 279.9 | Hampden | MA | 2014-11-10 | 2014-11-10 |  | 115kV Shawinigan Substation | CNR | FALSE | FALSE |  |  | WMA |  |  |  |  | Executed
| 468 | 2015-03-16 12:38 | G | 2014-06-02 | Manchester Street Station Increase and CNR | CC | NG | 27 | 510 | 510 | Providence | RI | 2015-03-12 | 2015-03-02 |  | CTGs NGrid 115 kV Franklin Square Substation. STGs NGrid 11.5 kV distribution substation | CNR | TRUE | TRUE | ISO-NE | PD | RI |  | Document Posted |  |  | Executed | In Service
| 469 | 2015-06-23 12:15 | G | 2014-06-16 | Bridgeport Energy Uprate | CC | NG | 84 | 560 | 588 | Fairfield | CT | 2015-06-05 | 2015-03-31 |  | UI Singer Substation | CNR | TRUE | TRUE | ISO-NE | PD | SWCT |  | Document Posted |  |  | Executed | In Service
| 470 | 2018-04-12 09:37 | G | 2014-06-19 | Wind | WT | WND | 600.6 | 600.6 | 600.6 | Aroostook | ME | 2018-12-30 | 2018-11-30 | 2018-04-12 | Primary: Orrington Substations 345kV with two alternatives: Keene Rd. Substation 345kV and the Orrington-Albion Rd 345kV line | NR | FALSE | FALSE |  | PD | BHE | Not Started |  |  |  |  | Under Study
| 471 | 2018-04-12 09:41 | G | 2014-06-19 | Wind | WT | WND | 600.6 | 600.6 | 600.6 | Aroostook | ME | 2019-12-30 | 2019-11-30 | 2018-04-12 | Primary: Orrington Substations 345kV with two alternatives: Keene Rd. Substation 345kV and the Orrington-Albion Rd 345kV line | NR | FALSE | FALSE |  | PD | BHE | Not Started |  |  |  |  | Under Study
| 472 | 2015-12-29 11:21 | G | 2014-06-20 | Combined Cycle Increase | CC | DFO NG | 22 | 409.9 | 441.1 | Hampden | MA | 2019-03-01 | 2018-06-01 | 2015-12-28 | 115kV Line 1302 between Buck Pond and Pochassic substations, approximately 1 mile south of Buck Pond | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | In Progress
| 473 | 2014-07-21 11:38 | TS | 2014-06-30 | RNS Application | NA | N/A | 0 | 0 | 0 | Norfolk | MA | 2017-01-01 | 2017-01-01 | 2014-07-21 | NU 115 kV | N/A | FALSE | FALSE |  |  | BOST
| 474 | 2015-04-10 08:30 | G | 2014-08-01 | CNR Increase | CC | NG | 0 | 1600 | 1700 | Middlesex | MA | 2016-05-31 | 2016-05-30 | 2015-04-09 | Mystic 115 and 345 kV Stations | CNR | FALSE | FALSE |  |  | BOST
| 475 | 2015-02-17 08:30 | ETU | 2014-08-14 | 600 MW HVDC Tie | NA | N/A |  |  |  | Berkshire | MA | 2019-12-30 | 2019-09-30 | 2015-02-16 | Alps Sub in NY to WMECO Berkshire Sub in MA | N/A | FALSE | FALSE |  |  | WMA
| 476 | 2016-06-21 16:47 | G | 2014-08-29 | Wind | WT | WND | 52.8 | 52.8 | 52.8 | Penobscot/Washington | ME | 2017-10-01 | 2017-09-01 | 2016-06-17 | Emera Maine (Bangor Hydro) Keene Road Substation (Connecting through Evergreen Gen Lead, LLC Line 56) | CNR | FALSE | FALSE |  | PD | BHE |  | Not Started |  |  |  | Under Study
| 477 | 2019-06-03 08:24 | G | 2014-09-19 | Deerfield Wind Project | WT | WND | 30 | 30 | 30 | Bennington | VT | 2019-06-01 | 2017-12-08 |  | Future GMP Putnam Road 69 kV Substation on Y-25N Line | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | Executed | In Service
| 478 | 2016-08-17 10:41 | G | 2014-10-01 | Wind | WT | WND | 9.6 | 9.6 | 9.6 | Washington | ME | 2016-06-01 | 2016-05-01 | 2016-08-17 | Emera 34.5kV Line 16 | NA | FALSE | FALSE |  |  | BHE
| 479 | 2014-11-19 08:16 | G | 2014-10-17 | Combined Cycle Increase | CC | NG | 33 | 754 | 838 | Rockingham | NH | 2015-03-08 | 2015-03-07 | 2014-11-18 | Watts Brook, North Litchfield | CNR | FALSE | FALSE |  |  | NH
| 480 | 2015-02-23 10:56 | ETU | 2014-11-13 | 1000 MW HVDC Tie | NA | N/A |  |  |  | Suffolk | MA | 2017-12-31 | 2017-10-31 | 2015-02-12 | HQ to NSTAR K Street 115 kV substation | N/A | FALSE | FALSE |  |  | BOST
| 481 | 2022-06-15 12:49 | G | 2014-11-18 | GRE Capacity Uprate | CC | NG | 41 | 762 | 812 | Rockingham | NH | 2017-06-29 | 2015-09-01 |  | Watts Brook, North Litchfield | CNR | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | Executed | In Service
| 482 | 2015-01-08 13:53 | G | 2014-11-18 | Hydro | HD | WAT | 1.318 | 0.325 | 0.325 | Rutland | VT | 2014-12-12 | 2014-12-11 | 2015-01-08 | GMP Power Circuit 85G2 from Ryegate Paper Substation No. 85. | CNR | FALSE | FALSE |  |  | VT
| 483 | 2016-03-30 07:56 | G | 2014-11-21 | Wyman Hydro CNR only | HW | WAT | 0 | 89.9 | 89.9 | Somerset | ME | 2016-03-30 | 2016-03-24 |  | Interconnection of Buyer’s 115 kV gang operated disconnect switch BS &#189; to CMP’s 115 kV Bus No. 2 located in the 115 kV switchyard | CNR | FALSE | FALSE |  |  | ME |  |  |  |  | Executed
| 484 | 2015-11-16 09:24 | G | 2014-12-04 | Newington Gas Turbine Uprate | CC | NG | 27.9 | 596.1 | 634.8 | Rockingham | NH | 2015-10-30 | 2015-10-30 |  | Public Service New Hampshire Newington Switchyard - Gosling Road, Newington, NH | CNR | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | Executed | In Service
| 485 | 2015-04-27 07:58 | G | 2014-12-10 | Combined Cycle | CC | DFO NG | 837 | 837 | 844 | Hampden | MA | 2019-06-01 | 2018-09-01 | 2015-04-23 | Ludlow 19S Substation, Ludlow, MA | CNR | FALSE | FALSE |  |  | WMA |  | In Progress |  |  |  | Under Study
| 486 | 2018-06-08 14:28 | G | 2014-12-19 | Wind | WT | WND | 250 | 250 | 250 | Hancock | ME | 2021-12-01 | 2021-10-01 | 2018-06-08 | Rebel Hill 115 kV | NR | FALSE | FALSE |  | PD | BHE | Document Posted |  |  |  |  | Under Study
| 487 | 2020-04-21 15:23 | G | 2014-12-18 | Cricket Valley Project (QP444 in NYISO Queue) | CC | NG | 1020 | 1020 | 1132 | Dutchess | NY | 2020-04-18 | 2019-07-01 |  | Pleasant Valley - Long Mtn 345 kV | NA | TRUE | FALSE
| 488 | 2015-10-16 11:26 | G | 2014-12-22 | Wind | WT | WND | 73.5 | 73.5 | 73.5 | Windham | VT | 2019-12-31 | 2019-10-01 | 2015-10-16 | VELCO Coolidge - Vermont Yankee 345 kV line | CNR | FALSE | FALSE |  |  | VT | Document Posted | In Progress
| 489 | 2019-11-26 15:26 | G | 2015-01-08 | Clear River | CC | NG | 1030 | 1030 | 1080 | Providence | RI | 2022-05-31 | 2022-01-15 | 2019-11-26 | Sherman Road 345kV Station | NR | TRUE | TRUE | ISO-NE |  | RI | Document Posted | Document Posted |  | Document Posted | IA Filed Unexecuted
| 490 | 2016-05-31 12:28 | G | 2015-01-15 | Kendall Reconfiguration Project | CC | DFO NG | 1.88 | 75 | 75 | Middlesex | MA | 2016-05-31 | 2016-05-31 |  | Where line 875-539 interconnects with TO&#39;&#39;s 115 kv bus at station 875 | CNR | FALSE | FALSE |  |  | BOST |  |  |  |  | Executed | In Service
| 491 | 2016-01-26 14:19 | G | 2015-01-16 | Fore River CNR Increase | CC | DFO NG | 0 | 800 | 843 | Norfolk | MA | 2016-01-20 | 2016-01-20 |  | NSTAR Edgar 115kv substation | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed | In Service
| 492 | 2017-11-03 08:21 | G | 2015-02-05 | Combustion Turbine Generator | GT | DFO NG | 238 | 238 | 238 | Providence | RI | 2020-05-31 | 2020-03-01 | 2017-10-03 | NGRID 345 kV Sherman Road (via OSP Switchyard) | CNR | TRUE | TRUE | ISO-NE | PD | RI | Document Posted | Document Posted |  |  | In Progress
| 493 | 2015-02-17 08:30 | ETU | 2015-02-12 | 1000 MW HVDC - bidirectional | NA | N/A |  |  |  | Middlesex | MA | 2018-12-31 | 2018-09-01 | 2015-02-16 | CMP 345 kV ME Yankee to NSTAR 345 kV Mystic | N/A | FALSE | FALSE |  |  | BOST
| 494 | 2015-02-17 08:31 | ETU | 2015-02-12 | 1000 MW HVDC - bidirectional | NA | N/A |  |  |  | Suffolk | MA | 2018-12-01 | 2018-09-01 | 2015-02-16 | CMP 345 kV ME Yankee to NSTAR 115 kV K Street | N/A | FALSE | FALSE |  |  | BOST
| 495 | 2015-02-17 08:31 | ETU | 2015-02-13 | 1200 MW HVDC Tie - Import Only | NA | N/A |  |  |  | Rockingham | NH | 2018-12-01 | 2018-09-01 | 2015-02-16 | HQ Des Cantons substation to PSNH Deerfield Substation | N/A | FALSE | FALSE |  |  | NH
| 496 | 2019-07-22 09:37 | G | 2015-02-13 | Millinocket Frequency Conversion | HW | WAT | 0 | 126 | 126 | Penobscot | ME | 2019-06-15 | 2019-02-13 |  | Powersville Substation, Emera, 115kV, Line62, existing node424. | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted | Not Required | Not Required | Executed | In Service
| 497 | 2020-02-04 15:33 | G | 2015-02-13 | Beacon Falls Energy Park | FC | NG | 62.9 | 62.9 | 62.9 | New Haven | CT | 2022-04-01 | 2022-02-01 | 2020-01-30 | Beacon Falls Substation, 180 Cold Spring Rd, Beacon Falls, CT Junction of 115kV lines 1570-1 and 1319 | NR | TRUE | TRUE | ISO-NE |  | SWCT | Document Posted | Document Posted |  |  | Executed
| 498 | 2018-02-05 16:16 | ETU | 2015-02-16 | 150 kV HVDC Tie - Import Only | NA | N/A | 400 | 400 | 400 | Colchester | VT | 2020-12-31 | 2020-12-01 | 2018-02-02 | NYPA 230/115 kV substation to VELCO 345 kV New Haven Substation | NI | TRUE | TRUE | ISO-NE |  | VT |  | Document Posted |  |  | In Progress
| 499 | 2019-08-14 14:48 | ETU | 2015-02-16 | Northern Pass Transmission Project (300 kV HVDC/AC Tie) - Import Only | NA | N/A | 1090 | 1090 | 1090 | Rockingham | NH | 2022-12-29 | 2022-11-04 | 2019-08-14 | HQ Des Cantes substation to PSNH Deerfield substation | NI | TRUE | TRUE | ISO-NE | PD | NH |  | Document Posted |  |  | Executed
| 500 | 2019-07-08 13:57 | ETU | 2015-02-16 | Keene Road ETU | NA | N/A |  |  |  | Penobscot | ME | 2018-12-01 | 2018-12-15 | 2018-06-15 | Emera Keene Road substation | N/A | TRUE | FALSE |  | PD | BHE |  | Document Posted
| 501 | 2021-03-26 12:10 | ETU | 2015-02-16 | NE Clean Power Link - controllable HVDC Tie - Import only | NA | N/A | 1000 | 1000 | 1000 | Windsor | VT | 2027-12-31 | 2027-10-28 |  | HQ 735 kV substation to VELCO 345 kV Coolidge substation | NI | TRUE | TRUE | ISO-NE | PD | VT |  | Document Posted | Document Posted |  | Executed
| 502 | 2015-04-17 15:25 | ETU | 2015-02-16 | 345 kV Tie - Phase 1 | NA | N/A | 200 | 200 | 200 | Aroostook | ME | 2016-12-01 | 2016-12-01 | 2015-04-17 | Houlton, ME to MEPCO 396 Line | N/A | FALSE | FALSE |  |  | BHE
| 502 | 2015-04-17 15:26 | ETU | 2015-02-16 | 345 kV Tie - Phase 2 | NA | N/A | 0 | 0 | 0 | Aroostook | ME | 2016-12-01 | 2016-12-01 | 2015-04-17 | Bridgewater, ME to MEPCO 396 Line | N/A | FALSE | FALSE |  |  | BHE
| 503 | 2015-04-15 08:05 | ETU | 2015-02-16 | HVDC Tie - Import only | NA | N/A | 1000 | 1000 | 1000 | Rutland | VT | 2018-12-31 | 2018-10-31 | 2015-04-15 | HQ 735 kV substation to VELCO 345 kV W. Rutland substation | CNI | FALSE | FALSE |  |  | VT
| 504 | 2015-04-15 08:05 | ETU | 2015-02-16 | HVDC Tie - Import only | NA | N/A | 1000 | 1000 | 1000 | Addison | VT | 2018-12-31 | 2018-10-31 | 2015-04-15 | HQ 735 kV substation to VELCO 345 kV New Haven substation | CNI | FALSE | FALSE |  |  | VT
| 505 | 2015-04-17 16:17 | ETU | 2015-02-16 | HVDC Tie - Import only | NA | N/A | 1000 | 1000 | 1000 | Windsor | VT | 2017-12-31 | 2017-12-31 | 2015-04-17 | HQ to VELCO 345 kV Coolidge substation | CNI | FALSE | FALSE |  |  | VT
| 506 | 2020-02-10 11:06 | ETU | 2015-02-16 | Internal HVDC - North to South flow | NA | N/A | 1000 | 1000 | 1000 | Suffolk | MA | 2027-10-01 | 2027-09-01 | 2020-02-10 | NMISA to NSTAR 345 kV K Street substation | N/A | TRUE | TRUE | ISO-NE | PD | BOST |  | Document Posted |  | Document Posted | In Progress | Under Study
| 507 | 2018-01-30 11:37 | ETU | 2015-02-16 | AC Tie - bidirectional flows | NA | N/A | 75 | 75 | 75 | Aroostook | ME | 2017-07-31 | 2017-07-25 | 2018-01-30 | NMISA Mullen substation to Emera Keene Road substation | NI | FALSE | FALSE |  | PD | BHE |  | Not Started |  |  |  | Under Study
| 508 | 2018-10-31 15:30 | ETU | 2015-02-16 | HVDC from NY to WMA - bidirectional | NA | N/A | 600 | 600 | 600 | Berkshire | MA | 2019-08-30 | 2019-07-30 | 2018-10-31 | NY Alps substation to WMECO Berkshire substation | NI | TRUE | TRUE | ISO-NE | PD | WMA |  | Document Posted |  |  | In Progress
| 509 | 2015-04-17 14:50 | ETU | 2015-02-16 | HVDC Line | NA | N/A | 1100 | 1100 | 1100 | Middlesex | MA | 2017-06-30 | 2017-03-30 | 2015-04-17 | Orrington substation to NGRID Tewksbury substation | N/A | FALSE | FALSE |  |  | BOST
| 510 | 2015-04-15 09:10 | ETU | 2015-02-16 | HVDC Line | NA | N/A | 1000 | 1000 | 1000 | Plymouth | MA | 2020-06-01 | 2020-06-01 | 2015-04-15 | NSTAR 345 kV Carver substation | N/A | FALSE | FALSE |  |  | SEMA
| 511 | 2015-04-15 09:10 | ETU | 2015-02-16 | HVDC Line | NA | N/A | 1000 | 1000 | 1000 | Barnstable | MA | 2020-06-01 | 2020-06-01 | 2015-04-15 | NSTAR 345 kV Barnstable substation | N/A | FALSE | FALSE |  |  | SEMA
| 512 | 2015-04-17 16:19 | ETU | 2015-02-16 | AC to HVDC Tie | NA | N/A | 1200 | 1200 | 1200 | Middlesex | MA | 2019-03-31 | 2019-01-01 | 2015-04-17 | NB 345 kV Keswick or St. Andre substation to NGRID 345 kV Wakefield substation | CNI | FALSE | FALSE |  |  | BOST
| 513 | 2015-04-17 16:19 | ETU | 2015-02-16 | Coos ETU | NA | N/A |  |  |  | Coos | NH | 2016-07-01 | 2016-07-01 | 2015-04-17 | PSNH Coos area transmission | N/A | FALSE | FALSE |  |  | NH
| 514 | 2015-04-17 11:14 | ETU | 2015-02-16 | Expand NB/NE Interface | NA | N/A | 350 | 350 | 350 | Aroostook | ME | 2017-11-01 | 2017-09-01 | 2015-04-17 | NB to ME interface | CNI | FALSE | FALSE |  |  | BHE
| 515 | 2015-04-15 09:11 | ETU | 2015-02-16 | HVDC Tie - Import only | NA | N/A | 425 | 425 | 425 | Franklin | VT | 2018-06-30 | 2018-01-30 | 2015-04-15 | HQ to VELCO Williston 115 kV substation | CNI | FALSE | FALSE |  |  | VT
| 516 | 2015-04-15 09:12 | ETU | 2015-02-16 | HVDC Tie - Import only | NA | N/A | 425 | 425 | 425 | Addison | VT | 2018-06-30 | 2018-01-30 | 2015-04-15 | HQ to VELCO 345 kV New Haven substation | CNI | FALSE | FALSE |  |  | VT
| 517 | 2015-07-09 11:24 | ETU | 2015-02-16 | HVDC from S. Maine to Mystic - bidirectional flow | NA | N/A | 1000 | 1000 | 1000 | Middlesex | MA | 2018-12-31 | 2018-11-01 | 2015-07-09 | CMP 345 kV ME Yankee substation to NSTAR 345 kV Mystic substation | N/A | FALSE | FALSE |  | PD | BOST
| 518 | 2015-07-09 11:25 | ETU | 2015-02-16 | HVDC from S. Maine to K Street - bidirectional fl | NA | N/A | 1000 | 1000 | 1000 | Suffolk | MA | 2018-12-01 | 2018-11-01 | 2015-07-09 | CMP 345 kV ME Yankee substation to NSTAR 115 kV K Street substation | N/A | FALSE | FALSE |  | PD | BOST
| 519 | 2015-08-18 15:23 | ETU | 2015-02-16 | HVDC/AC Tie - Import only | NA | N/A | 1200 | 1200 | 1200 | Rockingham | NH | 2019-04-30 | 2019-03-30 | 2015-08-18 | HQ Des Cantons substation to PSNH Deerfield substation | CNI | FALSE | FALSE |  | PD | NH
| 520 | 2016-03-10 15:06 | G | 2015-02-17 | Simple Cycle gas turbine | GT | DFO NG | 109.799 | 109.799 | 109.799 | Fairfield | CT | 2018-05-02 | 2018-04-04 | 2016-03-10 | Eversource Energy 115 kv Line Middle River Substation 28M | CNR | FALSE | FALSE |  | PD | SWCT | Document Posted |  |  |  |  | Under Study
| 521 | 2016-03-10 15:06 | G | 2015-02-17 | Combustion Turbine | GT | DFO NG | 109.799 | 109.799 | 109.799 | Fairfield | CT | 2018-05-02 | 2018-04-04 | 2016-03-10 | CL&amp;P (Eversource) 115 kV Middle River Substation | CNR | FALSE | FALSE |  | PD | SWCT | Not Started |  |  |  |  | Under Study
| 522 | 2015-07-09 10:10 | G | 2015-02-20 | Plainfield 2.3 MW Capacity Restoration (CNR Only) | ST | WDS | 0 | 38.5 | 38.5 | Windham | CT | 2015-07-01 | 2015-07-01 |  | Frybrook substation, 115 KV | CNR | FALSE | FALSE |  |  | CT |  |  |  |  | Executed
| 523 | 2015-09-14 08:05 | G | 2015-02-23 | Combustion Turbine | GT | DFO NG | 226.5 | 226.5 | 233.5 | Providence | RI | 2019-05-01 | 2019-01-01 | 2015-09-11 | Both National Grid 345kV lines 328 and 332 south of the Rhode Island State Energy project | CNR | FALSE | FALSE |  | PD | RI |  | Not Started
| 524 | 2015-03-31 14:41 | G | 2015-02-23 | Combustion Turbine (Alt to Q523) | GT | DFO NG | 0 | 226.5 | 233.5 | Providence | RI | 2019-05-01 | 2019-01-01 | 2015-03-31 | Both National Grid 115kV lines S171 and T172 south of the Rhode Island State Energy tap. | CNR | FALSE | FALSE |  |  | RI
| 525 | 2016-11-08 16:02 | G | 2015-02-25 | Tiverton Power LLC Upgrade | CC | NG | 21.5 | 287.5 | 305.5 | Newport | RI | 2016-11-04 | 2016-11-02 |  | near Bell Rock and Somerset on NGRID 115kV lines L14 and M13. | CNR | TRUE | TRUE | ISO-NE |  | RI |  | Document Posted |  |  | Executed | In Service
| 526 | 2016-09-29 08:24 | G | 2015-02-26 | Combined Cycle Upgrade #1 | CC | NG | 40.583 | 189.583 | 200.73 | Worcester | MA | 2018-10-08 | 2018-09-24 | 2016-09-28 | Milford Power Switch DS-F3 115kV (Nat Grid # D-130-3) and Milford Power Switch DS-A3 115kV (Nat Grid # C-129-3) | CNR | TRUE | FALSE | ISO-NE | PD | CMA |  | Document Posted
| 527 | 2018-12-20 11:25 | G | 2015-02-26 | Combined Cycle Uprate #2 | CC | NG | 30 | 219.583 | 230.73 | Worcester | MA | 2018-12-14 | 2018-12-13 |  | Milford Power Switch DS-F3 115kV (Nat Grid #D-130-3) and Milford Power Switch DS-A3 115kV (Nat Grid #C-129-3). | CNR | TRUE | TRUE | ISO-NE | PD | CMA |  | Document Posted |  | Document Posted | Executed | In Service
| 528 | 2016-09-29 08:26 | G | 2015-02-26 | Combined Cycle Upgrate #3 | CC | NG | 30 | 249.583 | 260.73 | Worcester | MA | 2018-10-08 | 2018-09-24 | 2016-09-28 | Milford Power Switch DS-F3 115kV (Nat Grid # D-130-3) and Milford Power Switch DS-A3 115kV (Nat Grid # C-129-3) | CNR | TRUE | FALSE | ISO-NE | PD | CMA |  | Document Posted
| 529 | 2017-06-26 13:46 | G | 2015-02-26 | Combined Cycle CNR Only | CC | NG | 0 | 585.648 | 615 | Worcester | MA | 2017-11-03 | 2017-10-20 | 2017-06-26 | ANP Blackstone 345kV Bus 110785 Station BLK_336 | CNR | FALSE | FALSE |  |  | CMA |  |  |  |  | In Progress
| 530 | 2017-11-21 15:18 | G | 2015-02-26 | Bridgeport Energy Wet Compression Upgrade | CC | NG | 18 | 578 | 588 | Fairfield | CT | 2018-06-01 | 2018-05-16 | 2017-09-14 | UI Singer Substation | CNR | TRUE | TRUE | ISO-NE | PD | SWCT |  | Document Posted |  |  | Executed
| 531 | 2018-04-05 11:02 | G | 2015-02-27 | Combined Cycle Uprate | CC | NG | 29.999 | 546.8459 | 582.5609 | Penobscot | ME | 2018-08-01 | 2018-07-16 | 2018-04-05 | EMERA Maine-Graham Station via 115kv | CNR | FALSE | FALSE |  | PD | BHE |  | In Progress |  |  |  | Under Study
| 532 | 2016-06-02 11:00 | G | 2015-02-27 | wind | WT | WND | 17.4 | 17.4 | 17.4 | Franklin | VT | 2016-09-15 | 2016-09-01 | 2016-06-01 | GMP 34.5 kV Line between North St. Albans and Sheldon Springs Substations. State Route 105, Swanton, Vermont | CNR | FALSE | FALSE |  |  | VT |  | In Progress |  |  |  | Under Study
| 533 | 2017-08-01 08:26 | G | 2015-02-27 | Milford Upgrades - Phase I | CC | NG | 16.606 | 293 | 318.5 | New Haven | CT | 2017-06-05 | 2017-05-22 |  | 115kV East Devon Substation | CNR | TRUE | TRUE | ISO-NE | PD | SWCT | Document Posted | Document Posted |  |  | Executed | In Service
| 533 | 2017-08-01 08:27 | G | 2015-02-27 | Milford Upgrades - Phase II | CC | NG | 16.606 | 293 | 318.5 | New Haven | CT | 2017-05-22 | 2017-04-12 |  | 115kV East Devon Substation | CNR | TRUE | TRUE | ISO-NE | PD | SWCT | Document Posted | Document Posted |  |  | In Progress
| 534 | 2018-08-01 15:53 | G | 2015-02-27 | Lake Road Upgrades | CC | NG | 49.836 | 882 | 951 | Windham | CT | 2018-05-20 | 2017-11-26 |  | 345kV Lake Road 27E Substation | CNR | TRUE | TRUE | ISO-NE | PD | CT | Document Posted | Document Posted |  |  | Executed | In Service
| 535 | 2020-01-07 15:52 | G | 2015-02-27 | Holiday Hill Community Wind | WT | WND | 4.98 | 4.98 | 4.98 | Hampden | MA | 2020-01-07 | 2019-11-26 |  | WMECo 23 kV line 19J1 adjacent to Pine Hill Road in the town of Russell, Massachusetts | CNR | TRUE | TRUE | NU |  | WMA |  | Document Posted |  |  | Executed | In Service
| 536 | 2015-12-10 11:22 | G | 2015-02-27 | Wind | WT | WND | 4.98 | 4.98 | 4.98 | Orleans | VT | 2016-09-13 | 2016-09-01 | 2015-12-10 | GMP Line 14 between Irasburg and Lowell Substations approximately 3.6 miles from Irasburg Substation adjacent to Kidder Hill Road | CNR | FALSE | FALSE |  |  | VT |  | Not Started
| 537 | 2015-05-22 08:01 | G | 2015-02-28 | Combustion Turbine | GT | NG | 11.965 | 11.965 | 14.097 | Middlesex | MA | 2016-11-30 | 2016-08-31 | 2015-05-21 | MECO 23KV Behen St feeder load side of MTR 04034085 | CNR | FALSE | FALSE |  |  | BOST
| 538 | 2016-04-27 10:49 | G | 2015-03-02 | Internal Combustion | IC | NG | 119.4 | 119.4 | 119.4 | Newport | RI | 2019-05-31 | 2019-04-30 | 2016-04-27 | Near Bell Rock and Somerset on NGRID 115kV lines L14 and M13. Adjacent to existing Tiverton combined cycle generator, possibly associated with existing tap. | CNR | FALSE | FALSE |  | PD | RI | Document Posted
| 539 | 2016-01-29 15:40 | G | 2015-03-02 | Hoosac Wind Project CNR Only | WT | WND | 0 | 28.5 | 28.5 | Franklin | MA | 2016-01-19 | 2016-01-19 |  | Hoosac 69 kV Substation | CNR | FALSE | FALSE |  |  | WMA |  |  |  |  | Executed | In Service
| 540 | 2018-05-21 09:53 | G | 2015-03-02 | CPV Towantic Increase | CC | DFO NG | 55.5 | 800.5 | 830.5 | New Haven | CT | 2018-05-21 | 2018-01-24 |  | CL&amp;P 115kV Lines 1575, 1585 &amp; 1990 | CNR | TRUE | TRUE | ISO-NE | PD | SWCT |  | Document Posted |  |  | Executed | In Service
| 541 | 2016-02-17 07:58 | G | 2015-03-02 | Combined cycle (alt to Q442/472) | CC | DFO NG | 431 | 431 | 452 | Hampden | MA | 2019-03-01 | 2018-06-01 | 2016-02-16 | 115kV Line 1302 between Buck Pond and Pochassic substations, approximately 1 mile south of Buck Pond | CNR | FALSE | FALSE |  |  | WMA | In Progress |  |  |  |  | Under Study
| 542 | 2016-04-18 12:22 | G | 2015-03-02 | combustion turbine | GT | DFO NG | 97 | 97 | 97 | Norfolk | MA | 2018-02-01 | 2017-12-01 | 2016-04-18 | NSTAR 115kV Edgar substation | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted
| 543 | 2019-12-30 13:33 | G | 2015-03-02 | Antrim Wind | WT | WND | 28.4 | 28.4 | 28.4 | Hillsborough | NH | 2019-12-24 | 2019-08-16 |  | Proposed POI is to PSNH 115 kV line L163. | CNR | TRUE | TRUE | ISO-NE | PD | NH |  | Document Posted |  |  | Executed | In Service
| 544 | 2015-08-18 16:01 | G | 2015-03-03 | Increase RISEC Winter CNR | CC | NG | 0 | 613 | 625 | Providence | RI | 2015-08-17 | 2015-08-17 |  | 115 kV RISE substation | CNR | FALSE | FALSE |  |  | RI |  |  |  |  | Executed | In Service
| 545 | 2015-06-29 14:44 | G | 2015-03-03 | Proctor Hydroelectric Station Uprate | HD | WAT | 3.241 | 2 | 2 | Rutland | VT | 2015-06-25 | 2015-05-02 |  | GMP Proctor Substation 46kV Circuit Breaker BB8 | CNR | FALSE | TRUE |  |  | VT |  |  |  |  | Executed | In Service
| 546 | 2019-05-21 11:03 | G | 2015-03-04 | NEA Bell. Uprate (Northeast Energy Associates, LP) | CC | DFO NG | 1.393 | 314.7 | 340.241 | Norfolk | MA | 2018-07-31 | 2018-07-15 |  | 345 kV NEA Bellingham substation | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed | Under Construction
| 547 | 2018-05-31 14:50 | G | 2015-04-28 | Wind uprate | WT | WND | 2.93 | 42.9 | 42.9 | Penobscot | ME | 2018-12-31 | 2018-12-01 | 2018-05-31 | Existing connection between Emera Maine 115kV lines 64 and 97 | NR | FALSE | FALSE |  | PD | BHE |  | Not Started |  |  |  | Under Study
| 548 | 2016-05-20 08:11 | G | 2015-05-28 | Combined Cycle | CC | DFO NG | 870 | 870 | 893 | Plymouth | MA | 2020-05-01 | 2020-01-02 | 2016-05-19 | interconnection between Carver and Tremont substations (NSTAR 115kV Lines 127/128 and 134): ALT connection 345kV Carver substation | CNR | FALSE | FALSE |  | BL | SEMA | Document Posted
| 549 | 2015-07-13 08:29 | G | 2015-05-28 | Combined Cycle | CC | DFO NG | 870 | 870 | 893 | Newport | RI | 2020-05-01 | 2020-01-02 | 2015-07-09 | interconnection on NGRID 115kV M13 &amp; L14 lines connecting to Somerset and Bell Rock substations | CNR | FALSE | FALSE |  | PD | RI
| 550 | 2015-08-04 13:34 | G | 2015-06-12 | Solar | PV | SUN | 19.9 | 19.9 | 19.9 | Franklin | VT | 2016-12-01 | 2016-11-15 | 2015-08-04 | 115 kV Highgate Sub | CNR | FALSE | FALSE |  |  | VT
| 551 | 2015-08-04 13:34 | G | 2015-06-12 | Solar | PV | SUN | 19.9 | 19.9 | 19.9 | Windsor | VT | 2016-12-01 | 2016-11-15 | 2015-08-04 | 115kV Coolidge sub | CNR | FALSE | FALSE |  |  | VT
| 552 | 2020-12-08 11:02 | G | 2015-06-12 | Nutmeg Solar, LLC | PV | SUN | 19.9 | 19.9 | 19.9 | Hartford | CT | 2020-12-07 | 2020-11-15 |  | 115kV Sitico Sub | NR | TRUE | TRUE | ISO-NE |  | CT |  | Document Posted |  |  | Executed | In Service
| 553 | 2015-08-28 14:06 | G | 2015-06-12 | Solar | PV | SUN | 19.9 | 19.9 | 19.9 | Franklin | ME | 2016-12-01 | 2016-11-15 | 2015-08-28 | 115 kV Sturtevant sub | CNR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 554 | 2017-07-05 12:55 | G | 2015-06-18 | Southbridge LFGTE Engine 2 | IC | LFG | 1.6 | 3.2 | 3.2 | Worcester | MA | 2018-08-18 | 2018-07-25 | 2017-07-05 | National Grid 413L4 (Existing facility POI) | CNR | TRUE | FALSE | NGRID |  | CMA |  | Document Posted |  |  | Executed
| 555 | 2019-01-18 12:08 | G | 2015-08-07 | Wind farm | WT | WND | 39.6 | 39.6 | 39.6 | Oxford | ME | 2019-12-01 | 2019-09-01 | 2019-01-18 | CMP Rumford-Kimball Road 115 kV | CNR | TRUE | FALSE |  | PD | ME | Document Posted | Document Posted |  | Not Started
| 556 | 2017-04-27 13:38 | G | 2015-08-07 | Wind Farm | WT | WND | 79.2 | 79.2 | 79.2 | Somerset | ME | 2019-12-01 | 2019-09-01 | 2017-04-27 | CMP Wyman - Harris 115 kV | CNR | FALSE | FALSE |  | PD | ME | Not Started |  |  |  |  | Under Study
| 557 | 2021-10-27 10:38 | G | 2015-08-10 | Farminton Solar | PV | SUN | 78.4 | 78.4 | 78.4 | Franklin | ME | 2021-10-27 | 2021-09-09 |  | CMP Sturtevant Substation - 115 kV | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed | In Service
| 558 | 2015-09-08 12:21 | G | 2015-08-12 | solar | PV | SUN | 20 | 20 | 20 | Franklin | VT | 2016-12-01 | 2016-11-15 | 2015-09-03 | 115 kV Highgate Substation | NA | FALSE | FALSE |  |  | VT
| 559 | 2015-09-08 12:22 | G | 2015-08-12 | solar | PV | SUN | 20 | 20 | 20 | Windsor | VT | 2016-12-01 | 2016-11-15 | 2015-09-03 | 115 kV Coolidge substation | NA | FALSE | FALSE |  |  | VT
| 560 | 2015-10-30 09:54 | G | 2015-08-27 | Solar | PV | SUN | 20 | 20 | 20 | Orange | VT | 2016-12-01 | 2016-11-01 | 2015-10-29 | GMP 46 kV Randolph Center Substation | NA | FALSE | FALSE |  |  | VT
| 561 | 2017-01-26 09:49 | G | 2015-08-27 | Solar | PV | SUN | 20 | 20 | 20 | Franklin | VT | 2017-08-31 | 2017-07-31 | 2017-01-25 | VEC Highgate to Rock Tenn 46 kV line | NA | FALSE | FALSE |  |  | VT
| 562 | 2017-05-24 15:44 | G | 2015-08-27 | Solar | PV | SUN | 20 | 20 | 20 | Orleans | VT | 2017-08-31 | 2017-07-31 | 2017-05-24 | VEC Irasburg H16 46 kV line | NA | FALSE | FALSE |  |  | VT
| 563 | 2015-09-08 12:23 | G | 2015-09-01 | Solar | PV | SUN | 20 | 20 | 20 | Rutland | VT | 2016-11-01 | 2016-10-01 | 2015-09-03 | VELCO 46 kV bus at Florence Substation | NA | FALSE | FALSE |  |  | VT
| 564 | 2016-02-24 14:11 | G | 2015-09-04 | Solar | PV | SUN | 19.9 | 19.9 | 19.9 | Franklin | VT | 2016-12-01 | 2016-11-15 | 2016-02-24 | 115 kV Highgate Substation | CNR | FALSE | FALSE |  | PD | VT
| 565 | 2018-12-20 10:25 | G | 2015-09-08 | Coolidge Solar | PV | SUN | 19.9 | 19.9 | 19.9 | Windsor | VT | 2018-12-20 | 2018-12-12 |  | 115 kV Coolidge Substation | CNR | TRUE | TRUE | ISO-NE | PD | VT |  | Document Posted |  |  | Executed | In Service
| 566 | 2016-04-18 08:18 | G | 2015-09-09 | Solar | PV | SUN | 19.9 | 19.9 | 19.9 | Rutland | VT | 2016-12-01 | 2016-11-01 | 2016-04-15 | VELCO Florence Substation - 46 kV | CNR | FALSE | FALSE |  | PD | VT |  | Not Started |  |  |  | Under Study
| 567 | 2015-09-21 14:17 | G | 2015-09-11 | Solar | PV | SUN | 196 | 196 | 196 | Franklin | VT | 2017-07-01 | 2017-06-15 | 2015-09-21 | VELCO Highgate Substation - 345 kV Bus | CNR | FALSE | FALSE |  |  | VT
| 568 | 2021-03-11 15:12 | G | 2015-09-25 | Solar | PV | SUN | 10 | 10 | 10 | Rockingham | NH | 2021-11-01 | 2021-10-15 | 2021-03-11 | Unitil 34.5 kV W. Port. St. sub | NA | TRUE | TRUE |  |  | NH
| 569 | 2018-06-25 10:46 | ETU | 2015-10-16 | HVDC from ME to MA (MA import only) | NA | N/A | 1200 | 1200 | 1200 | Plymouth | MA | 2021-12-31 | 2021-11-30 | 2018-06-25 | Emera Orrington 345 kV substation to Eversource Jordan Rd | N/A | FALSE | FALSE |  | PD | SEMA | Document Posted
| 570 | 2016-05-31 12:28 | G | 2015-10-21 | Kendall Revised Reconfiguration Project | CC | DFO NG | 0 | 250 | 250 | Middlesex | MA | 2016-05-31 | 2016-05-31 |  | Where line 875-539 interconnects with TO&#39;&#39;s 115KV bus at station | CNR | FALSE | FALSE |  |  | BOST |  |  |  |  | Executed | In Service
| 571 | 2019-08-08 11:18 | ETU | 2015-11-02 | Wyman Area to Larabee Rd Line | NA | N/A | 850 | 850 | 850 | Somerset/Androscoggin | ME | 2019-11-30 | 2019-10-31 | 2019-08-08 | Wyman Area to CMP Larabee Rd 345 kV sub | N/A | TRUE | FALSE | ISO-NE | PD | ME |  | In Progress
| 572 | 2018-04-09 09:22 | G | 2015-11-03 | Wind | WT | WND | 113 | 113 | 113 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2018-04-09 | CMP Larrabee Road 345 kV station | NR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 573 | 2019-08-08 11:18 | G | 2015-11-03 | Wind | WT | WND | 245.38 | 245.38 | 245.38 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road Station 345 kV | NR | TRUE | FALSE | ISO-NE | PD | ME |  | In Progress
| 574 | 2019-08-08 11:19 | G | 2015-11-03 | Wind | WT | WND | 216.41 | 216.41 | 216.41 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road Station 345 kV | NR | TRUE | FALSE | ISO-NE | PD | ME |  | In Progress
| 575 | 2017-08-25 10:39 | G | 2015-11-03 | Casco Bay Energy Storage | OT | BAT | 16.2 | 16.2 | 16.2 | Cumberland | ME | 2016-12-31 | 2016-12-02 |  | CMP&#39;&#39;s PTF 115kV Upper Bus at William F Wyman Station | NR | TRUE | TRUE | ISO-NE |  | ME |  | Document Posted |  |  | Executed | In Service
| 576 | 2019-08-08 11:20 | G | 2015-11-12 | Battery Storage | OT | WND BAT | 52.26 | 241.49 | 241.49 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road station 345 kV | NR | TRUE | FALSE | ISO-NE | PD | ME |  | In Progress
| 577 | 2019-08-08 11:20 | G | 2015-11-12 | Battery Storage | OT | WND BAT | 25.08 | 270.46 | 270.46 | Frqanklin | ME | 2019-11-09 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road Station,345 kV | NR | TRUE | FALSE | ISO-NE | PD | ME |  | In Progress
| 578 | 2019-08-08 11:21 | G | 2015-11-20 | Solar | PV | SUN | 152 | 152 | 152 | Somerset | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road 345 kV. | NR | TRUE | FALSE | ISO-NE | PD | ME |  | In Progress
| 579 | 2016-04-21 14:52 | G | 2015-11-25 | Energy Center | OT | NG OTH | 570.1 | 570.1 | 569.6 | Cheshire | NH | 2020-06-01 | 2020-03-01 | 2016-04-21 | Eversource (PSNH) 379 line crossing Forest Lake Road (POI will be south of Forest Lake Road), which is in close proximity to the Project site. | CNR | FALSE | FALSE |  | PD | VT | Not Started |  |  |  |  | Under Study
| 580 | 2016-05-18 08:28 | G | 2015-11-30 | Combined Cycle | CC | DFO NG | 1020 | 1020 | 1030 | Worcester | MA | 2020-05-31 | 2020-01-15 | 2016-05-17 | Anticipated interconnection is the National Grid 345kV line 366 between the West Farnum and Millbury substations, and/or the Eversource 345kV line 3361 between Sherman Rd and Blackstone. | CNR | FALSE | FALSE |  | PD | CMA |  | Not Started
| 581 | 2018-02-05 08:40 | G | 2015-12-02 | Solar | PV | SUN | 2.66 | 2.66 | 2.66 | Worcester | MA | 2017-12-01 | 2017-11-01 | 2018-02-05 | POI is the GRID 69KV switchyard at the Harrington Street Facility. 229 Harrington Street, East Brookfield, MA. National Grid has this information. | CNR | TRUE | FALSE |  |  | CMA |  | Document Posted |  |  | In Progress
| 582 | 2018-02-05 08:41 | G | 2015-12-02 | Solar | PV | SUN | 3.11 | 3.105 | 3.105 | Worcester | MA | 2017-12-01 | 2017-11-01 | 2018-02-05 | POI is the GRID 69KV switchyard at the Harrington Street Facility. 229 Harrington Street, East Brookfield, MA. National Grid has this information. | CNR | TRUE | FALSE |  |  | CMA |  | Document Posted |  |  | In Progress
| 583 | 2020-11-09 16:11 | G | 2015-12-04 | Sanford Airport Solar | PV | SUN | 50 | 50 | 50 | York | ME | 2020-11-07 | 2020-10-06 |  | CMP Sanford 115kV Substation | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed | In Service
| 584 | 2018-10-31 15:31 | ETU | 2015-12-10 | ETU CNI only (see Q508) | NA | N/A | 0 | 0 | 0 | Berkshire | MA | 2019-08-31 | 2019-07-31 | 2018-10-31 | NY Alps substation to WMECO Berkshire substation | CNI | FALSE | FALSE |  |  | WMA |  | Document Posted |  |  | In Progress
| 585 | 2018-03-05 15:26 | ETU | 2015-12-14 | HVDC Tie NB to Mystic | NA | N/A | 900 | 900 | 900 | Middlesex | MA | 2020-12-30 | 2020-11-30 | 2018-03-05 | NB 345 kV Coleson Cove substation to NSTAR 345 kV Mystic substation | CNI | FALSE | FALSE |  | PD | BOST | Not Started
| 586 | 2016-10-28 14:15 | G | 2016-01-04 | Hemphill Increase | ST | WDS | 3.363 | 17.5 | 17.5 | Sullivan | NH | 2016-10-28 | 2016-10-28 |  | 34.5 Kv PSNH 316 Utility Line | CNR | TRUE | TRUE | ISO-NE |  | NH |  | Not Required |  |  | Executed | In Service
| 587 | 2016-09-29 07:52 | G | 2016-01-07 | Solar | PV | SUN | 98 | 98 | 98 | Cheshire | NH | 2018-07-01 | 2018-06-15 | 2016-09-28 | 115 kV Eversource Fitzwilliam Substation | CNR | FALSE | FALSE |  | PD | VT |  | Not Started
| 588 | 2021-12-27 14:16 | G | 2016-01-07 | Quinebaug Solar | PV | SUN | 49 | 49 | 49 | Windham | CT | 2021-12-18 | 2021-12-11 |  | Killingly to Tunnel 115 kV line (approx 5.5 miles south of Brooklyn Substation) GPS Coordinates: - 71 55’ 27.9” W - 41 44’ 14.21” N | NR | TRUE | TRUE | ISO-NE | PD | CT |  | Document Posted |  |  | Executed | In Service
| 589 | 2018-04-12 09:43 | ETU | 2016-01-11 | AC Line to Pittsfield, ME | NA | N/A | 550 | 550 | 550 | Somerset | ME | 2019-12-31 | 2019-11-30 | 2018-04-12 | CMP Section 3023 345 kV Line | N/A | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 590 | 2018-04-12 09:49 | ETU | 2016-01-11 | AC Line from NMISA to Chester and Pittsfield, ME | NA | N/A | 1200 | 1200 | 1200 | Somerset and Penobscot | ME | 2019-12-31 | 2019-11-30 | 2018-04-12 | Emera Keene Rd substation and CMP Section 3023 345 kV Line | N/A | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 591 | 2018-04-12 09:53 | ETU | 2016-01-20 | AC Line | NA | N/A | 400 | 400 | 400 | Cumberland | ME | 2019-11-30 | 2019-10-31 | 2018-04-12 | CMP Surowiec Area | N/A | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 592 | 2023-01-09 10:03 | G | 2016-01-21 | Bear Swamp Unit 1 and 2 Upgrade | PS | WAT | 66 | 663 | 663 | Berkshire | MA | 2023-01-06 | 2022-12-01 |  | GRID 230 kV Bear Swamp substation | CNR | TRUE | TRUE | ISO-NE | PD | WMA |  | Document Posted |  |  | Executed | Partially In Service
| 593 | 2018-04-09 10:27 | G | 2016-01-27 | Wind | WT | WND | 0 | 216.41 | 216.41 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2018-04-09 | CMP&#39;&#39;s Orrington - Albion Road 345 kV line, section 3023 | NR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 594 | 2018-04-09 10:28 | G | 2016-01-27 | Wind | WT | WND | 0 | 245.48 | 245.48 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2018-04-09 | CMP&#39;&#39;s existing Orrington - Albion Road 345 kV line section 3023 | NR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 595 | 2017-06-26 14:07 | G | 2016-02-08 | Bridgeport Energy PSS Tuning | GT | NG | 0 | 578 | 588 | Fairfield | CT | 2016-10-28 | 2016-10-28 |  | UI Singer Substation | CNR | TRUE | TRUE | ISO-NE |  | SWCT |  | Document Posted |  |  | Executed | In Service
| 596 | 2017-05-19 13:39 | G | 2016-02-08 | Combined Cycle | CC | DFO NG | 1120 | 1120 | 1170 | Windham | CT | 2020-06-01 | 2019-10-01 | 2017-05-19 | Killingly or Lake Road 345 kV | CNR | FALSE | FALSE |  | PD | CT | In Progress |  |  |  |  | Under Study
| 597 | 2018-04-20 08:37 | G | 2016-02-24 | Hydro | HD | WAT | 28.325 | 28.325 | 28.325 | Oxford/Franklin/Androscoggin | ME | 2019-06-01 | 2019-05-31 | 2018-04-20 | CMP Section 230 (115 kV) at southeast end, high side of Verso Androscoggin substation | CNR | FALSE | FALSE |  | PD | ME | Document Posted | Not Started |  |  |  | Under Study
| 598 | 2018-03-28 16:13 | G | 2016-03-07 | Combined Cycle | CC | DFO NG | 563 | 563 | 576 | Windham | CT | 2022-03-01 | 2021-09-01 | 2018-03-28 | Killingly/Lake Road 345 kV | CNR | TRUE | FALSE | ISO-NE | PD | CT |  | Document Posted |  |  | In Progress
| 599 | 2018-01-23 16:25 | G | 2016-04-05 | Solar | PV | SUN | 65 | 65 | 65 | Cheshire | NH | 2018-04-18 | 2018-04-15 | 2018-01-23 | NGrid 115kV line from Vernon road tap to the Vernon Road Substation | CNR | FALSE | FALSE |  | PD | VT |  | In Progress |  |  |  | Under Study
| 600 | 2017-08-28 16:18 | G | 2016-04-14 | Combined Cycle Uprate | CC | DFO NG | 21.077 | 615.873 | 649.794 | Providence | RI | 2016-07-31 | 2016-07-15 | 2017-08-28 | NGRID 345kV Sherman Road (existing OSP I and II switchyard) | CNR | FALSE | FALSE |  | PD | RI | Not Started |  |  |  |  | Under Study
| 601 | 2017-08-28 16:19 | G | 2016-04-14 | Combined Cycle Upgrade | CC | DFO NG | 40 | 655.873 | 689.794 | Providence | RI | 2020-05-31 | 2020-03-01 | 2017-08-28 | NGRID 345kV Sherman Road (existing OSP I and II switchyard) | CNR | FALSE | FALSE |  | PD | RI | Not Started |  |  |  |  | Under Study
| 602 | 2023-10-25 10:59 | G | 2016-04-14 | Moore Station Uprate | HW | WAT | 4.6 | 195.9 | 195.9 | Grafton | NH | 2023-10-18 | 2023-09-22 |  | NGRID at Moore power station switchyard 230kV | CNR | TRUE | TRUE | ISO-NE |  | NH | Document Posted | Document Posted |  |  | Executed | In Service
| 603 | 2022-06-15 12:49 | G | 2016-04-15 | Essential Power Newington - CNRC Increase | CC | DFO NG | 0 | 596.1 | 634.9 | Rockingham | NH | 2016-10-28 | 2016-10-28 |  | Public Service New Hampshire Newington Switchyard - Gosling Road, Newington, NH | CNR | FALSE | FALSE |  |  | NH
| 604 | 2018-08-01 15:58 | G | 2016-04-20 | Lake Road CNR Only (see Q534) | CC | NG | 0 | 882 | 951 | Windham | CT | 2018-05-20 | 2017-11-26 |  | 345kV Lake Road 27E Substation | CNR | FALSE | FALSE |  | PD | RI |  |  |  |  | Executed
| 605 | 2020-11-09 16:12 | G | 2016-04-21 | Sanford Airport Solar CNR only | PV | SUN | 0 | 50 | 50 | York | ME | 2020-11-07 | 2020-10-06 |  | CMP Sanford 115kV substation | NR | FALSE | FALSE |  | PD | ME |  |  |  |  | Executed | In Service
| 606 | 2017-06-08 09:32 | G | 2016-04-21 | Huntington Falls 2017 Upgrades | HD | WAT | 1.59 | 1.24 | 1.24 | Chittenden | VT | 2017-04-12 | 2017-03-13 |  | GMP Huntington Falls Substation 46 kV Circuit Breaker BB-10 | CNR | TRUE | TRUE |  | PD | VT |  |  |  |  | Executed | In Service
| 607 | 2017-11-29 08:44 | G | 2016-04-21 | Canton Mountain Wind CNR Only | WT | WND | 0 | 22.8 | 22.8 | Oxford | ME | 2017-12-01 | 2017-10-18 |  | CMP Ludden Lane Substation, Canton, Maine | CNR | FALSE | FALSE |  |  | ME |  |  |  |  | Executed | In Service
| 608 | 2016-05-24 15:02 | G | 2016-04-22 | Combined Cycle GT | CC | NG WO | 68.01 | 68.01 | 69.5 | Bristol | MA | 2020-05-01 | 2019-12-31 | 2016-05-24 | Located at current Cleary node 375,376 interconnected with National Grid s-8 and v-5 line, SEMA load zone. | CNR | FALSE | FALSE |  | PD | SEMA
| 609 | 2016-06-03 15:37 | G | 2016-04-22 | Gas Turbine Upgrade | GT | DFO | 23.52 | 162 | 162 | New Haven | CT | 2020-05-31 | 2020-04-21 | 2016-06-03 | POI is the CL&amp;P Devon 115kv Substation | CNR | FALSE | FALSE |  | PD | CT
| 610 | 2017-03-27 09:14 | G | 2016-04-22 | Steam Turbines | ST | BLQ DFO KER WDS | 75 | 75 | 80 | Franklin | ME | 2018-05-31 | 2018-05-30 | 2017-03-24 | Central Maine Power (CMP) Riley 115kV Section 230 (K230-2) | CNR | FALSE | FALSE |  | PD | ME | Document Posted
| 611 | 2018-01-04 09:19 | G | 2016-04-25 | Combustion Turbine | GT | NG | 102 | 102 | 102 | Fairfield | CT | 2019-06-01 | 2019-01-01 | 2018-01-04 | Eversource Energy 115kV MiddleRiver Substation Danbury, CT | CNR | TRUE | FALSE | ISO-NE | PD | SWCT |  | Document Posted |  |  | In Progress
| 612 | 2017-09-25 15:30 | G | 2016-04-26 | Medway Hydro - CNR only | HD | WAT | 0 | 4.003 | 4.003 | Penobscot | ME | 2017-08-14 | 2017-08-14 |  | Medway Substation | CNR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed | In Service
| 613 | 2016-07-14 07:59 | G | 2016-06-28 | Solar | PV | SUN | 63 | 63 | 63 | Windham | CT | 2018-07-01 | 2018-06-15 | 2016-07-13 | Killingly to Tunnel 115 kV line | CNR | FALSE | FALSE |  | PD | CT
| 614 | 2016-07-14 07:59 | G | 2016-06-28 | Solar | PV | SUN | 78.4 | 78.4 | 78.4 | Franklin | ME | 2018-07-01 | 2018-06-15 | 2016-07-13 | CMP Sturtevant Substation - 115 kV | CNR | FALSE | FALSE |  | PD | ME
| 615 | 2016-07-14 07:58 | G | 2016-06-28 | Solar | PV | SUN | 78.4 | 78.4 | 78.4 | Cheshire | NH | 2018-07-01 | 2018-06-15 | 2016-07-13 | Mondanock to Ashburnham Eversource 115 kV line | CNR | FALSE | FALSE |  | PD | VT
| 616 | 2016-07-14 07:58 | G | 2016-07-01 | Solar | PV | SUN | 19.9 |  |  | Windsor | VT | 2017-07-01 | 2017-06-15 | 2016-07-13 | 115 kV Cooolidge Substation | CNR | FALSE | FALSE |  | PD | VT
| 617 | 2024-07-23 11:46 | G | 2016-07-22 | Simple Cycle Gas Turbine | GT | DFO NG | 61.851 | 61.851 | 67.851 | Essex | MA | 2024-06-29 | 2024-01-11 |  | Peabody Waters River Substation | NA | TRUE | TRUE | NGRID |  | BOST
| 618 | 2022-08-10 12:59 | G | 2016-08-01 | Bay State Offshore Wind 1 | WT | WND | 800 | 800 | 800 | NA | MA | 2026-05-31 | 2025-09-21 | 2022-08-10 | National Grid, 345 kV Brayton Point Substation, Somerset, MA | NR | TRUE | TRUE | ISO-NE | PD | RI | Document Posted | Document Posted |  | Document Posted | Executed
| 619 | 2017-01-25 15:01 | ETU | 2016-09-16 | Bi-directional AC LIne | NA | N/A |  |  |  | Berkshire | MA | 2021-12-31 | 2021-11-30 | 2017-01-25 | NY Alps 345 kV Substation to WMECO Berkshire 345 kV substation | N/A | FALSE | FALSE |  | PD | WMA
| 620 | 2020-08-13 07:49 | G | 2016-10-07 | Solar | PV | SUN | 75 | 75 | 75 | Washington | ME | 2022-05-31 | 2022-05-15 | 2020-08-12 | Emera 115 kV Deblois substation | NR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  |  | In Progress
| 621 | 2018-04-12 10:01 | G | 2016-10-17 | Wind | WT | WND | 93.6 | 93.6 | 93.6 | Somerset | ME | 2020-01-15 | 2019-12-30 | 2018-04-12 | CMP Section 3023 345 kV line (via Johnson Mountain substation) | CNR | FALSE | FALSE |  | PD | ME | Not Started |  |  |  |  | Under Study
| 622 | 2022-04-29 12:24 | G | 2016-10-17 | Cogen DG | GT | NG | 43 | 43 | 43 | Middlesex | MA | 2021-09-30 | 2020-08-31 |  | Putnum Station 831 | NA | TRUE | TRUE | NU |  | CMA
| 623 | 2021-08-12 15:31 | G | 2016-10-31 | Solar | PV | SUN | 150 | 150 | 150 | York | ME | 2022-12-31 | 2022-12-15 | 2021-08-12 | CMP/Eversource 345 kV Line 391 from Buxton substation to Scobie Pond substation (approx. 27.7 miles from Buxton substation) | NR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed | Under Study
| 624 | 2020-08-26 15:59 | G | 2016-11-08 | Vineyard Offshore Wind | WT | WND | 800 | 800 | 800 | NA | MA | 2025-12-30 | 2024-01-02 |  | 115 kV Barnstable Substation | CNR | TRUE | TRUE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  |  | Executed | Under Construction
| 625 | 2019-04-11 16:49 | ETU | 2016-11-10 | 345 kV AC line | NA | N/A | 1600 | 1600 | 1600 | Bristol | MA | 2023-12-31 | 2023-08-31 | 2019-04-11 | 345 kV Brayton point substation | N/A | FALSE | FALSE |  | PD | RI |  | In Progress |  |  |  | Under Study
| 626 | 2018-04-03 09:37 | G | 2016-12-14 | Wind | WT | WND | 376.2 | 376.2 | 376.2 | Aroostook | ME | 2019-12-01 | 2019-10-01 | 2018-04-02 | MEPCO 396 line | CNR | FALSE | FALSE |  | PD | BHE | Not Started |  |  |  |  | Under Study
| 627 | 2019-07-16 12:29 | ETU | 2016-12-27 | 400 kV HVDC Tie - Import Only | NA | N/A | 1200 | 1200 | 1200 | Grafton | NH | 2022-12-31 | 2022-10-01 | 2019-07-16 | GRID 230 kV Comerford Substation | CNI | FALSE | FALSE |  |  | NH | Document Posted | In Progress |  |  |  | Under Study
| 628 | 2017-09-15 09:52 | G | 2017-03-07 | Solar | PV | SUN | 30 | 30 | 30 | Cheshire | NH | 2018-12-31 | 2018-09-30 | 2017-08-09 | Eversource 34.5 kV Monadnock SS (3120 line) | NA | FALSE | FALSE |  |  | NH
| 629 | 2017-05-24 09:27 | G | 2017-03-07 | Solar | PV | SUN | 20 | 20 | 20 | New Haven | CT | 2018-12-31 | 2018-11-15 | 2017-05-23 | CT_NU 115 kV Line from Wallingford to NU_1208_WAL. Proposed POI is located at 41° 26’ 27.9” N , 72° 50’36.6” W (see the drawing with file name "Project Facility Layout - 22NOV16.pdf" for a map of proposed POI location). | NR | FALSE | FALSE |  |  | CT
| 630 | 2017-11-29 13:51 | G | 2017-04-05 | Project Increase | ST | MSW | 2.153 | 15.67 | 15.67 | Hartford | CT | 2017-09-01 | 2017-09-01 | 2017-11-21 | Connecticut Light and Powers 13.8 kv Forestville 12A Substation | CNR | FALSE | FALSE |  |  | CT |  | In Progress
| 631 | 2017-07-26 14:49 | G | 2017-04-05 | CHP | IC | NG | 8 | 8.64 | 8.64 | Coos | NH | 2018-07-15 | 2018-06-15 | 2017-07-26 | PSNH 34.5 kV Line, Berlin, NH | CNR | FALSE | FALSE |  |  | NH
| 632 | 2020-01-23 12:49 | G | 2017-04-05 | Offshore Wind w/ battery storage | OT | WND BAT | 880 | 880 | 880 | NA | MA | 2024-12-06 | 2024-04-05 | 2020-01-23 | Eversource, 115kV Bourne Substation, Barnstable County, Massachusetts | CNR | TRUE | FALSE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  | Not Started |  | Under Study
| 633 | 2020-02-24 16:08 | G | 2017-04-06 | Passadumkeag Wind CNR only | WT | WND | 0 | 39.97 | 39.97 | Penobscot | ME | 2019-06-28 | 2019-06-28 |  | Existing connection between Emera Maine 115kV lines 64 and 97 | NR | FALSE | FALSE |  |  | BHE |  |  |  |  | In Progress
| 634 | 2019-08-08 11:23 | G | 2017-04-11 | Wind CNR (see Q573) | WT | WND | 0 | 245.38 | 245.38 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larabee Road 345 kV station | CNR | FALSE | FALSE |  |  | ME
| 635 | 2019-08-08 11:23 | G | 2017-04-13 | Wind CNR (see Q574) | WT | WND | 0 | 216.41 | 216.41 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larabee Road 345 kV station | CNR | FALSE | FALSE |  | PD | ME
| 636 | 2019-08-08 11:25 | G | 2017-04-13 | BSS CNR only (see Q576) | OT | WND BAT | 0 | 241.49 | 241.49 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road station 345 kV | CNR | FALSE | FALSE |  | PD | ME
| 637 | 2019-08-08 11:25 | G | 2017-04-13 | BSS CNR only (see Q577) | OT | WND BAT | 0 | 270.46 | 270.46 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road Station,345 kV | CNR | FALSE | FALSE |  | PD | ME
| 638 | 2019-08-08 11:26 | G | 2017-04-13 | Solar CNR only (see Q578) | PV | SUN | 0 | 152 | 152 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road 345 kV. | CNR | FALSE | FALSE |  | PD | ME
| 639 | 2020-11-02 15:01 | ETU | 2017-04-19 | NECEC 1200 MW HVDC (import only) - controllable | NA | N/A | 1200 |  |  | Androscoggin | ME | 2026-01-07 | 2025-09-01 |  | CMP Larrabee Rd 345 kV Substation | NI | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 640 | 2020-12-01 13:04 | ETU | 2017-04-21 | 1000 MW HVDC (import only) | NA | N/A | 1000 |  |  | Plymouth | MA | 2022-12-31 | 2022-11-30 | 2020-11-30 | Northern Interconnection: Coleson Cove 345kV Substation, New Brunswick Southern Interconnection: 345kV lines from Pilgrim Substation, Plymouth, Massachusetts | NI | FALSE | FALSE |  | PD | SEMA | In Progress |  |  |  |  | Under Study
| 641 | 2018-08-13 13:49 | G | 2017-04-24 | Wind | WT | WND | 65.55 | 54.6 | 54.6 | Oxford | ME | 2020-12-31 | 2020-09-15 | 2018-08-13 | CMP 115 kV Line 210 | CNR | FALSE | FALSE |  | PD | ME | Document Posted | Not Started |  |  |  | Under Study
| 642 | 2017-05-31 14:58 | G | 2017-04-26 | Repowering Increase | GT | DFO NG | 34.85 | 98.12 | 98.16 | Norfolk | MA | 2021-05-22 | 2021-02-22 | 2017-05-31 | BELD station 16 switchyard | CNR | FALSE | FALSE |  |  | SEMA
| 643 | 2017-05-24 09:27 | G | 2017-04-27 | Solar CNR only | PV | SUN | 0 | 20 | 20 | New Haven | CT | 2018-12-31 | 2018-11-15 | 2017-05-23 | CT_NU 115 kV Line from Wallingford to NU_1208_WAL. Proposed POI is located at 41° 26’ 27.9” N , 72° 50’36.6” W (see the attached site layout drawing). | CNR | FALSE | FALSE |  |  | CT
| 644 | 2017-07-24 11:01 | G | 2017-04-28 | Solar | PV | SUN | 20.1 | 20.1 | 20.1 | Franklin | VT | 2018-10-31 | 2018-10-15 | 2017-07-24 | VEC Sheldon - Rocktenn 46 kV line | CNR | FALSE | FALSE |  |  | VT
| 645 | 2017-07-24 11:02 | G | 2017-04-28 | Solar | PV | SUN | 20.1 | 20.1 | 20.1 | Orange | VT | 2019-12-15 | 2019-11-15 | 2017-07-24 | GMP Randolph Center Substation 46 kV | CNR | FALSE | FALSE |  |  | VT
| 646 | 2017-07-24 11:02 | G | 2017-04-28 | Solar | PV | SUN | 20.1 | 20.1 | 20.1 | Franklin | VT | 2019-09-01 | 2019-08-01 | 2017-07-24 | VEC Highgate - Enosburg 46 kV line, 700 feet from Highgate | CNR | FALSE | FALSE |  |  | VT
| 647 | 2020-06-11 07:06 | G | 2017-04-28 | Gas turbine repowering | GT | DFO NG | 23 | 376 | 378 | Middlesex | CT | 2022-05-31 | 2022-02-01 | 2020-06-11 | Middletown Substation at 115KV, MD#2 breaker position | CNR | TRUE | TRUE | ISO-NE |  | CT | Document Posted | Document Posted |  |  | In Progress
| 648 | 2017-06-01 08:11 | G | 2017-04-28 | Gas Turbine Repowering | GT | DFO NG | 0 | 376 | 378 | Middlesex | CT | 2021-05-31 | 2021-03-01 | 2017-06-01 | Middletown Station 345KV Substation | CNR | FALSE | FALSE |  |  | CT
| 649 | 2022-12-14 09:08 | G | 2017-05-04 | Silver Maple Wind | WT | WND | 20 | 20 | 20 | Penobscot | ME | 2022-12-14 | 2022-09-24 |  | Pisgah Mountain Substation, Clifton, ME. 115 kv Bus. | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed | In Service
| 650 | 2018-02-05 16:17 | ETU | 2017-05-08 | ETU CNI only (see Q498) | NA | N/A | 0 |  |  | Colchester | VT | 2021-12-31 | 2021-10-01 | 2018-02-02 | N/A | CNI | FALSE | FALSE |  |  | VT
| 651 | 2019-07-29 14:47 | ETU | 2017-05-11 | AC tie line (import only) | NA | N/A | 600 |  |  | Berkshire | MA | 2023-12-31 | 2023-09-15 | 2019-07-29 | NY Alps 345kV substation and Eversource Berkshire 345 kV substation | CNI | TRUE | FALSE | ISO-NE |  | WMA |  | Document Posted |  | Not Started |  | Under Study
| 652 | 2018-04-12 10:08 | ETU | 2017-06-01 | AC to Larabee Road | NA | N/A | 460 |  |  | Lewiston | ME | 2020-12-31 | 2020-11-30 | 2018-04-12 | Larrabee Road 345 kV Substation in Lewiston, Androscoggin county Maine 04240. | NI | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 653 | 2019-05-14 10:55 | G | 2017-06-09 | Number Nine Wind CNR only (Q417) | WT | WND | 0 | 250 | 250 | Aroostook | ME | 2021-10-31 | 2021-04-05 | 2019-05-13 | Pittsfield 345KV | CNR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed
| 654 | 2018-04-16 12:27 | G | 2017-06-09 | Wind CNR only (see Q460, 461, 462) | WT | WND | 0 | 312 | 312 | Aroostook | ME | 2020-12-30 | 2020-09-15 | 2018-04-12 | Pittsfield 345KV | CNR | FALSE | FALSE |  |  | BHE
| 655 | 2021-11-30 09:56 | G | 2017-06-15 | RoxWind | WT | WND | 15.3 | 15.3 | 15.3 | Oxford | ME | 2021-11-30 | 2021-11-09 |  | 34.5 kV Bus at Roxbury Substation, Roxbury, Maine | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed | In Service
| 656 | 2021-02-23 14:19 | G | 2017-06-28 | Weaver Wind CNR (see Q420) | WT | WND | 0 | 72.6 | 72.6 | Hancock | ME | 2020-12-12 | 2020-10-13 |  | EMERA Maine 115kV Bull Hill switching station | NR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed | In Service
| 657 | 2019-09-12 09:46 | ETU | 2017-06-29 | ETU to increase Downeast Loop transfer | NA | N/A |  |  |  | Hancock | ME | 2020-12-31 | 2020-11-30 | 2019-09-12 | N/A | N/A | FALSE | FALSE |  | PD | BHE | Document Posted | Not Started |  |  |  | Under Study
| 658 | 2018-04-12 10:12 | ETU | 2017-07-14 | AC to Larabee Road increase (see Q652) | NA | N/A | 200 |  |  | Lewiston | ME | 2020-12-31 | 2020-11-30 | 2018-04-12 | Larrabee Road 345 kV Substation in Lewiston, Androscoggin county Maine 04240. | NI | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 659 | 2018-04-12 10:16 | ETU | 2017-07-18 | AC to Larabee Road increase (See Q652 and 658) | NA | N/A | 540 |  |  | Lewiston | ME | 2020-12-31 | 2020-11-30 | 2018-04-12 | Larrabee Road 345 kV Substation in Lewiston, Androscoggin county Maine 04240. | NI | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 660 | 2020-09-10 10:01 | G | 2017-07-20 | Solar | PV | SUN | 20 | 20 | 20 | Windham | VT | 2022-07-01 | 2022-06-01 | 2020-09-10 | National Grid line tap 69 kV transmission line (D-4), feeding the Vernon Station No. 13 | CNR | TRUE | TRUE | ISO-NE | NA | NH | Document Posted | Document Posted |  |  | In Progress
| 661 | 2018-04-12 10:19 | ETU | 2017-07-20 | 345 kV AC line from Quebec to ME | NA | N/A | 450 |  |  | Franklin | ME | 2022-12-01 | 2022-09-01 | 2018-04-12 | CMP/Avangrid 345 kV Larabee Road | N/A | FALSE | FALSE |  | PD | ME
| 662 | 2018-04-12 10:40 | G | 2017-07-20 | Wind | WT | WND | 150 | 150 | 150 | Franklin | ME | 2022-12-01 | 2022-09-01 | 2018-04-12 | CMP Avangrid Larrabee Road 345 kV Substation | CNR | FALSE | FALSE |  | PD | ME
| 663 | 2018-04-12 11:03 | G | 2017-07-21 | Wind | WT | WND | 0 | 241.2 | 241.2 | Franklin | ME | 2020-10-31 | 2020-08-01 | 2018-04-12 | CMP Larrabee Road Station 345 kV | CNR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 664 | 2018-04-12 11:07 | G | 2017-07-21 | Wind | WT | WND | 0 | 214.3 | 214.3 | Franklin | ME | 2020-10-31 | 2020-08-01 | 2018-04-12 | CMP Larrabee Road Station 345 kV | CNR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 665 | 2018-04-12 11:10 | G | 2017-07-21 | Battery storage addition (see Q663) | OT | WND BAT | 0 | 265.6 | 265.6 | Franklin | ME | 2020-10-31 | 2020-08-01 | 2018-04-12 | CMP Larrabee Road Station,345 kV | CNR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 666 | 2018-04-12 11:15 | G | 2017-07-21 | battery storage additional (see Q664) | OT | WND BAT | 0 | 238.6 | 238.6 | Franklin | ME | 2020-10-31 | 2020-08-01 | 2018-04-12 | CMP Larrabee Road Station 345 kV | CNR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 667 | 2018-04-12 11:19 | G | 2017-07-21 | Solar | PV | SUN | 0 | 150 | 150 | Somerset | ME | 2020-10-31 | 2020-08-01 | 2018-04-12 | CMP Larrabee Road 345 kV | CNR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 668 | 2025-11-14 11:13 | ETU | 2017-07-24 | NE Clean Power Link - controllable HVDC Tie - CNI only | NA | N/A |  |  |  | Windsor | VT | 2027-12-31 | 2027-10-28 | 2021-02-09 | Coolidge Substation | NI | FALSE | FALSE |  |  | VT |  |  |  |  | Executed
| 669 | 2019-02-14 15:31 | G | 2017-07-25 | Offshore Wind | WT | WND | 288 | 288 | 288 | NA | MA | 2023-12-01 | 2023-09-01 | 2019-02-14 | 115 kV Brayton Point Station (Primary) or 115 kV Davisville Substation (alternative) | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
| 670 | 2024-07-26 12:56 | G | 2017-07-25 | Three Corners Solar | PV | SUN | 110 | 113.4 | 113.4 | Somerset | ME | 2024-07-27 | 2024-07-26 |  | CMP Albion Rd 115kV substation | CNR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed
| 671 | 2017-10-25 11:23 | G | 2017-07-26 | Solar | PV | SUN | 26 | 26 | 26 | Hartford | CT | 2019-12-01 | 2019-10-01 | 2017-10-25 | Interconnection to existing 115 kV transmission line running across the property between Eversources's Barbour Hill Substation and Endfield Substation. | CNR | FALSE | FALSE |  |  | CT
| 672 | 2019-10-22 08:38 | G | 2017-07-26 | Wind | WT | WND | 630 | 630 | 630 | Aroostook | ME | 2022-12-31 | 2022-11-30 | 2019-10-22 | NSTAR 345 kV K Street substation. | CNR | FALSE | FALSE |  | CD | BHE |  | In Progress |  |  |  | Under Study
| 673 | 2017-11-27 15:08 | G | 2017-07-26 | wind | WT | WND | 20 | 20 | 20 | Franklin | VT | 2020-12-31 | 2020-10-01 | 2017-11-27 | Green Mountain Power 34.5kV TL 137 Line between North St. Albans and Sheldon Springs Substations along State Route 105 in Swanton Vermont (approximately at pole 44) | CNR | FALSE | FALSE |  |  | VT | In Progress |  |  |  |  | Under Study
| 674 | 2021-05-20 11:24 | G | 2017-07-28 | Shaftsbury Solar | PV | SUN | 20 | 20 | 20 | Bennington | VT | 2028-01-01 | 2027-12-01 |  | GMP 46 kV between East Arlington and S. Shaftsbury Tap | NR | TRUE | TRUE | ISO-NE | NA | VT | Document Posted | Document Posted |  |  | Executed
| 675 | 2017-12-07 09:42 | G | 2017-07-28 | Solar | PV | SUN | 22 | 22 | 22 | New London | CT | 2019-12-31 | 2019-11-01 | 2017-09-27 | Eversource Bean Hill - Tunnel 115 kV | CNR | FALSE | FALSE |  |  | CT
| 676 | 2021-10-05 16:22 | G | 2017-08-03 | Claremont Solar | PV | SUN | 20 | 20 | 20 | Sullivan | NH | 2023-07-01 | 2023-06-01 | 2021-10-05 | GMP 46 kV line 107 between High Bridge and Windsor | NR | TRUE | TRUE | ISO-NE | NA | NH | Document Posted | Document Posted |  |  | Executed
| 677 | 2017-10-25 08:14 | G | 2017-08-03 | Solar | PV | SUN | 20 | 20 | 20 | Grafton | NH | 2019-07-01 | 2019-06-01 | 2017-10-24 | Eversource 34.5 kV Beebe River Substation | CNR | FALSE | FALSE |  |  | NH
| 678 | 2017-10-25 08:15 | G | 2017-08-03 | Solar | PV | SUN | 20 | 20 | 20 | Grafton | NH | 2019-07-01 | 2019-06-01 | 2017-10-24 | Eversource 34.5 kV Beebe River substation | CNR | FALSE | FALSE |  |  | NH
| 679 | 2021-01-26 14:56 | G | 2017-08-03 | Solar | PV | SUN | 20 | 20 | 20 | Hillsborough | NH | 2022-07-01 | 2022-06-01 | 2021-01-26 | Eversource NH 34.5 kV line 313, between South Peterborough and Monadnock substations. The Project will tap this line at about 0.1-0.5 miles south of the South Peterborough substation. | CNR | TRUE | TRUE | ISO-NE | NA | VT | Document Posted | Document Posted |  |  | In Progress
| 680 | 2021-05-20 11:23 | G | 2017-08-03 | Fair Haven Solar | PV | SUN | 20 | 20 | 20 | Rutland | VT | 2027-07-01 | 2027-06-01 |  | GMP 46 kV between Carver Falls and Fair Haven Tap | NR | TRUE | TRUE | ISO-NE | NA | VT |  | Document Posted |  |  | Executed
| 681 | 2021-01-26 14:57 | G | 2017-08-03 | Solar | PV | SUN | 20 | 20 | 20 | Grafton | NH | 2022-07-01 | 2022-06-01 | 2021-01-26 | Eversource 34.5 kV between Thornton and Beebe River | CNR | TRUE | TRUE | ISO-NE | NA | NH | Document Posted | Document Posted |  |  | In Progress
| 682 | 2018-07-25 08:29 | G | 2017-09-18 | solar with battery | OT | SUN BAT | 20.005 | 20 | 20 | Worcester | MA | 2020-12-01 | 2020-11-17 | 2018-07-24 | National Grid 13.8kV circuit (E.-Winchendon Substation) on Winchendon Road (near Depot Road), Winchendon, MA | CNR | FALSE | FALSE |  |  | CMA | Document Posted | Not Started
| 683 | 2019-05-21 14:37 | G | 2017-10-20 | Solar | PV | SUN | 20 | 20 | 20 | Grafton | NH | 2020-07-01 | 2020-06-01 | 2019-05-21 | 34.5 kV bus at Eversource NH Beebe Substation | CNR | FALSE | FALSE |  | PD | NH | Document Posted | Not Started |  |  |  | Under Study
| 684 | 2019-05-14 08:34 | G | 2017-10-20 | Solar | PV | SUN | 20 | 20 | 20 | Grafton | NH | 2020-07-01 | 2020-06-01 | 2019-05-10 | 34.5 kV bus at Eversource NH Beebe Substation | CNR | FALSE | FALSE |  | PD | NH | Document Posted |  |  |  |  | Under Study
| 685 | 2019-11-26 15:26 | G | 2017-10-20 | Solar | PV | SUN | 20 | 20 | 20 | Coos | NH | 2022-07-01 | 2022-06-01 | 2019-11-26 | 34.5 kV Express Feeder to Berlin substation | CNR | FALSE | FALSE |  |  | NH | Document Posted | In Progress |  |  |  | Under Study
| 686 | 2020-03-12 11:59 | G | 2017-10-24 | Solar | PV | SUN | 19.98 | 19.98 | 19.98 | Berkshire | MA | 2021-12-15 | 2021-09-15 | 2020-03-12 | National Grid 115kV line F132-2 | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | In Progress
| 687 | 2019-02-06 16:13 | G | 2017-11-21 | Energy Storage | OT | BAT | 150 | 150 | 150 | Barnstable | MA | 2021-12-31 | 2021-09-09 | 2019-02-06 | Falmouth 533 Eversource Energy 115KV | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted |  |  |  |  | Suspended
| 688 | 2020-06-09 08:15 | G | 2017-11-21 | Energy Storage | OT | BAT | 50 | 50 | 50 | Worcester | MA | 2021-12-31 | 2021-09-01 | 2018-02-09 | Little Rest Road 516 New England Power Co 115KV | CNR | FALSE | FALSE |  | NA | CMA
| 689 | 2020-02-16 13:11 | G | 2017-11-21 | Energy Storage | OT | BAT | 100 | 100 | 100 | Middlesex | MA | 2023-05-31 | 2023-02-01 | 2020-02-14 | Wakefield 115 kV Substation Bus (Bus #114433) | CNR | TRUE | FALSE | ISO-NE | PD | BOST | Document Posted | Document Posted |  |  | In Progress | Under Study
| 690 | 2018-02-09 13:51 | G | 2017-11-21 | Energy Storage | OT | BAT | 100 | 100 | 100 | Bristol | MA | 2021-12-31 | 2021-09-01 | 2018-02-09 | Wing Lane 624 Eversource Energy 115KV | CNR | FALSE | FALSE |  | PD | SEMA
| 691 | 2020-11-10 15:27 | G | 2017-11-20 | University Solar | PV | SUN | 31.34 | 31.34 | 31.34 | Kent | RI | 2020-09-15 | 2020-05-07 |  | GRID 3311 circuit in West Greenwich | NA | TRUE | TRUE | NGRID | NA | RI
| 692 | 2019-05-24 09:08 | G | 2017-11-20 | Solar | PV | SUN | 16.25 | 16.25 | 16.25 | Providence | RI | 2019-05-24 | 2019-05-22 |  | GRID 23 kV 2228 circuit/Grid 12.47 kV 21F1 circuit | NA | TRUE | TRUE | NGRID | NA | RI
| 693 | 2020-07-09 15:53 | G | 2017-11-20 | Alton Solar | PV | SUN | 13.875 | 13.875 | 13.875 | Washington | RI | 2020-04-30 | 2020-04-24 |  | Grid 85T3 circuit | NA | TRUE | TRUE | NGRID | NA | RI
| 694 | 2020-08-14 09:49 | G | 2017-11-20 | Solar | PV | SUN | 7 | 7 | 7 | Washington | RI | 2020-09-01 | 2020-05-01 | 2020-08-14 | GRID circuit 88F3 | NA | TRUE | TRUE | NGRID | NA | RI
| 695 | 2020-08-14 09:50 | G | 2017-11-20 | Solar | PV | SUN | 6.12 | 6.12 | 6.12 | Washington | RI | 2020-09-01 | 2020-05-01 | 2020-08-14 | GRID circuit 88F3 | NA | TRUE | TRUE | NGRID | NA | RI
| 696 | 2019-04-22 15:18 | G | 2017-11-27 | Johnston Landfill Wind | WT | WND | 21 | 21 | 21 | Providence | RI | 2018-12-20 | 2018-12-10 |  | GRID Johnston substation, Circuit 2227 | NA | TRUE | TRUE | NGRID | NA | RI
| 697 | 2020-03-06 11:37 | G | 2017-12-07 | Solar | PV | SUN | 5.97 | 5.97 | 5.97 | Worcester | MA | 2020-02-05 | 2020-02-03 |  | GRID 13.8 kV 612W1 Feeder (Pole 53) | NA | TRUE | TRUE | NGRID | PD | CMA
| 698 | 2020-03-06 11:37 | G | 2017-12-07 | Solar | PV | SUN | 8.04 | 8.04 | 8.04 | Worcester | MA | 2020-02-05 | 2020-02-03 |  | GRID 13.8 kV 612W3 Feeder (Pole 53) | NA | TRUE | TRUE | NGRID | PD | CMA
| 699 | 2019-02-14 11:40 | G | 2017-12-13 | Offshore Wind with battery addition | OT | WND BAT | 75 | 875 | 875 | NA | MA | 2023-05-31 | 2022-04-30 | 2019-02-14 | National Grid 345 kV Brayton Point Substation, Somerset, MA | CNR | FALSE | FALSE |  |  | RI | Document Posted
| 700 | 2022-09-16 09:41 | G | 2017-12-15 | Park City Offshore Wind | WT | WND | 791 | 791 | 791 | NA | MA | 2029-12-31 | 2029-05-01 |  | Eversource 345 kV West Barnstable Substation | NR | TRUE | TRUE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  |  | Executed
| 701 | 2019-02-14 15:32 | G | 2017-12-15 | Offshore Wind | WT | WND | 400 | 400 | 400 | NA | MA | 2023-12-01 | 2023-08-01 | 2019-02-14 | Brayton Point Substation in the Town of Somerset, Massachusetts or alternatively at Davisville Substation in the Town of North Kingstown, Rhode Island | CNR | FALSE | FALSE |  | PD | RI | In Progress |  |  |  |  | Under Study
| 702 | 2019-07-11 12:31 | G | 2018-01-24 | Solar | PV | SUN | 9.5 | 9.5 | 9.5 | Plymouth | MA | 2019-07-10 | 2019-06-28 |  | NSTAR Wareham Substation 23 kV bus | NA | TRUE | TRUE | NSTAR |  | SEMA
| 703 | 2020-01-10 13:39 | G | 2018-01-24 | Solar | PV | SUN | 6.75 | 6.75 | 6.75 | Plymouth | MA | 2019-04-23 | 2019-04-15 |  | NSTAR Crystal Spring Substation 13.2 kV bus | NA | TRUE | TRUE | NSTAR |  | SEMA | [5 empty] | Partially In Service
| 704 | 2020-10-08 14:09 | G | 2018-01-24 | Solar | PV | SUN | 1.904 | 1.904 | 1.904 | Bristol | MA | 2020-02-21 | 2020-02-21 |  | NSTAR Wing Lane Substation, #1 bank | NA | FALSE | FALSE |  |  | SEMA
| 705 | 2019-11-26 15:27 | G | 2018-01-26 | Combined Cycle CNR | CC | NG | 0 | 1030 | 1080 | Providence | RI | 2023-05-31 | 2023-02-01 | 2019-11-26 | Sherman Road 345kV substation | CNR | FALSE | FALSE |  |  | RI |  |  |  |  | In Progress
| 706 | 2020-02-04 15:34 | G | 2018-02-21 | Beacon Falls Energy Park CNR only | FC | FC | 0 | 62.9 | 62.9 | New Haven | CT | 2022-04-01 | 2022-02-01 | 2020-01-30 | Eversource, Beacon Falls Substation, 180 Cold Spring Rd, Beacon Falls, Junction of the 115 kV lines 1570-1 and 1319 | CNR | FALSE | FALSE |  |  | CT |  |  |  |  | Executed
| 707 | 2019-04-03 08:50 | G | 2018-02-21 | Solar | PV | SUN | 7.5 | 7.5 | 7.5 | Windham | CT | 2019-04-01 | 2019-03-31 | 2019-04-03 | Eversource 11F10 Feeder | NA | FALSE | FALSE |  |  | CT
| 708 | 2024-05-10 15:23 | G | 2018-02-21 | Solar | PV | SUN | 20 | 20 | 20 | Litchfield | CT | 2024-02-01 | 2023-12-01 | 2024-05-10 | Eversource Rocky river 12Y | NA | TRUE | TRUE | NU |  | CT
| 709 | 2020-10-08 14:08 | G | 2018-02-21 | Fuel Cell | FC | FC | 14.8 | 14.8 | 14.8 | Hartford | CT | 2021-01-01 | 2020-12-31 | 2020-10-01 | Eversource 12A Forestville | NA | FALSE | FALSE |  |  | CT
| 710 | 2025-03-03 15:32 | G | 2018-02-21 | Solar | PV | SUN | 19.8 | 19.8 | 19.8 | Litchfield | CT | 2025-02-24 | 2024-12-20 |  | Eversource 14R31 Feeder | NA | TRUE | TRUE | NU |  | CT
| 711 | 2024-04-10 15:46 | G | 2018-02-21 | Solar | PV | SUN | 9.99 | 9.99 | 9.99 | New London | CT | 2024-03-30 | 2024-02-29 |  | Eversource Shunock 32P | NA | TRUE | TRUE | NU |  | CT
| 712 | 2023-02-15 13:50 | G | 2018-02-21 | Solar | PV | SUN | 20 | 20 | 20 | Windham | CT | 2025-06-30 | 2025-06-15 | 2023-02-15 | Eversource Frybrook 13B | NA | TRUE | TRUE | NU |  | CT
| 713 | 2019-12-17 11:53 | G | 2018-02-21 | Solar | PV | SUN | 26.4 | 26.4 | 26.4 | Hartford | CT | 2019-12-10 | 2019-10-01 |  | Eversource North Simsbury | NA | TRUE | TRUE | NU |  | CT
| 714 | 2023-03-09 15:00 | G | 2018-02-21 | Solar | PV | SUN | 20 | 20 | 20 | Windham | CT | 2023-06-01 | 2023-03-01 | 2023-03-09 | Eversource Frybrook 13B | NA | TRUE | TRUE | NU |  | CT
| 715 | 2018-10-03 14:32 | G | 2018-02-21 | Fusion Solar Center | PV | SUN | 20 | 20 | 20 | New London | CT | 2018-04-18 | 2018-04-12 |  | Eversource Tunnel 12S | NA | TRUE | TRUE | NU |  | CT
| 716 | 2023-09-19 08:40 | G | 2018-02-21 | Solar | PV | SUN | 17.73 | 17.73 | 17.73 | New London | CT | 2023-08-18 | 2023-04-26 |  | Eversource Waterford 36F2 | NA | TRUE | TRUE | NU |  | CT
| 717 | 2022-05-26 09:12 | G | 2018-02-21 | Battery Storage | OT | BAT | 20 | 20 | 20 | Hartford | CT | 2022-02-01 | 2021-12-01 | 2022-05-26 | Eversource North Bloomfield 2A | NA | FALSE | FALSE |  |  | CT
| 718 | 2018-03-05 09:37 | G | 2018-02-21 | Solar | PV | SUN | 6 | 6 | 6 | New London | CT | 2019-04-02 | 2019-04-01 | 2018-03-02 | Eversource 13B25 Feeder | NA | FALSE | FALSE |  |  | CT
| 719 | 2018-04-25 12:43 | G | 2018-02-21 | Solar | PV | SUN | 19.92 | 19.92 | 19.92 | Hartford | CT | 2021-01-01 | 2020-12-31 | 2018-04-25 | Eversource Barber Hill 23J | NA | FALSE | FALSE |  |  | CT
| 720 | 2022-10-03 10:49 | G | 2018-02-21 | Solar | PV | SUN | 15 | 15 | 15 | New London | CT | 2022-10-01 | 2022-08-29 |  | Eversource Shunock 32P | NA | TRUE | TRUE | NU |  | CT
| 721 | 2018-04-25 12:43 | G | 2018-02-21 | Solar | PV | SUN | 26.4 | 26.4 | 26.4 | Hartford | CT | 2020-01-01 | 2019-12-31 | 2018-04-25 | Eversource North Simsbury | NA | FALSE | FALSE |  |  | CT
| 722 | 2018-04-25 12:44 | G | 2018-02-21 | Solar | PV | SUN | 24.6 | 24.6 | 24.6 | Hartford | CT | 2020-01-01 | 2019-12-31 | 2018-04-25 | Eversource North Simsbury | NA | FALSE | FALSE |  |  | CT
| 723 | 2019-05-06 12:43 | G | 2018-03-01 | Battery Storage | OT | BAT | 142.8 | 142.8 | 142.8 | Barnstable | MA | 2021-05-31 | 2021-04-30 | 2019-03-27 | Primary POI: Eversource 115 kV W. Barnstable Alternative POI 1: Eversource 115 kV Barnstable Alternative POI 2: New Eversource W. Barnstable – Bourne 115 kV line (RSP #1725) tapped at 51% (7.2 miles) from W. Barnstable substation | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started
| 724 | 2023-08-31 17:03 | G | 2018-03-07 | NTE Connecticut | CC | DFO NG | 672 | 671 | 692 | Windham | CT | 2025-02-28 | 2024-11-15 | 2023-07-12 | Lake Road 345 kV | CNR | TRUE | TRUE | ISO-NE |  | CT |  | In Progress |  |  | Executed
| 725 | 2021-01-21 12:10 | G | 2018-03-20 | Wallingford Solar | PV | SUN | 14.97 | 14.97 | 14.97 | New Haven | CT | 2020-12-18 | 2020-10-30 |  | WED Wallingford 13.8 KV substation | NA | TRUE | TRUE | ISO-NE |  | SWCT
| 726 | 2025-05-19 13:29 | G | 2018-03-21 | Cranberry Point Energy Storage | OT | BAT | 150 | 150 | 150 | Plymouth | MA | 2025-05-16 | 2025-03-14 |  | Carver 115 kV Primary POI – Loop-in station with 3-breaker ring bus interconnecting to line 127 located just south of Carver substation Alternate POI – Expand the existing station to add a 4th bay with 2 breakers to interconnect the project. | CNR | TRUE | TRUE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  |  | Executed
| 727 | 2025-01-13 17:41 | G | 2018-04-10 | Chariot Solar | PV | SUN | 49.5 | 49.5 | 49.5 | Cheshire | NH | 2024-12-15 | 2024-11-15 | 2025-01-13 | NGrid 115 kV Vernon Road tap to Vernon Road Substation, 2.5 mi from Vernon Road Substation | NR | TRUE | TRUE | ISO-NE | PD | VT |  | Document Posted |  |  | Executed
| 728 | 2019-06-28 16:52 | G | 2018-04-02 | Vernon Station Incremental Capacity Increase | HD | WAT | 2.9 | 34.9 | 34.9 | Windham | VT | 2019-03-31 | 2019-03-31 |  | (Same as Existing POI Vernon Substation No.13 69 KV Bus) Street Address: 152 Governor Hunt Road | CNR | FALSE | FALSE |  |  | VT |  |  |  |  | Executed | In Service
| 729 | 2020-12-01 14:22 | G | 2018-04-12 | Wind | WT | WND | 103.5 | 103.5 | 103.5 | Aroostook | ME | 2022-11-20 | 2022-09-03 | 2020-12-01 | PITTSFIELD 345KV on line 3023 | CNR | FALSE | FALSE |  | PD | BHE
| 730 | 2020-12-01 14:22 | G | 2018-04-12 | Wind | WT | WND | 103.5 | 103.5 | 103.5 | Aroostook | ME | 2022-11-20 | 2022-09-03 | 2020-12-01 | PITTSFIELD 345KV on line 3023 | CNR | FALSE | FALSE |  | PD | BHE
| 731 | 2020-12-01 14:23 | G | 2018-04-12 | Wind | WT | WND | 103.5 | 103.5 | 103.5 | Aroostook | ME | 2022-11-20 | 2022-09-03 | 2020-12-01 | PITTSFIELD 345KV on line 3023 | CNR | FALSE | FALSE |  | PD | BHE
| 732 | 2020-12-01 14:24 | G | 2018-04-12 | Wind | WT | WND | 103.5 | 103.5 | 103.5 | Aroostook | ME | 2022-11-20 | 2022-09-03 | 2020-12-01 | PITTSFIELD 345KV on line 3023 | CNR | FALSE | FALSE |  | PD | BHE
| 733 | 2020-12-01 14:24 | G | 2018-04-12 | Wind | WT | WND | 103.5 | 103.5 | 103.5 | Aroostook | ME | 2022-11-20 | 2022-09-03 | 2020-12-01 | PITTSFIELD 345KV on line 3023 | CNR | FALSE | FALSE |  | PD | BHE
| 734 | 2019-02-07 18:44 | G | 2018-04-12 | Wind | WT | WND | 600.6 | 600.5999 | 600.5999 | Aroostook | ME | 2021-12-01 | 2021-11-01 | 2019-02-07 | Primary: Orrington Substations 345kV with two alternatives: Keene Rd. Substation 345kV and the Orrington-Albion Rd 345kV line | NR | FALSE | FALSE |  | PD | BHE
| 735 | 2019-02-07 18:44 | G | 2018-04-12 | Wind | WT | WND | 600.6 | 600.599 | 600.599 | Aroostook | ME | 2021-12-01 | 2021-11-01 | 2019-02-07 | Primary: Orrington Substations 345kV with two alternatives: Keene Rd. Substation 345kV and the Orrington-Albion Rd 345kV line | NR | FALSE | FALSE |  | PD | BHE
| 736 | 2019-02-07 18:45 | ETU | 2018-04-12 | Internal noncontrollable ETU to Pittsfield ME | NA | N/A | 550 |  |  | Somerset | ME | 2021-12-31 | 2021-11-30 | 2019-02-07 | CMP Section 3023 345 kV | N/A | FALSE | FALSE |  | PD | ME
| 737 | 2019-02-07 18:45 | ETU | 2018-04-12 | Internal noncontrollable ETU from NMISA to Pittsfield ME | NA | N/A | 1200 |  |  | Somerset and Penobscot | ME | 2021-12-31 | 2021-11-30 | 2019-02-07 | Emera Keene Rd substation and CMP Section 3023 345 kV Line | N/A | FALSE | FALSE |  | PD | ME
| 738 | 2020-12-01 13:09 | ETU | 2018-04-12 | Internal noncontrollable ETU - interface upgrade | NA | N/A | 400 |  |  | Cumberland | ME | 2019-11-30 | 2019-10-31 | 2020-11-30 | N/A | N/A | FALSE | FALSE |  | PD | ME
| 739 | 2019-01-17 09:10 | G | 2018-04-12 | Wind | WT | WND | 89.7 | 89.7 | 89.7 | Somerset | ME | 2020-01-30 | 2020-01-15 | 2019-01-16 | CMP Section 3023 345kV line (via Johnson Mountain Substation) | CNR | FALSE | FALSE |  | PD | ME
| 740 | 2020-12-01 13:12 | ETU | 2018-04-12 | Internal noncontrollable ETU to Larabee Road | NA | N/A | 460 |  |  | Lewiston | ME | 2021-12-31 | 2021-11-30 | 2020-11-29 | Larrabee Road 345 kV Substation in Lewiston, Androscoggin county Maine 04240 | N/A | FALSE | FALSE |  | PD | ME
| 741 | 2020-12-01 13:10 | ETU | 2018-04-12 | Internal noncontrollable ETU to Larabee Road - increase (see Q740) | NA | N/A | 200 |  |  | Lewiston | ME | 2021-12-31 | 2021-11-30 | 2020-11-29 | Larrabee Road 345 kV Substation in Lewiston, Androscoggin county Maine 04240. | N/A | FALSE | FALSE |  | PD | ME
| 742 | 2020-12-01 13:10 | ETU | 2018-04-12 | Internal noncontrollable ETU to Larabee Road - increase (see Q740 and Q741) | NA | N/A | 540 |  |  | Lewiston | ME | 2021-12-31 | 2021-11-30 | 2020-11-29 | Larrabee Road 345 kV Substation in Lewiston, Androscoggin county Maine 04240. | N/A | FALSE | FALSE |  | PD | ME
| 743 | 2019-02-07 18:46 | ETU | 2018-04-12 | noncontrollable ETU from Quebec to ME | NA | N/A | 450 |  |  | Franklin | ME | 2022-12-01 | 2022-09-01 | 2019-02-07 | CMP/Avangrid 345 kV Larabee Road | N/A | FALSE | FALSE |  | PD | ME
| 744 | 2019-02-07 18:47 | G | 2018-04-12 | Wind | WT | WND | 150 | 150 | 150 | Franklin | ME | 2022-12-01 | 2022-09-01 | 2019-02-07 | Approximate location of the proposed Point of Interconnection is the CMP Avangrid Larrabee Road 345 kV Substation | CNR | FALSE | FALSE |  | PD | ME
| 745 | 2019-08-28 08:09 | G | 2018-04-12 | Wind | WT | WND | 241.2 | 241.2 | 241.2 | Franklin | ME | 2021-10-29 | 2021-08-01 | 2019-08-27 | CMP Larrabee Road Station 345 kV | CNR | FALSE | FALSE |  | PD | ME
| 746 | 2019-08-28 08:13 | G | 2018-04-12 | Wind | WT | WND | 214.3 | 214.3 | 214.3 | Franklin | ME | 2021-12-15 | 2021-10-29 | 2019-08-27 | CMP Larrabee Road Station 345 kV | CNR | FALSE | FALSE |  | PD | ME
| 747 | 2019-08-28 08:14 | G | 2018-04-12 | Battery storage addition (see Q745) | OT | WND BAT | 24.4 | 265.6 | 265.6 | Franklin | ME | 2021-10-31 | 2021-08-01 | 2019-08-27 | CMP Larrabee Road Station,345 kV | CNR | FALSE | FALSE |  | PD | ME
| 748 | 2019-08-28 08:15 | G | 2018-04-12 | Battery storage addition (see Q746) | OT | WND BAT | 24.3 | 238.6 | 238.6 | Franklin | ME | 2021-10-31 | 2021-08-01 | 2019-08-27 | CMP Larrabee Road Station 345 kV | CNR | FALSE | FALSE |  | PD | ME
| 749 | 2019-08-28 08:16 | G | 2018-04-12 | Solar | PV | SUN | 150 | 150 | 150 | Franklin | ME | 2021-10-31 | 2021-08-01 | 2019-08-27 | CMP Larrabee Road 345 kV | CNR | FALSE | FALSE |  | PD | ME
| 750 | 2019-08-06 09:27 | G | 2018-04-12 | Solar | PV | SUN | 20 | 20 | 20 | Franklin | VT | 2021-11-01 | 2021-10-15 | 2019-08-06 | VEC's Highgate - Enosburg 46 kV line, 700 feet from Highgate | CNR | FALSE | FALSE |  |  | VT | Document Posted | Not Started |  |  |  | Under Study
| 751 | 2020-08-12 16:42 | G | 2018-04-12 | Solar | PV | SUN | 20 | 20 | 20 | Orange | VT | 2021-11-01 | 2021-10-15 | 2020-08-12 | GMP's Randolph Center substation 46 kV | CNR | TRUE | TRUE | ISO-NE |  | VT |  | Document Posted |  |  | In Progress | Under Study
| 752 | 2019-05-14 08:10 | G | 2018-04-19 | Energy Storage | OT | BAT | 102.85 | 102.85 | 102.85 | Bristol | MA | 2022-05-02 | 2022-03-02 | 2019-05-13 | Eversource 115kV Cross Road Substation [both buses at Cross Road Substation (bus/line 111 = primary; bus/line 109 = alternate)] | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted |  |  |  |  | Under Study
| 753 | 2019-08-06 09:28 | G | 2018-04-20 | Solar | PV | SUN | 20 | 20 | 20 | Franklin | VT | 2021-11-01 | 2021-10-15 | 2019-08-06 | VEC Sheldon Substation - 46 kV | CNR | FALSE | FALSE |  | PD | VT | In Progress |  |  |  |  | Under Study
| 754 | 2021-11-01 08:14 | G | 2018-04-25 | Solar | PV | SUN | 30 | 30 | 30 | Cheshire | NH | 2024-07-30 | 2024-06-30 | 2021-10-31 | Primary: NGRID 115 KV Line I-135 between Fitzwilliam Sub and Flagg Pond Sub Alternate 1: NGRID 115 KV Line J-136 between Bellows Falls Sub and Flagg Pond Sub Alternate 2: Eversource 115 KV Bus at Monadnock Substation via short 115 KV gentie line from project site | CNR | TRUE | TRUE | ISO-NE | PD | NH | Document Posted | Document Posted |  |  | In Progress | Under Study
| 755 | 2018-12-27 11:54 | G | 2018-04-25 | Bingham Wind CNR Only | WT | WND | 0 | 184.8 | 184.8 | Somerset | ME | 2016-12-13 | 2016-08-15 |  | CMP 115kV Guilford Substation | CNR | FALSE | FALSE |  |  | ME |  |  |  |  | Executed | In Service
| 756 | 2020-08-12 16:43 | G | 2018-04-26 | Solar | PV | SUN | 20 | 20 | 20 | Kennebec | ME | 2021-11-01 | 2021-10-15 | 2020-08-12 | CMP Albion to Detroit 115 kV line approximately 2.5 miles from Albion. | CNR | FALSE | FALSE |  | PD | ME | Document Posted | In Progress |  |  |  | Under Study
| 757 | 2020-08-12 16:44 | G | 2018-04-26 | Solar | PV | SUN | 20 | 20 | 20 | Somerset | ME | 2021-11-01 | 2021-10-15 | 2020-08-12 | Approximately at 44°42'47.78"N, 69°39'15.37"W at proposed interconnection substation to tap CMP Section 83 line and SAPI Somerset generator tap line. Substation to have short gen tie line to project site located between Kendall Annex Road and Middle Road in Fairfield, Maine | CNR | FALSE | FALSE |  | PD | ME | Document Posted | In Progress |  |  |  | Under Study
| 758 | 2023-05-17 16:58 | G | 2018-04-26 | Ocean State Power uprate | CC | DFO NG | 73.204 | 631.2 | 652.342 | Providence | RI | 2025-11-30 | 2025-11-30 |  | NGRID 345kV Sherman Road (existing OSP I and II switchyard) | CNR | TRUE | TRUE | ISO-NE | PD | RI | Document Posted | Document Posted | Document Posted |  | Executed
| 759 | 2022-08-12 14:12 | G | 2018-04-26 | Wallingford GT Uprate | GT | NG | 0 | 350 | 350 | New Haven | CT | 2022-05-31 | 2022-05-31 |  | WED 115kV Lines 1305 and 1406 | CNR | FALSE | FALSE |  |  | SWCT |  |  |  |  | Executed | In Service
| 760 | 2025-06-17 13:15 | G | 2018-04-26 | Downeast Wind | WT | WND | 126 | 126 | 126 | Washington | ME | 2025-05-29 | 2024-12-02 |  | Primary POI: Emera Maine 115 line 52 near Epping switching station Alternate POI: Epping station | NR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  | Document Posted | Executed | In Service
| 761 | 2020-03-26 09:16 | G | 2018-04-27 | Storage | OT | BAT | 150 | 150 | 150 | Middlesex | MA | 2021-05-31 | 2021-04-30 | 2020-03-26 | National Grid 115 kV line M139 | CNR | FALSE | FALSE |  | PD | BOST | Document Posted | In Progress |  |  |  | Under Study
| 762 | 2018-05-21 11:13 | G | 2018-04-27 | Solar | PV | SUN | 22.5 | 22.5 | 22.5 | Rutland | VT | 2020-08-01 | 2020-05-15 | 2018-05-18 | POI tap of GMP Florence - S. Middlebury Jct. 46 kV line, approx. 4 miles from Florence. Site is 13 acres on Carver Street/Syndicate Road, Brandon, VT 05733 | CNR | FALSE | FALSE |  | PD | VT
| 763 | 2022-06-22 09:50 | G | 2018-04-27 | Davenport Solar | PV | SUN | 15 | 15 | 15 | Rutland | VT | 2021-12-01 | 2021-11-01 | 2022-06-14 | Florence - S. Middlebury Jct. 46 kV line, approx. 4 miles from Florence | NR | TRUE | TRUE | ISO-NE |  | VT |  | Document Posted |  |  | Executed | Under Study
| 764 | 2019-09-30 08:51 | G | 2018-05-09 | Solar | PV | SUN | 10 | 10 | 10 | Providence | RI | 2019-09-30 | 2019-08-30 |  | GRID 2228 circuit 23 kV feeder (Hope Rd, Cranston) | NA | TRUE | TRUE | NGRID |  | RI
| 765 | 2021-01-25 17:25 | G | 2018-05-09 | Solar | PV | SUN | 10 | 10 | 10 | Providence | RI | 2021-07-15 | 2021-06-30 | 2021-01-25 | GRID 228 circuit 23 kV feeder (7 Mile Rd, Scituate) | NA | TRUE | TRUE | NGRID |  | RI
| 766 | 2025-06-16 12:31 | G | 2018-05-22 | Solar | PV | SUN | 5.2 | 5.2 | 5.2 | Washington | RI | 2025-03-28 | 2025-03-21 | 2025-06-13 | GRID 68F1 feeder (Richmond, RI) | NA | TRUE | TRUE | NGRID |  | RI
| 767 | 2019-06-03 12:26 | G | 2018-06-13 | Solar | PV | SUN | 20 | 20 | 20 | Fairfield | ME | 2020-11-30 | 2020-09-14 | 2019-06-03 | Tap point on 34.5kV CMP Section 9 approximately 2.2mi west of Shawmut Hydro S/S in the direction of Skowhegan South Side S/S. | CNR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
| 768 | 2019-09-30 10:08 | G | 2018-06-13 | Solar with battery addition | OT | SUN BAT | 1.32 | 6.138 | 6.138 | Hampshire | MA | 2019-09-03 | 2019-06-01 |  | Eversource Tillson Substation | NA | TRUE | TRUE |  |  | WMA
| 769 | 2018-08-21 15:59 | G | 2018-06-13 | Wind | WT | WND | 7.5 | 7.5 | 7.5 | Berkshire | MA | 2020-03-01 | 2020-02-01 | 2018-08-21 | Eversource 23 kV Feeder Berkshire Substation | NA | FALSE | FALSE |  |  | WMA
| 770 | 2018-07-27 12:08 | G | 2018-06-20 | Solar | PV | SUN | 10 | 10 | 10 | Rockingham | NH | 2019-06-01 | 2019-05-31 | 2018-07-27 | Eversource 34.5 kV feeder (3184 circuit), Mammoth Rd substation | NA | FALSE | FALSE |  |  | NH
| 771 | 2018-08-28 08:49 | G | 2018-07-26 | Battery Storage | OT | BAT | 19.01 | 19.01 | 19.01 | Penobscot | ME | 2019-06-01 | 2019-05-01 | 2018-08-28 | Lincoln (Maine) - 46 kv - bus #103039 | CNR | FALSE | FALSE |  | PD | BHE
| 772 | 2019-06-06 11:29 | G | 2018-08-07 | Combined Reciprocating, Solar and Battery | OT | NG SUN BAT | 7.81 | 7.81 | 7.81 | Middlesex | MA | 2019-06-03 | 2019-05-01 |  | GRID Norman Street D substation (8W1) | NA | TRUE | TRUE | NGRID |  | BOST
| 773 | 2020-06-16 11:53 | G | 2018-08-13 | Solar | PV | SUN | 4.95 | 4.95 | 4.95 | Plymouth | MA | 2019-12-18 | 2019-12-01 |  | GRID Circuit 912W75 River Street | NA | TRUE | TRUE | NGRID |  | SEMA
| 774 | 2025-06-16 12:32 | G | 2018-08-13 | Solar | PV | SUN | 8 | 8 | 8 | Washington | RI | 2021-07-15 | 2021-07-01 | 2025-06-13 | GRID 85T1 Woodville Road | NA | TRUE | TRUE | NGRID |  | SEMA
| 775 | 2020-08-21 09:46 | G | 2018-08-20 | Solar | PV | SUN | 20 | 20 | 20 | Kennebec | ME | 2021-11-01 | 2021-10-15 | 2020-08-21 | CMP Albion to Detroit 115 kV line approximately 2.5 miles from Albion | NR | FALSE | FALSE |  | PD | ME | Not Required | In Progress |  |  |  | Under Study
| 776 | 2018-10-22 14:51 | G | 2018-08-29 | Solar | PV | SUN | 10 | 10 | 10 | North Kingstown | RI | 2019-10-01 | 2019-10-01 | 2018-10-17 | GRID 84T3 feeder to Davisville Substation | NA | FALSE | FALSE |  |  | SEMA
| 777 | 2019-05-03 07:54 | G | 2018-08-29 | Solar | PV | SUN | 30 | 40 | 40 | North Kingstown | RI | 2020-08-01 | 2020-08-01 | 2019-10-17 | GRID L-190 line | NA | FALSE | FALSE |  | PD | SEMA
| 778 | 2021-12-23 11:04 | G | 2018-08-31 | Kearsarge Solar with battery | OT | SUN BAT | 5.4 | 5.4 | 5.4 | Norfolk | MA | 2021-12-21 | 2021-12-06 |  | GRID circuit 335W1, Pole 11 on Williams Way, Bellingham | NA | TRUE | TRUE | NGRID | PD | SEMA
| 779 | 2021-09-17 16:23 | G | 2018-09-04 | Solar with Battery | OT | SUN BAT | 9.98 | 9.98 | 9.98 | Worcester | MA | 2021-08-03 | 2021-03-31 |  | GRID Circuit 320W1, Pole 9, Puddon Street, Northbridge | NA | TRUE | TRUE | NGRID | PD | WMA
| 780 | 2025-06-16 12:35 | G | 2018-09-11 | Combined Reciprocating, Solar and Battery modification | OT | NG SUN BAT | 0 | 7.81 | 7.81 | Middlesex | MA | 2022-05-31 | 2022-05-01 | 2025-06-13 | GRID Hendersonville 593 substation (593W1 and 593W4) | NA | TRUE | TRUE | NGRID | PD | BOST
| 781 | 2022-04-27 13:33 | G | 2018-09-13 | Revoultion Offshore wind | WT | WND | 704 | 704 | 704 | NA | RI | 2026-11-05 | 2026-05-08 |  | NG 115 kV Davisville substation, Washington County | NR | TRUE | TRUE | ISO-NE | PD | RI | Document Posted | Document Posted |  |  | Executed
| 782 | 2019-09-27 11:00 | G | 2018-09-13 | Offshore Wind | WT | WND | 352 | 352 | 352 | NA | RI | 2024-12-01 | 2024-04-30 | 2019-09-27 | NG 115 kV Kent County substation, RI or alternatively NG 345 kV Kent County Substation, RI | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
| 783 | 2019-04-17 11:23 | ETU | 2018-09-18 | controllable 150 kV HVDC Tie - Import Only | NA | N/A | 400 |  |  | Addison | VT | 2023-12-31 | 2023-10-31 | 2019-04-17 | a new ~60-mile, 400 MW, ±150 kV, VSC-controlled HVDC transmission line originating from New York Power Authority’s (NYPA) Plattsburgh 230 kV Substation in Plattsburgh, NY and terminating at VELCO’s 345 kV Substation at New Haven, Vermont. The project will deliver a maximum of 400 MW from New York to New England. VGL is an elective transmission upgrade project that will begin in Clinton County, NY, and terminate in Addison County, VT. | CNI | FALSE | FALSE |  | PD | VT |  | In Progress
| 784 | 2020-04-13 12:51 | G | 2018-09-18 | CPV Towantic incremental | CC | DFO NG | 45 | 845.5 | 876.5 | New Haven | CT | 2020-03-01 | 2020-03-01 |  | Eversource 115 KV lines 1575, 1585 and 1990 | CNR | TRUE | TRUE | ISO-NE |  | SWCT |  | Document Posted |  |  | Executed | In Service
| 785 | 2024-11-27 14:36 | G | 2018-09-26 | Tilton Heights Energy Center | PV | SUN | 19.9 | 19.9 | 19.9 | Belknap | NH | 2025-09-25 | 2025-07-31 | 2024-11-27 | POI at Eversource 34.5 kV circuit #3216 (sourced from Webster SS) near pole #3798/1. | NR | TRUE | TRUE | ISO-NE | PD | NH |  | Document Posted |  |  | Executed
| 786 | 2024-11-27 14:36 | G | 2018-09-26 | Keay Brook Energy Solar | PV | SUN | 19.9 | 19.9 | 19.9 | York | ME | 2025-09-25 | 2025-07-31 | 2024-11-27 | Tap of CMP 34.5 kV Section 185 A TA approximately 3.5 miles north of Lebanon substation | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 787 | 2024-11-27 14:37 | G | 2018-09-26 | Black Hill Point Energy Center | PV | SUN | 19.9 | 19.9 | 19.9 | Windham | CT | 2025-09-25 | 2025-07-31 | 2024-11-27 | New 3 breaker ring bus switching station on Eversource (CL&P) Killingly to Tunnel 115 kV line L-1607. | NR | TRUE | TRUE | ISO-NE | PD | CT |  | Document Posted |  |  | Executed | Under Study
| 788 | 2022-09-09 14:06 | G | 2018-09-28 | Solar | PV | SUN | 19.9 | 19.9 | 19.9 | New London | CT | 2023-12-31 | 2023-07-31 | 2022-09-09 | Primary POI - Eversource Montville Plant 69 kV switchyard via new breaker position. Alternate POI - New 34.5 kV breaker position at Mohegan Tribal Utility Authority (MTUA) Fort Hill Substation. | NR | TRUE | TRUE | ISO-NE |  | CT | Document Posted | Document Posted |  |  | In Progress
| 789 | 2025-06-16 12:35 | G | 2018-09-28 | CHP | GT | NG | 6.268 | 6.268 | 9.091 | Newport | RI | 2021-06-30 | 2021-06-01 | 2025-06-13 | GRID 13.8 kV supplied by 69/13.8 KV Navy Substion in RI | NA | TRUE | TRUE | NGRID | PD | RI
| 790 | 2019-02-13 09:10 | G | 2018-10-11 | Solar | PV | SUN | 15 | 15 | 15 | Coos | NH | 2020-07-01 | 2020-07-01 | 2019-02-13 | Eversource, 115kV, Line X178-3, POI ~2.2 miles from Whitefield Substation, POI Lat/Long = 44.368066, -71.640429 | CNR | FALSE | FALSE |  | PD | NH | Not Started
| 791 | 2020-03-06 08:37 | G | 2018-10-19 | Offshore Wind | WT | WND | 805 | 805 | 805 | NA | CT | 2023-05-31 | 2023-04-01 | 2020-03-05 | Eversource (CL&P) 345kV Montville, alternatively Eversource (CL&P) 345kV Millstone | CNR | FALSE | FALSE |  | PD | CT | Document Posted | ISA Not Executed |  |  |  | Under Study
| 792 | 2022-01-13 14:44 | G | 2018-10-19 | Offshore Wind | WT | WND | 805 | 805 | 805 | NA | CT | 2023-05-31 | 2023-04-01 | 2022-01-13 | Eversource (CL&P) 345kV Montville, alternatively Eversource (CL&P) 345kV Millstone | CNR | TRUE | TRUE | ISO-NE | PD | CT | Document Posted | Document Posted |  |  | Not Started
| 793 | 2025-06-16 12:36 | G | 2018-10-26 | Solar (QF) | PV | SUN | 40 | 40 | 40 | North Kingstown | RI | 2025-04-01 | 2023-09-29 | 2025-06-13 | GRID L-190 line via new station | NA | TRUE | TRUE | NGRID | PD | RI
| 794 | 2025-06-16 12:53 | G | 2018-10-26 | Solar (QF) | PV | SUN | 10 | 10 | 10 | North Kingstown | RI | 2025-04-01 | 2024-12-31 | 2025-06-13 | GRID L-190 line via new station | NA | TRUE | TRUE | NGRID | PD | RI
| 795 | 2022-06-15 15:53 | G | 2018-10-26 | Solar (QF) | PV | SUN | 56.496 | 56.496 | 56.496 | North Kingstown | RI | 2021-06-01 | 2021-05-15 | 2022-04-04 | GRID L-190 line via new station | NA | TRUE | TRUE | NGRID | PD | RI
| 796 | 2018-12-06 15:35 | G | 2018-10-26 | Solar | PV | SUN | 50 | 50 | 50 | Hartford | CT | 2022-11-01 | 2022-10-15 | 2018-12-06 | Tap of existing 115 kV Connecticut Light & Power Company line between Barbour Hill and Windsor Locks | CNR | FALSE | FALSE |  |  | CT
| 797 | 2025-06-16 12:53 | G | 2018-11-05 | Solar | PV | SUN | 8.125 | 8.125 | 8.125 | Worcester | MA | 2020-12-30 | 2020-12-01 | 2025-06-13 | GRID P7 and P8 McCormick Rd/Meadow St 552L5 (Spencer, MA) | NA | TRUE | TRUE | NGRID | PD | WMA
| 798 | 2019-08-02 13:42 | G | 2018-11-08 | Solar | PV | SUN | 15 | 15 | 15 | Androscoggin | ME | 2021-11-01 | 2021-10-01 | 2019-08-02 | Interconnecting to existing CMP 34.5 kV Sabattus substation | CNR | FALSE | FALSE |  | PD | ME | In Progress |  |  |  |  | Under Study
| 799 | 2021-03-15 17:58 | G | 2018-11-16 | Solar | PV | SUN | 10 | 10 | 10 | Sullivan | NH | 2021-11-01 | 2021-10-01 | 2021-03-05 | Primary POI - PSNH 46 kV River Road substation; Alternate POI - GMP 46 kV Line 102 | CNR | TRUE | FALSE | ISO-NE | PD | NH | Document Posted | Document Posted |  |  |  | Under Study
| 800 | 2019-02-14 09:54 | G | 2018-11-30 | Solar | PV | SUN | 19.8 | 19.8 | 19.8 | Somerset | ME | 2022-04-01 | 2022-03-01 | 2019-02-13 | CMP 34.5 kV express feeder at project site (Approx. 2.12 mile feeder originating from CMP North Anson substation) | NR | FALSE | FALSE |  | PD | ME
| 801 | 2019-02-15 11:44 | G | 2018-11-30 | Solar | PV | SUN | 14 | 14 | 14 | Cheshire | NH | 2022-04-01 | 2022-03-01 | 2019-02-15 | Eversource 34.5 kV distribution circuit #3178, near pole 2/97 on Brattleboro Rd (Rt 119) in Hinsdale, NH Chestnut Hill SS, approx. 3.8 miles away) | NR | FALSE | FALSE |  | PD | NH
| 802 | 2019-08-06 09:41 | G | 2018-12-04 | Generator Increase | ST | MSW | 2.08 | 15.6 | 15.6 | Hartford | CT | 2019-09-03 | 2019-09-03 | 2019-08-06 | Connecticut Light and Powers 13.8 kv Forestville 12A Substation | CNR | TRUE | FALSE | ISO-NE |  | CT |  | In Progress
| 803 | 2021-08-04 16:45 | G | 2018-12-06 | Solar | PV | SUN | 50 | 50 | 50 | York | ME | 2021-07-01 | 2021-06-01 | 2021-08-04 | Tap CMP existing 115 kV line section 225 approximately 2.25 miles from Sanford 115 kV Substation | CNR | TRUE | FALSE | ISO-NE | PD | ME |  | Document Posted |  |  | In Progress
| 804 | 2019-02-04 15:37 | G | 2018-12-10 | Solar | PV | SUN | 5 | 5 | 5 | Windham | CT | 2020-07-01 | 2020-07-01 | 2019-02-04 | Eversource, 23kV, Line 14MX29, POI is ~3.6 miles from Tracy Substation, POI Lat/Long = 41.907528, -71.914968 | CNR | FALSE | FALSE |  |  | CT | Not Started
| 805 | 2025-06-16 12:54 | G | 2018-12-10 | Solar | PV | SUN | 10.99 | 10.99 | 10.99 | Middletown | RI | 2025-02-26 | 2025-02-05 | 2025-06-13 | GRID Jepson 37K33 | NA | TRUE | TRUE | NGRID | PD | RI
| 806 | 2024-10-02 16:31 | G | 2018-12-12 | Offshore Wind | WT | WND | 827 | 827 | 827 | NA | MA | 2032-12-31 | 2032-05-01 |  | Eversource 345 kV West Barnstable Substation | CNR | TRUE | TRUE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  | In Progress |  | Under Study
| 807 | 2022-07-13 10:46 | G | 2018-12-13 | FPS Panton Solar | PV | SUN | 50 | 50 | 50 | Addison | VT | 2027-12-01 | 2027-11-01 |  | Vergennes 115 kV Substation | NR | TRUE | TRUE | ISO-NE | PD | VT |  | Document Posted |  |  | Executed
| 808 | 2025-06-16 12:54 | G | 2018-12-14 | Barre substation - NG Western MA Area Cluster Study | PV | SUN | 12.398 | 12.398 | 12.398 | Worcester | MA | 2022-12-30 | 2021-04-20 | 2025-06-13 | NG Barre substation | NA | TRUE | TRUE | NGRID | PD | WMA
| 809 | 2021-10-27 10:45 | G | 2018-12-14 | Belchertown Substation - NG Western MA Area Cluster Study | PV | SUN | 8 | 8 | 8 | Hampden | MA | 2021-08-08 | 2021-06-21 |  | NG Belchertown Substation | NA | TRUE | TRUE | NGRID | PD | WMA
| 810 | 2021-10-27 10:46 | G | 2018-12-14 | Chestnut Hill 702 Substation - NG Western MA Area Cluster Study | PV | SUN | 3.276 | 3.276 | 3.276 | Worcester | MA | 2020-03-05 | 2020-03-05 |  | NG Chestnut Hill 702 Substation | NA | TRUE | TRUE | NGRID | PD | WMA
| 811 | 2021-10-27 10:48 | G | 2018-12-14 | Crystal Lake Substation - NG Western MA Area Cluster Study | PV | SUN | 24.73 | 24.73 | 24.73 | Worcester | MA | 2020-12-31 | 2019-04-19 |  | NG Crystal Lake Substation | NA | TRUE | TRUE | NGRID | PD | WMA
| 812 | 2025-06-16 12:54 | G | 2018-12-14 | E. Westminster Substation - NG Western MA Area Cluster Study | PV | SUN | 7.98 | 7.98 | 7.98 | Worcester | MA | 2022-08-01 | 2021-03-28 | 2025-06-13 | NG E. Westminster Substation | NA | TRUE | TRUE | NGRID | PD | WMA
| 813 | 2025-06-16 12:55 | G | 2018-12-14 | E. Winchendon Substation - NG Western MA Area Cluster Study | PV | SUN | 3.9 | 3.9 | 3.9 | Worcester | MA | 2022-06-26 | 2022-06-26 | 2025-06-13 | NG E. Winchendon Substation | NA | TRUE | TRUE | NGRID | PD | WMA
| 814 | 2021-10-27 10:52 | G | 2018-12-14 | Five Corners Substation - NG Western MA Area Cluster Study | PV | SUN | 3 | 3 | 3 | Hampshire | MA | 2021-07-29 | 2021-07-29 |  | NG Five Corners Substation | NA | TRUE | TRUE | NGRID | PD | WMA
| 815 | 2025-06-16 12:55 | G | 2018-12-14 | Lashaway Substation - NG Western MA Area Cluster Study | PV | SUN | 13.675 | 13.675 | 13.675 | Worcester | MA | 2022-04-15 | 2020-07-20 | 2025-06-13 | NG Lashaway Substation | NA | TRUE | TRUE | NGRID | PD | WMA
| 816 | 2021-10-27 11:11 | G | 2018-12-14 | Leicester - NG Western MA Area Cluster Study | PV | SUN | 2.592 | 2.592 | 2.592 | Worcester | MA | 2021-05-31 | 2021-05-31 |  | NG Lecester | NA | FALSE | FALSE |  | PD | WMA
| 817 | 2025-06-16 12:56 | G | 2018-12-14 | Little Rest Rd Substation - NG Western MA Area Cluster Study | PV | SUN | 6 | 6 | 6 | Worcester | MA | 2022-08-20 | 2020-08-14 | 2025-06-13 | NG Little Rest Rd Substation | NA | TRUE | TRUE | NGRID | PD | WMA
| 818 | 2025-06-16 12:57 | G | 2018-12-14 | Meadow Street 552 Substation - NG Western MA Area Cluster Study | PV | SUN | 13.38 | 13.38 | 13.38 | Worcester | MA | 2022-11-08 | 2020-06-20 | 2025-06-13 | NG Meadow Street 552 Substation | NA | TRUE | TRUE | NGRID | PD | WMA
| 819 | 2021-10-27 10:57 | G | 2018-12-14 | N. Oxford Substation - NG Western MA Area Cluster Study | PV | SUN | 8.7 | 8.7 | 8.7 | Worcester | MA | 2020-12-30 | 2020-01-31 |  | NG N. Oxford Substation | NA | TRUE | TRUE | NGRID | PD | WMA
| 820 | 2025-06-16 12:57 | G | 2018-12-14 | Palmer Substation - NG Western MA Area Cluster Study | PV | SUN | 18.095 | 18.095 | 18.095 | Hampden | MA | 2022-01-20 | 2019-02-28 | 2025-06-13 | NG Palmer Substation | NA | TRUE | TRUE | NGRID | PD | WMA
| 821 | 2025-06-16 13:00 | G | 2000-12-14 | Pondville - NG Western MA Area Cluster Study | PV | SUN | 4.875 | 4.875 | 4.875 | Worcester | MA | 2022-05-22 | 2022-05-22 | 2025-06-13 | NG Pondville | NA | FALSE | FALSE |  | PD | WMA
| 822 | 2021-10-27 11:00 | G | 2018-12-14 | Royalston - NG Western MA Area Cluster Study | PV | SUN | 2.5 | 2.5 | 2.5 | Worcester | MA | 2022-04-26 | 2022-04-26 | 2021-10-20 | NG Royalston | NA | TRUE | TRUE | NGRID | PD | WMA
| 823 | 2025-06-16 13:01 | G | 2018-12-14 | Thorndike Substation - NG Western MA Area Cluster Study | PV | SUN | 12.448 | 12.448 | 12.448 | Hampden | MA | 2023-12-31 | 2019-10-01 | 2025-06-13 | NG Thorndike Substation | NA | TRUE | TRUE | NGRID | PD | WMA
| 824 | 2025-06-16 13:01 | G | 2018-12-14 | Ware Substation - NG Western MA Area Cluster Study | PV | SUN | 13.272 | 13.272 | 13.272 | Hampshire | MA | 2023-12-31 | 2021-07-08 | 2025-06-13 | NG Ware Substation | NA | TRUE | TRUE | NGRID | PD | WMA
| 825 | 2019-05-03 07:56 | G | 2018-12-14 | Webster St - NG Western MA Area Cluster Study | PV | SUN | 9 | 9 | 9 | Worcester | MA | 2020-08-01 | 2020-08-01 | 2019-03-15 | NG Webster St | NA | FALSE | FALSE |  | PD | WMA
| 826 | 2021-10-27 11:05 | G | 2018-12-14 | Wendell Depot Substation - NG Western MA Area Cluster Study | PV | SUN | 14.97 | 14.97 | 14.97 | Franklin | MA | 2021-10-16 | 2021-06-01 |  | NG Wendell Depot Substation | NA | TRUE | TRUE | NGRID | PD | WMA
| 827 | 2021-10-27 11:14 | G | 2018-12-14 | Westminster - NG Western MA Area Cluster Study | PV | SUN | 4.875 | 4.875 | 4.875 | Worcester | MA | 2021-06-07 | 2021-06-07 |  | NG Westminster | NA | TRUE | TRUE |  | PD | WMA
| 828 | 2021-08-31 10:52 | ETU | 2018-12-14 | ETU for simultaneous delivery of specific Queued projects | NA | N/A |  |  |  | NA | MA | 2025-05-31 | 2025-03-31 | 2021-08-26 | N/A | N/A | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
| 829 | 2022-05-24 14:03 | G | 2018-12-19 | Offshore Wind | WT | WND | 400 | 400 | 400 | NA | MA | 2025-07-02 | 2025-04-01 | 2022-05-24 | NSTAR Electric Company 345 kV lines 322 and 342 | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | In Progress |  |  |  | Under Study
| 830 | 2022-05-24 14:04 | G | 2018-12-19 | Offshore Wind | WT | WND | 860 | 860 | 860 | NA | MA | 2025-07-01 | 2025-04-01 | 2022-05-24 | NSTAR Electric Company West Barnstable 345 kV. | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
| 831 | 2021-03-16 08:08 | G | 2018-12-21 | Battery Storage | OT | BAT | 200 | 200 | 200 | Windham | CT | 2024-05-01 | 2024-04-01 | 2021-03-16 | Eversource Killingly 345kV substation, Lat: 41.881266°, Long: -71.891253° | CNR | TRUE | TRUE | ISO-NE | PD | CT |  | Document Posted |  |  | In Progress
| 832 | 2019-09-05 11:40 | G | 2019-01-04 | Battery Storage | OT | BAT | 150 | 150 | 150 | Plymouth | MA | 2021-12-01 | 2021-11-01 | 2019-09-05 | National Grid East Bridgewater 115kV substation, Lat: 42.023890°, Long: -70.966356° | CNR | FALSE | FALSE |  | PD | SEMA | In Progress |  |  |  |  | Under Study
| 833 | 2023-10-26 14:52 | G | 2019-01-09 | Three Rivers Solar | PV | SUN | 100 | 100 | 100 | Hancock | ME | 2026-12-31 | 2026-06-29 |  | New 115 kV breaker Ring bus, tapping 115 kV Line 93 (Emera Maine) between Bull Hill & Deblois | NR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  | Document Posted | Executed
| 834 | 2022-05-16 12:56 | G | 2019-01-17 | GD 1-9 Iron Mine Solar | PV | SUN | 38.4 | 38.4 | 38.4 | N. Smithfield | RI | 2022-05-13 | 2021-12-30 |  | GRID 115 kV H17 Line (via 34.5 kV feeders from new 115/34.5 kV station) | NA | TRUE | TRUE | NGRID | PD | RI
| 835 | 2025-06-16 13:02 | G | 2019-01-22 | Solar | PV | SUN | 5 | 5 | 5 | Norfolk | MA | 2021-09-03 | 2021-08-15 | 2025-06-13 | GRID 348W7, Pole P53 on Washington St, Franklin | NA | FALSE | FALSE |  | NA | SEMA
| 836 | 2025-06-16 13:03 | G | 2019-01-31 | Solar | PV | SUN | 6.25 | 6.25 | 6.25 | Cranston | RI | 2023-03-01 | 2023-01-01 | 2025-06-13 | GRID Feeder 21F1 connected to West Cranston No. 21 substation | NA | TRUE | TRUE | NGRID |  | RI
| 837 | 2024-07-17 14:18 | ETU | 2019-02-22 | Somerset Wind Link - 1200 MW HVDC Line (Controllable) into Brayton Point | NA | N/A | 1200 |  |  | Bristol | MA | 2031-12-31 | 2030-05-01 |  | The proposed point of interconnection is: GRID Brayton PT 345kV | N/A | TRUE | TRUE | ISO-NE | PD | RI |  | Document Posted |  | Document Posted | Executed
| 838 | 2025-06-16 13:03 | G | 2019-02-25 | Solar | PV | SUN | 9.8 | 9.8 | 9.8 | Kent | RI | 2021-09-30 | 2021-09-01 | 2025-06-13 | GRID 3310 Feeder 34.5 kV to Kent County substation | NA | TRUE | TRUE | NGRID | PD | RI
| 839 | 2023-03-30 17:18 | G | 2019-02-25 | Solar | PV | SUN | 20 | 20 | 20 | Kent | RI | 2023-03-17 | 2023-01-20 |  | GRID 3310 Feeder 34.5 kV to Kent County substation | NA | TRUE | TRUE | NGRID | PD | RI
| 840 | 2020-11-09 16:13 | G | 2019-03-01 | Sanford Airport Solar CNR only | PV | SUN | 0 | 50 | 50 | York | ME | 2020-11-07 | 2020-10-06 |  | CMP's Sanford - Maguire 115 kV line, section 237 | CNR | FALSE | FALSE |  | NA | ME |  |  |  |  | Executed | In Service
| 841 | 2021-12-27 14:19 | G | 2019-03-05 | Quinebaug Solar CNR only | PV | SUN | 0.9 | 49.9 | 49.9 | Windham | CT | 2021-12-18 | 2021-12-11 |  | Killingly to Tunnel 115 kV line (approx 5.5 miles south of Brooklyn Substation) - New Eversource Canterbury switching station. GPS Coordinates: - 71 55’ 27.9” W - 41 44’ 14.21” N | CNR | FALSE | FALSE |  |  | CT |  |  |  |  | Executed | In Service
| 842 | 2021-09-27 13:02 | G | 2019-03-05 | Milo Solar | PV | SUN | 20 | 20 | 20 | Pisataquis | ME | 2021-09-25 | 2021-06-02 |  | EMERA 46kV 28 ME-16 Milo, Maine | CNR | TRUE | TRUE | ISO-NE |  | BHE |  | Document Posted |  |  | Executed | In Service
| 843 | 2019-04-18 09:07 | G | 2019-03-07 | Solar | PV | SUN | 12 | 12 | 12 | Essex | VT | 2020-07-01 | 2020-06-01 | 2019-04-18 | POI location: 44.777214,-71.633269 New 34.5 kV Line Tap at VEC Pole 84-872 | CNR | FALSE | FALSE |  |  | VT
| 844 | 2023-10-19 13:46 | G | 2019-03-13 | Medway Grid Battery Storage | OT | BAT | 250 | 250 | 250 | Norfolk | MA | 2025-12-31 | 2025-11-20 |  | Eversource 345 kV West Medway substation | CNR | TRUE | TRUE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  |  | Executed | Under Study
| 845 | 2019-11-12 09:31 | G | 2019-03-18 | Solar | PV | SUN | 20 | 20 | 20 | Windham | CT | 2020-07-01 | 2020-06-01 | 2019-11-08 | 3 Breaker Ring Bus on the Eversource 1607 Line (modeling based on same point as Exeter Tap for practical purposes) | CNR | FALSE | FALSE |  | PD | CT | In Progress |  |  |  |  | Under Study
| 846 | 2022-08-10 13:00 | G | 2019-03-19 | Offshore Wind Increase | WT | WND | 40 | 840 | 840 | NA | MA | 2026-05-31 | 2025-09-21 | 2022-08-10 | National Grid, 345 kV Brayton Point Substation, Somerset, MA | CNR | TRUE | TRUE | ISO-NE | PD | RI | Document Posted | Document Posted |  |  | Not Started
| 847 | 2020-03-09 08:26 | G | 2019-03-19 | Battery Storage | OT | BAT | 150 | 150 | 150 | Essex | MA | 2023-05-31 | 2023-04-30 | 2020-03-06 | Primary POI: Expand NGRID S.Danvers 115 kV substation by connecting to B-154N line Alternative POI: Tap B-154N line two spans west of the S. Danvers substation to construct a new three-breaker ring bus | CNR | FALSE | FALSE |  | PD | BOST | Document Posted |  |  |  |  | Under Study
| 848 | 2025-06-16 13:04 | G | 2019-03-21 | Adams substation - NG Western MA Area Cluster Study | PV | SUN | 10.978 | 10.978 | 10.978 | Berkshire | MA | 2021-12-31 | 2021-12-02 | 2025-06-13 | NG Adams substation | NA | TRUE | TRUE | NGRID |  | WMA
| 849 | 2025-06-16 13:04 | G | 2019-03-21 | Ashburnham substation - NG Western MA Area Cluster Study | PV | SUN | 4.98 | 4.98 | 4.98 | Worcester | MA | 2023-01-12 | 2023-01-12 | 2025-06-13 | NG Ashburnham substation | NA | FALSE | FALSE |  |  | WMA
| 850 | 2021-10-27 11:08 | G | 2019-03-21 | Bear Swamp Upper Yard substation - NG Western MA Area Cluster Study | PV | SUN | 2.5 | 2.5 | 2.5 | Berkshire | MA | 2021-09-08 | 2021-09-08 |  | NG Bear Swamp Upper Yard substation | NA | TRUE | TRUE | NGRID |  | WMA
| 851 | 2020-02-26 15:35 | G | 2019-03-21 | Brookfield substation - NG Western MA Area Cluster Study | PV | SUN | 24 | 24 | 24 | Worcester | MA | 2020-08-01 | 2020-08-01 | 2020-02-18 | NG Brookfield substation | NA | FALSE | FALSE |  |  | WMA
| 852 | 2025-06-16 13:05 | G | 2019-03-21 | E. Webster substation - NG Western MA Area Cluster Study | PV | SUN | 4.88 | 4.88 | 4.88 | Worcester | MA | 2023-10-01 | 2022-08-09 | 2025-06-13 | NG E.. Webster substation | NA | TRUE | TRUE | NGRID |  | WMA
| 853 | 2025-06-16 13:06 | G | 2019-03-21 | East Longmeadow substation - NG Western MA Area Cluster Study | PV | SUN | 8.99 | 8.99 | 8.99 | Hampden | MA | 2022-08-07 | 2019-11-15 | 2025-06-13 | NG East Longmeadow | NA | TRUE | TRUE | NGRID |  | WMA
| 854 | 2021-10-27 11:58 | G | 2019-03-21 | Litchfield substation - NG Western MA Area Cluster Study | PV | SUN | 9.49 | 9.49 | 9.49 | Worcester | MA | 2021-04-30 | 2021-04-30 |  | NG Litchfield substation | NA | TRUE | TRUE | NGRID |  | WMA
| 855 | 2025-06-16 13:06 | G | 2019-03-21 | Millbury substation - NG Western MA Area Cluster Study | PV | SUN | 14.44 | 14.44 | 14.44 | Worcester | MA | 2023-11-01 | 2022-05-21 | 2025-06-13 | NG Millbury substation | NA | TRUE | TRUE | NGRID |  | WMA
| 856 | 2021-03-04 08:54 | G | 2019-03-21 | New Salem substation - NG Western MA Area Cluster Study | PV | SUN | 21.272 | 21.272 | 21.272 | Worcester | MA | 2020-08-01 | 2020-08-01 |  | NG New Salem substation | NA | TRUE | TRUE | NGRID |  | WMA
| 857 | 2021-03-04 09:15 | G | 2019-03-21 | Powder Mill substation - NG Western MA Area Cluster Study | PV | SUN | 70.664 | 70.664 | 70.664 | Worcester | MA | 2020-08-01 | 2020-08-01 |  | NG Powder Mill substation | NA | TRUE | TRUE | NGRID |  | WMA
| 858 | 2020-02-26 15:38 | G | 2019-03-21 | Pratts Junction substation - NG Western MA Area Cluster Study | PV | SUN | 2 | 2 | 2 | Worcester | MA | 2020-08-01 | 2020-08-01 | 2020-02-18 | NG Pratts Junction substation | NA | FALSE | FALSE |  |  | WMA
| 859 | 2020-02-26 15:36 | G | 2019-03-21 | Prospect Street substation - NG Western MA Area Cluster Study | PV | SUN | 2 | 2 | 2 | Worcester | MA | 2020-08-01 | 2020-08-01 | 2020-02-18 | NG Prospect Street Substation | NA | FALSE | FALSE |  |  | WMA
| 860 | 2025-06-16 13:07 | G | 2019-03-21 | Shutesbury substation - NG Western MA Area Cluster Study | PV | SUN | 19.992 | 19.992 | 19.992 | Hampshire | MA | 2023-12-31 | 2021-12-31 | 2025-06-13 | NG Shutesbury substation | NA | TRUE | TRUE | NGRID |  | WMA
| 861 | 2025-06-16 13:08 | G | 2019-03-21 | Snow Street substation - NG Western MA Area Cluster Study | PV | SUN | 24.652 | 24.652 | 24.652 | Worcester | MA | 2023-04-05 | 2020-12-31 | 2025-06-13 | NG Snow Street substation | NA | TRUE | TRUE | NGRID |  | WMA
| 862 | 2021-10-27 12:03 | G | 2019-03-21 | Stafford Street substation - NG Western MA Area Cluster Study | PV | SUN | 20.38 | 20.38 | 20.38 | Worcester | MA | 2022-10-01 | 2020-08-01 | 2021-10-20 | NG Stafford Street substation | NA | TRUE | TRUE | NGRID |  | WMA
| 863 | 2021-10-27 12:05 | G | 2019-03-21 | Treasure Valley substation - NG Western MA Area Cluster Study | PV | SUN | 2.23 | 2.23 | 2.23 | Worcester | MA | 2019-09-19 | 2019-09-19 |  | NG Treasure Valley substation | NA | TRUE | TRUE | NGRID |  | WMA
| 864 | 2025-06-16 13:09 | G | 2019-03-21 | W. Charlton substation - NG Western MA Area Cluster Study | PV | SUN | 17.032 | 17.032 | 17.032 | Worcester | MA | 2022-10-10 | 2020-08-29 | 2025-06-13 | NG W. Charlton substation | NA | TRUE | TRUE | NGRID |  | WMA
| 865 | 2025-06-16 13:09 | G | 2019-03-21 | West Hampden 139 substation - NG Western MA Area Cluster Study | PV | SUN | 13.173 | 13.173 | 13.173 | Hampden | MA | 2023-03-10 | 2019-07-05 | 2025-06-13 | NG West Hampden substation | NA | TRUE | TRUE | NGRID |  | WMA
| 866 | 2021-03-04 09:07 | G | 2019-03-21 | Whitmanville substation - NG Western MA Area Cluster Study | PV | SUN | 26.612 | 26.612 | 26.612 | Worcester | MA | 2020-08-01 | 2020-08-01 |  | NG Whitmanville substation | NA | TRUE | TRUE | NGRID |  | WMA
| 867 | 2021-10-27 12:10 | G | 2019-03-21 | Wilbraham substation - NG Western MA Area Cluster Study | PV | SUN | 4 | 4 | 4 | Hampden | MA | 2020-12-03 | 2020-12-03 |  | NG Wilbraham substation | NA | TRUE | TRUE | NGRID |  | WMA
| 868 | 2024-10-18 17:15 | G | 2019-04-10 | Nellie Solar | PV | SUN | 15 | 15 | 15 | Sullivan | NH | 2024-10-01 | 2024-09-04 | 2024-10-18 | Eversource 34.5 kV line 3410 out of the North Road substation, extended along Maple Street, Newport NH. | NR | TRUE | TRUE | ISO-NE | PD | NH | Document Posted | Document Posted |  |  | Executed
| 869 | 2025-06-16 13:44 | G | 2019-03-26 | Solar | PV | SUN | 6.22 | 6.22 | 6.22 | Providence | RI | 2025-03-10 | 2022-04-01 | 2025-06-13 | NG feeder 26W1, Woonsocket substation | NA | TRUE | TRUE | NGRID | PD | RI
| 870 | 2025-06-16 13:44 | G | 2019-03-26 | Solar | PV | SUN | 6.22 | 6.22 | 6.22 | Providence | RI | 2025-03-10 | 2022-04-01 | 2025-06-13 | NG feeder 26W7, Woonsocket substation | NA | TRUE | TRUE | NGRID | PD | RI
| 871 | 2020-01-17 10:27 | G | 2019-03-28 | Energy Storage | OT | BAT | 100 | 100 | 100 | Grafton | NH | 2023-05-31 | 2022-03-01 | 2020-01-17 | PSNH 115kV Littleton substation | CNR | FALSE | FALSE |  | PD | NH |  | In Progress |  |  |  | Under Study
| 872 | 2020-02-10 08:26 | G | 2019-04-01 | Battery Storage | OT | BAT | 180 | 180 | 180 | Washington | RI | 2023-03-01 | 2022-11-15 | 2020-02-08 | National Grid 115kV Kent County- West Kingston line Approx: Latitude: 41°28'50.34"N, Longitude: 71°34'24.82"W | CNR | FALSE | FALSE |  | PD | RI |  | In Progress |  |  |  | Under Study
| 873 | 2020-07-02 11:34 | ETU | 2019-04-04 | 1200 MW HVDC Line (controllable) Into Mystic | NA | N/A | 1200 |  |  | Middlesex | MA | 2024-08-01 | 2024-05-01 | 2020-07-02 | The proposed point of Interconnection is: NSTAR Mystic 345kV Substation | N/A | FALSE | FALSE |  | PD | BOST | Document Posted | Not Started |  |  |  | Under Study
| 874 | 2025-12-01 14:43 | G | 2019-04-08 | Cross Town Battery Storage | OT | BAT | 175 | 175 | 175 | Cumberland | ME | 2025-11-29 | 2025-09-05 |  | CMP Mosher 115kV Substation - Lat: 43°41'2.39"N Long: 70°23'56.24"W | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 875 | 2021-10-27 10:39 | G | 2019-04-08 | Farmington Solar CNR only | PV | SUN | 0 | 78.4 | 78.4 | Franklin | ME | 2021-10-27 | 2021-09-09 |  | CMP's Sturtevant - Livermoore Fall 115 kV line | CNR | FALSE | FALSE |  | NA | ME |  |  |  |  | Executed
| 876 | 2021-12-21 09:46 | G | 2019-04-11 | Energy Storage | OT | BAT | 246 | 246 | 246 | Bristol | MA | 2024-12-31 | 2024-10-28 | 2021-12-20 | Eversource 115kV Cross Road Substation Line 109 | CNR | TRUE | TRUE | ISO-NE | PD | SEMA |  | Document Posted |  | In Progress |  | Under Study
| 877 | 2025-06-30 14:06 | G | 2019-04-11 | Energy Storage | OT | BAT | 170 | 170 | 170 | Norfolk | MA | 2027-07-26 | 2027-06-26 |  | National Grid's South Wrentham 115kV substation | NR | TRUE | TRUE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  |  | Executed
| 878 | 2019-05-02 16:10 | G | 2019-04-15 | Solar | PV | SUN | 19.8 | 19.8 | 19.8 | Sullivan | NH | 2020-11-05 | 2020-03-05 | 2019-05-01 | Eversource Lost Nation Substation (34.5 kV) | NR | FALSE | FALSE |  | PD | NH
| 879 | 2019-05-28 17:05 | G | 2019-04-15 | Simple Cycle Combustion Turbine Repowering (alternative to Q647) | GT | DFO NG | 0 | 376 | 378 | Middlesex | CT | 2023-05-31 | 2023-01-16 | 2019-05-28 | Middletown 115 kV substation, Bus A, between breakers 1T and 2T | CNR | FALSE | FALSE |  |  | CT
| 880 | 2019-05-15 14:10 | G | 2019-04-17 | Generator reactivation | ST | BLQ WDS | 24 | 24 | 24 | Penobscot | ME | 2020-10-30 | 2020-09-30 | 2019-05-15 | Emera Maine 46kv Line 5/7 / Old Town Maine @ Penobscot River | CNR | FALSE | FALSE |  |  | BHE
| 881 | 2020-06-02 13:02 | G | 2019-04-18 | Fore River CNR Uprate | CC | DFO NG | 0 | 800 | 843 | Norfolk | MA | 2020-06-01 | 2020-06-01 |  | NSTAR Edgar 115kv substation. | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed
| 882 | 2021-12-14 13:04 | G | 2019-04-24 | Kendall CNR Restoration | CC | DFO NG | 13.551 | 248.504 | 252.074 | Middlesex | MA | 2021-11-04 | 2021-11-04 |  | Kendall CT and Kendall Steam 3: point where Eversource Line 875-539 connects to Eversource 115 kV bus at Station 875. Kendall Jet: point where Eversource breaker J1242 connects to A bus at Kendall Station. | CNR | TRUE | TRUE |  |  | BOST |  | Document Posted |  |  | Executed
| 883 | 2025-03-04 12:16 | G | 2019-04-24 | Kendall Combined Cycle increase | CC | DFO NG | 16.449 | 264.953 | 268.523 | Middlesex | MA | 2025-06-01 | 2025-06-01 | 2025-03-04 | Kendall CT and Kendall Steam 3: point where Eversource Line 875-539 connects to Eversource 115 kV bus at Station 875. Kendall Jet: point where Eversource breaker J1242 connects to A bus at Kendall Station. | CNR | TRUE | TRUE | ISO-NE | PD | BOST |  | Document Posted |  |  | Executed
| 884 | 2021-01-12 09:46 | G | 2019-04-24 | Nutmeg Solar CNR only | PV | SUN | 0 | 19.9 | 19.9 | Hartford | CT | 2020-12-07 | 2020-11-15 |  | 115kV Sitico Sub | CNR | FALSE | FALSE |  |  | CT |  |  |  |  | Executed
| 885 | 2019-09-03 11:24 | G | 2019-04-25 | Fuel Cell | FC | NG | 20.24 | 20.24 | 20.24 | Hartford | CT | 2020-06-30 | 2020-05-01 | 2019-09-03 | Black Rock Substation (Eversource) via the Farmington River Power Company owned Burritt St substation 69kv line 680 | CNR | FALSE | FALSE |  |  | CT
| 886 | 2020-03-09 08:27 | G | 2019-04-26 | Battery Storage | OT | BAT | 200 | 200 | 200 | Norfolk | MA | 2023-05-31 | 2023-04-30 | 2020-03-06 | Eversource 345 kV Holbrook | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted |  |  |  |  | Under Study
| 887 | 2023-11-14 16:22 | G | 2019-04-26 | Battery Storage | OT | BAT | 150 | 150 | 150 | Plymouth | MA | 2026-05-31 | 2026-04-30 | 2023-11-14 | Eversource Line 113 at Wareham 115 kV substation | NR | TRUE | FALSE | ISO-NE | PD | SEMA | Document Posted | In Progress |  |  |  | Under Study
| 888 | 2021-03-04 11:56 | G | 2019-04-26 | Millinocket Battery additon | OT | WAT BAT | 0 | 126 | 126 | Penobscot | ME | 2020-12-30 | 2020-12-07 |  | 115/34.5 kV Powersville Rd Substation and Millinocket Sub 4, 34.5 kV Bus | CNR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed | In Service
| 889 | 2023-06-05 16:50 | ETU | 2019-05-01 | NECEC Elective Transmission Deliverability Upgrades | NA | N/A |  |  |  | Androscoggin | ME | 2025-08-28 | 2025-08-28 |  | N/A | N/A | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 890 | 2020-06-26 17:07 | ETU | 2019-05-13 | Increase transfer capability for N to S flows (Norwalk Harbor substation to Northport substation) | NA | N/A |  |  |  | NA | CT | 2023-07-01 | 2023-06-02 | 2020-06-26 | N/A | N/A | FALSE | FALSE |  |  | SWCT | In Progress |  |  |  |  | Under Study
| 891 | 2020-01-16 13:31 | ETU | 2019-05-29 | 1400 MW HVDC Line into Millstone | NA | N/A | 1400 |  |  | New London | CT | 2024-03-01 | 2024-01-01 | 2020-01-16 | The proposed point of Interconnection is the Eversource Millstone 345kV substation in Waterford, CT - Alternate is Haddam 345 kV Substation | N/A | FALSE | FALSE |  | PD | CT | Not Started |  |  |  |  | Under Study
| 892 | 2025-08-19 14:26 | G | 2019-06-12 | Gravel Pit Solar | PV | SUN | 50 | 50 | 50 | Hartford | CT | 2025-08-13 | 2024-10-28 |  | Line cut and three-breaker ring bus of the 115 kV Connecticut Light & Power Company line between Barbour Hill and Windsor Locks | CNR | TRUE | TRUE | ISO-NE |  | CT |  | Document Posted |  |  | Executed
| 893 | 2021-10-20 10:01 | G | 2019-06-07 | Offshore Wind | WT | WND | 1200 | 1200 | 1200 | NA | CT | 2025-05-31 | 2024-06-01 | 2021-10-20 | Millstone 345kV alternate: lines 348 and 310 | CNR | FALSE | FALSE |  | PD | CT | Document Posted | In Progress |  |  |  | Under Study
| 894 | 2021-12-02 09:23 | G | 2019-06-10 | Gas turbine repowering (Alt. to Q647) | GT | DFO NG | 23 | 376 | 378 | Middlesex | CT | 2025-05-31 | 2025-01-16 | 2021-12-02 | Middletown 115 kV substation, Bus A, between breakers 1T and 2T | CNR | TRUE | TRUE | ISO-NE |  | CT |  | Document Posted |  |  | Not Started
| 895 | 2019-08-09 13:01 | G | 2019-06-27 | CT additional | GT | NG WO | 10 | 37.05 | 43.25 | Tolland | CT | 2021-02-01 | 2021-02-01 | 2019-08-09 | Connecticut Light and Power Company d/b/a Eversource Connecticut (ES CT) Card-Mansfield 900 Line operating at 69 kV at the North Eagleville / King Hill Road intersection | CNR | FALSE | FALSE |  |  | CT
| 896 | 2024-08-09 09:08 | G | 2019-07-17 | Saco Solar | PV | SUN | 19.6 | 19.6 | 19.6 | York | ME | 2026-07-01 | 2026-06-01 |  | CMPCO 34.5kV Louden Substation Saco, Maine | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  | Document Posted | Executed
| 897 | 2019-08-28 12:43 | G | 2019-07-26 | Solar | PV | SUN | 60 | 60 | 60 | Grafton | NH | 2022-06-01 | 2022-05-01 | 2019-08-28 | Eversource 34.5kV bus at the Beebe River Substation | CNR | FALSE | FALSE |  |  | NH
| 898 | 2019-08-28 12:43 | G | 2019-07-26 | Solar | PV | SUN | 33.1 | 33.1 | 33.1 | Grafton | NH | 2022-06-01 | 2022-05-01 | 2019-08-28 | NGRID 34.5kV transmission/distribution line 3318 in Monroe, NH | CNR | FALSE | FALSE |  |  | NH
| 899 | 2020-07-31 10:55 | ETU | 2019-07-29 | 1200 MW HVDC Line into Singer (Controllable) | NA | N/A | 1200 |  |  | Fairfield | CT | 2024-09-01 | 2024-07-01 | 2020-07-31 | The proposed point of interconnection is 345kV Singer substation in Bridgeport, CT. | N/A | FALSE | FALSE |  | PD | SWCT | Document Posted | Not Started |  |  |  | Under Study
| 900 | 2021-06-28 13:10 | G | 2019-08-01 | Solar | PV | SUN | 4.6 | 4.6 | 4.6 | Oxford | ME | 2021-06-14 | 2021-06-04 |  | CMP Oxford subsation, Circuit 437D1 | NA | TRUE | TRUE | CMP |  | ME
| 901 | 2021-06-28 13:11 | G | 2019-08-01 | Solar | PV | SUN | 4.6 | 4.6 | 4.6 | Oxford | ME | 2021-06-14 | 2021-06-04 |  | CMP Oxford substation, Circuit 437D2 | NA | TRUE | TRUE | CMP |  | ME
| 902 | 2021-07-02 11:07 | G | 2019-08-01 | Solar | PV | SUN | 7.2 | 7.2 | 7.2 | Kennebec | ME | 2021-07-02 | 2021-06-22 |  | CMP Blair Road substation, Circuit207D2 | NA | TRUE | TRUE | CMP |  | ME
| 903 | 2022-07-14 09:09 | G | 2019-08-01 | Solar | PV | SUN | 6.999 | 6.999 | 6.999 | Kennebec | ME | 2022-07-13 | 2022-05-24 |  | CMP Winslow substation, Circuit 870D2 | NA | TRUE | TRUE | CMP |  | ME | [5 empty] | Partially In Service
| 904 | 2025-01-08 11:44 | G | 2019-08-01 | Battery Storage | OT | BAT | 14 | 14 | 14 | Kennebec | ME | 2024-01-25 | 2024-01-01 | 2025-01-08 | CMP Puddledock substation, circuit 262D1 | NA | TRUE | TRUE | CMP |  | ME
| 905 | 2025-01-08 11:45 | G | 2019-08-01 | Battery Storage | OT | BAT | 10 | 10 | 10 | Cumberland | ME | 2024-08-01 | 2024-08-01 | 2025-01-08 | CMP Mussey Road substation, Circuit 636D2 | NA | TRUE | TRUE | CMP |  | ME
| 906 | 2023-03-14 16:05 | G | 2019-08-01 | Solar | PV | SUN | 4.8 | 4.8 | 4.8 | York | ME | 2022-07-14 | 2022-07-01 |  | CMP Pratt & Whitney substation, Circuit 661D2 | NA | TRUE | TRUE | CMP |  | ME
| 907 | 2019-10-21 15:52 | G | 2019-08-01 | Solar | PV | SUN | 5 | 5 | 5 | Androscoggin | ME | 2020-08-31 | 2020-08-01 | 2019-10-17 | CMP Hotel Road substation, Circuit 420D4 | NA | FALSE | FALSE |  |  | ME
| 908 | 2019-10-21 15:53 | G | 2019-08-01 | Solar | PV | SUN | 8.999 | 8.999 | 8.999 | Somerset | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Skowhegan North Side substation, Circuit 853D1 and 853D2 | NA | FALSE | FALSE |  |  | ME
| 909 | 2024-02-13 08:50 | G | 2019-08-01 | Offshore Wind | WT | WND | 814 | 814 | 814 | NA | MA | 2026-05-31 | 2026-04-01 | 2024-02-13 | Primary National Grid 115kV Bell Rock, alt: Eversource 115kV Wings Lane, National Grid 115kV Somerset | NR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
| 910 | 2025-10-30 09:29 | G | 2019-08-27 | Mousam River Solar | PV | SUN | 20 | 20 | 20 | York | ME | 2025-10-24 | 2025-09-15 |  | 34.5 kV bus at CMP Sanford Substation ( 43° 25.746'N, 70° 44.085'W) | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 911 | 2022-07-05 10:36 | G | 2019-08-22 | Solar | PV | SUN | 35 | 35 | 35 | Oxford | ME | 2024-12-30 | 2024-12-14 | 2022-07-05 | 34.5 kV bus at CMP's Lovell Substation. Lat/Lon 44° 7.315'N, 70° 53.332'W | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | In Progress
| 912 | 2021-10-22 08:55 | G | 2019-08-23 | Bloom Energy Fuel Cell | FC | FC | 10.2 | 10.2 | 10.2 | New London | CT | 2021-10-20 | 2021-10-07 |  | Eversource Willimantic 14S | NA | TRUE | TRUE | NU | PD | CT
| 913 | 2019-10-21 15:54 | G | 2019-08-29 | Solar | PV | SUN | 9.98 | 9.98 | 9.98 | Androscoggin | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Hotel Road substation, Curcuit 420D4 | NA | FALSE | FALSE |  | PD | ME
| 914 | 2019-10-21 15:55 | G | 2019-08-29 | Solar | PV | SUN | 5 | 5 | 5 | Androscoggin | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Deer Rips substation, curcuit 412D4 | NA | FALSE | FALSE |  | PD | ME
| 915 | 2019-10-21 15:56 | G | 2019-08-29 | Solar and Battery | OT | SUN BAT | 5 | 5 | 5 | Oxford | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Rumford substation, Curcuit 447D2 | NA | FALSE | FALSE |  | PD | ME
| 916 | 2019-10-21 15:56 | G | 2019-08-29 | Solar and Battery | OT | SUN BAT | 5 | 5 | 5 | Cumberland | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Fort Hill substation, Circuit 624D1 | NA | FALSE | FALSE |  | PD | ME
| 917 | 2019-10-21 15:57 | G | 2019-08-29 | Solar and Battery | OT | SUN BAT | 7.5 | 7.5 | 7.5 | Androscoggin | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Great Falls substation, Circuit 436D6 | NA | FALSE | FALSE |  | PD | ME
| 918 | 2019-10-21 15:58 | G | 2019-08-29 | Solar and Battery | OT | SUN BAT | 5 | 5 | 5 | Howard | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Trap Corner substation, Circuit 453D1 | NA | FALSE | FALSE |  | PD | ME
| 919 | 2019-10-21 15:59 | G | 2019-08-29 | Solar and Battery | OT | SUN BAT | 5 | 5 | 5 | Knox | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Thomaston Creek substation - Circuit 246D1 | NA | FALSE | FALSE |  | PD | ME
| 920 | 2019-10-21 15:59 | G | 2019-08-29 | Solar and Battery | OT | SUN BAT | 11.68 | 11.68 | 11.68 | York | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Biddleford Pump station - Circuit 605D1 | NA | FALSE | FALSE |  | PD | ME
| 921 | 2019-10-21 16:00 | G | 2019-08-29 | Solar and Battery | OT | SUN BAT | 9.35 | 9.35 | 9.35 | York | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Bonney Easgle substation - Circuit 610D2 | NA | FALSE | FALSE |  | PD | ME
| 922 | 2022-05-24 14:05 | G | 2019-09-03 | Offshore wind Increase (Q829) | WT | WND | 200 | 600 | 600 | NA | MA | 2025-07-01 | 2025-04-01 | 2022-05-24 | NSTAR Electric Company 345 kV lines 322 and 342 | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
| 923 | 2025-03-03 15:35 | G | 2019-09-03 | Solar | PV | SUN | 20 | 20 | 20 | Androscoggin | ME | 2025-02-25 | 2024-12-14 |  | CMP 34.5 kV Leeds substation | NA | TRUE | TRUE | CMP | PD | ME
| 924 | 2023-05-31 14:49 | ETU | 2019-09-06 | NY QP543 AC | NA | N/A | 0 | 0 | 0 | Albany/Dutchess | NY | 2023-12-31 | 2023-12-31 |  | NY Greenbush PV 345 kV | N/A | FALSE | FALSE |  | PD
| 925 | 2023-05-31 14:50 | ETU | 2019-09-06 | NY QP556 AC | NA | N/A | 0 | 0 | 0 | Onieda/Albany | NY | 2023-12-31 | 2023-12-31 |  | NY Edic - New Scotland 345 kV | N/A | FALSE | FALSE |  | PD | N/A
| 926 | 2020-11-06 13:00 | G | 2019-09-11 | Offshore Wind Increase (Q781) | WT | WND | 167 | 871 | 871 | NA | RI | 2023-12-01 | 2023-04-30 | 2020-11-06 | National Grid's 115kV Davisville Substation | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
| 927 | 2024-08-07 16:18 | G | 2019-09-16 | Offshore Wind | WT | WND | 1200 | 1200 | 1200 | NA | CT | 2031-05-31 | 2031-01-31 | 2024-08-07 | Primary: Eversource (CL&P) 345kV Montville, Alternatively Eversource (CL&P) 345kV Millstone. | NR | TRUE | TRUE | ISO-NE | PD | CT | Document Posted | Document Posted |  |  | In Progress
| 928 | 2023-11-27 09:52 | G | 2019-10-09 | Solar | PV | SUN | 20 | 20 | 20 | Somerset | ME | 2027-04-01 | 2027-03-15 | 2023-11-27 | 34.5 kV bus at CMP's Lakewood Substation in Madison, Maine | CNR | TRUE | FALSE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | In Progress
| 929 | 2023-08-31 14:28 | G | 2019-10-15 | GDC Saco Solar | PV | SUN | 20 | 20 | 20 | York | ME | 2024-08-31 | 2024-08-31 |  | CMP Louden 34.5kV substation | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 930 | 2022-10-24 14:42 | G | 2019-10-17 | Millstone Increase | ST | NUC | 37 | 1262 | 1262 | New London | CT | 2022-05-26 | 2022-05-26 |  | Eversource's Millstone 345 KV switchyard (15G) - no change to existing connection | CNR | TRUE | TRUE | ISO-NE | PD | CT |  | Document Posted |  |  | Executed | In Service
| 931 | 2024-10-18 17:16 | G | 2019-10-22 | Roxbury Solar | PV | SUN | 55 | 55 | 55 | Oxford | ME | 2024-10-24 | 2024-10-03 | 2024-10-18 | CMP Roxbury substation 115 kV bus | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 932 | 2023-01-03 11:58 | G | 2019-10-22 | Solar | PV | SUN | 110 | 110 | 110 | Carroll | NH | 2025-10-03 | 2025-09-12 | 2022-11-23 | 115 kV Eversource K1214 line between Saco Valley and Lovell, approximately 3.46 miles from Saco Valley. | CNR | TRUE | FALSE | ISO-NE | PD | ME |  | In Progress |  |  |  | Under Study
| 933 | 2020-12-01 14:45 | G | 2019-10-22 | Coolidge Solar CNR Only | PV | SUN | 0 | 19.9 | 19.9 | Windsor | VT | 2020-11-13 | 2018-12-12 |  | 115 kV Coolidge Substation | CNR | FALSE | FALSE |  | NA | VT |  |  |  |  | Executed
| 934 | 2025-01-06 15:15 | G | 2019-10-25 | Pembroke Solar | PV | SUN | 17.5 | 17.5 | 17.5 | Merrimack | NH | 2024-09-01 | 2024-08-05 | 2025-01-06 | Eversource Pole 334/201 of the 334G Line looped between Garvins & Rimmon, roughly 3.5 miles from Garvins | NR | TRUE | TRUE | ISO-NE | NA | NH |  | Document Posted |  |  | Executed
| 935 | 2025-05-05 16:00 | G | 2019-10-30 | West Baldwin Solar | PV | SUN | 17.1 | 17.1 | 17.1 | Cumberland | ME | 2029-09-30 | 2029-08-31 |  | CMP 34.5 kv Line, Section 91 | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 936 | 2023-12-06 13:53 | G | 2019-10-30 | Solar | PV | SUN | 45 | 45 | 45 | Coos | NH | 2024-10-01 | 2024-09-10 | 2023-12-06 | 115 kV bus of Eversource Paris Substation. | NR | TRUE | TRUE | ISO-NE | NA | NH |  | Document Posted |  |  | In Progress
| 937 | 2021-08-12 15:32 | G | 2019-11-14 | Solar CNR only | PV | SUN | 0 | 150 | 150 | York | ME | 2022-12-31 | 2022-12-15 | 2021-08-12 | CMP/Eversource 345 kV Line 391 from Buxton substation to Scobie Pond substation (approx. 27.7 miles from Buxton substation) | CNR | FALSE | FALSE |  |  | ME |  |  |  |  | Executed
| 938 | 2020-09-21 17:03 | G | 2019-11-21 | Solar | PV | SUN | 35 | 35 | 35 | Merrimack | NH | 2022-10-03 | 2022-09-25 | 2020-09-21 | POI is Eversource NH pole 317/153 of the 317 line out of the Oak Hill Substation. | CNR | FALSE | FALSE |  |  | NH | Document Posted |  |  |  |  | Under Study
| 939 | 2025-01-13 12:00 | G | 2019-11-25 | NB Fuel Cell | FC | NG | 20.24 | 20.24 | 20.24 | Hartford | CT | 2024-12-12 | 2024-05-28 |  | Black Rock Substation (Eversource) via the Farmington River Power Company owned Burritt St substation 69kv line 680 | NR | TRUE | TRUE | ISO-NE |  | CT |  | Document Posted |  |  | Executed | In Service
| 940 | 2025-08-19 14:26 | G | 2019-12-04 | Gravel Pit Solar increase | PV | SUN | 25 | 75 | 75 | Hartford | CT | 2025-08-13 | 2024-10-28 |  | Line cut and three-breaker ring bus of the 115 kV Connecticut Light & Power Company line between Barbour Hill and Windsor Locks. | CNR | TRUE | TRUE | ISO-NE | PD | CT |  | Document Posted |  |  | Executed
| 941 | 2024-04-29 10:37 | G | 2019-12-10 | Brayton Road Solar | PV | SUN | 3.368 | 3.368 | 3.368 | Newport | RI | 2024-02-15 | 2024-01-09 |  | GRID 33F4 Feeder Connecting to Tiverton No. 2 substation | NA | TRUE | TRUE | NGRID | PD | SEMA
| 942 | 2024-04-29 10:37 | G | 2019-12-10 | Brayton Road Solar | PV | SUN | 8.423 | 8.423 | 8.423 | Newport | RI | 2024-02-15 | 2024-01-09 |  | GRID 33F4 Feeder Connecting to Tiverton No. 2 substation | NA | TRUE | TRUE | NGRID | PD | SEMA
| 943 | 2021-11-12 15:03 | G | 2019-12-12 | Solar | PV | SUN | 15 | 15 | 15 | Androscoggin | ME | 2021-11-01 | 2021-10-01 | 2021-11-12 | Interconnecting to the existing CMP 34.5 kV line Section 72 between Gulf Island and Crowleys (about 3.85 miles from Crowleys). | CNR | TRUE | FALSE | ISO-NE | PD | ME |  | Document Posted |  |  | In Progress | Under Study
| 944 | 2024-08-08 11:23 | G | 2019-12-18 | Bay State Wind 4 Offshore Wind | WT | WND | 1200 | 1200 | 1200 | NA | MA | 2033-11-04 | 2033-03-27 |  | National Grid Brayton Point 345kV | NR | TRUE | TRUE | ISO-NE | PD | RI | Document Posted | Document Posted |  | Document Posted | Executed
| 945 | 2021-06-09 09:40 | G | 2019-12-18 | ND OTM LLC Generator Reactivation | ST | BLQ WDS | 8 | 8 | 8 | Penobscot | ME | 2021-06-05 | 2021-06-05 |  | Emera Maine 46 kv Line 5/7 / Old Town Maine @ Penobscot River | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed | In Service
| 946 | 2020-04-01 10:54 | G | 2019-12-27 | Solar | PV | SUN | 18.4 | 18.4 | 18.4 | York | ME | 2021-08-31 | 2021-08-15 | 2020-04-01 | CMP 34.5 kv, Section 182 | CNR | FALSE | FALSE | CMP | PD | ME
| 947 | 2020-03-12 16:38 | G | 2020-01-07 | Battery Storage | OT | BAT | 200 | 200 | 200 | Androscoggin | ME | 2022-12-07 | 2022-12-07 | 2020-03-12 | Sec 377, Approx. 2.71 miles east of Surowiec 345kV bus | CNR | FALSE | FALSE |  | PD | ME
| 948 | 2020-11-03 16:20 | G | 2020-01-10 | Solar | PV | SUN | 51.02 | 51.02 | 51.02 | Grafton | NH | 2022-06-01 | 2022-05-01 | 2020-11-03 | Eversource 115kV B-112 transmission line just east of Beebe River Substation | CNR | FALSE | FALSE |  | PD | NH | Document Posted |  |  |  |  | Under Study
| 949 | 2025-06-16 13:45 | G | 2020-01-23 | Fuel Cell | FC | NG | 9.66 | 9.66 | 9.66 | Fairfield | CT | 2024-12-01 | 2024-12-01 | 2025-06-13 | UI 13.8kV Congress I Substation | NA | TRUE | TRUE | UI |  | SWCT
| 950 | 2022-08-23 14:28 | G | 2020-01-20 | Solar | PV | SUN | 17 | 17 | 17 | Oxford | ME | 2024-06-20 | 2024-06-15 | 2022-08-23 | New substation on CMP 34.5 kV circuit Section #97 as shown on one-line | CNR | TRUE | FALSE | ISO-NE | PD | ME | Document Posted | In Progress |  |  |  | Under Study
| 951 | 2024-11-04 08:21 | G | 2020-02-03 | Riley-Jay-Otis-Livermore | HD | WAT | 28.325 | 28.325 | 28.325 | Androscoggin/Franklin | ME | 2024-11-01 | 2024-02-27 |  | CMP 115 kV Section 230 | NR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed | In Service
| 952 | 2020-04-08 12:16 | G | 2020-02-18 | Solar | PV | SUN | 4.99 | 4.99 | 4.99 | Androscoggin | ME | 2021-09-30 | 2021-08-31 | 2020-04-08 | CMP 34.5kV line. 44.074807, -70.280400 | NR | FALSE | FALSE |  |  | ME
| 953 | 2024-02-14 15:59 | G | 2020-02-19 | BD Solar Church Hill | PV | SUN | 20 | 20 | 20 | Androscoggin | ME | 2028-06-30 | 2028-05-31 |  | 101105 Augusta East w New Breaker | NR | TRUE | TRUE | ISO-NE |  | ME |  | Document Posted |  |  | Executed
| 954 | 2023-03-21 09:07 | G | 2020-03-05 | Tiverton Uprate | CC | NG | 0 | 287.5 | 305.5 | Newport | RI | 2021-05-31 | 2021-05-31 |  | Interconnection with Narragansett Electric Company's M13 and L14 115kV line taps to NEC's Tiverton substation. | CNR | FALSE | FALSE |  | PD | SEMA |  |  |  |  | Executed | In Service
| 955 | 2020-08-26 16:03 | G | 2020-03-12 | Vineyard Offshore Wind CNR Only | WT | WND | 0 | 800 | 800 | NA | MA | 2025-12-30 | 2024-01-02 |  | Eversource 115kV Barnstable Switch Station | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed
| 956 | 2024-05-01 10:53 | G | 2020-03-16 | Solar | PV | SUN | 10 | 10 | 10 | Rockingham | NH | 2024-10-28 | 2024-10-04 | 2024-05-01 | Eversource NH 3103 Line (34.5 kV) out of Brentwood substation extended along Exeter Rd | NR | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | In Progress
| 957 | 2025-06-16 13:46 | G | 2020-03-18 | Tower Hill - NG Western RI DG Area Study | PV | SUN | 6.75 | 6.75 | 6.75 | Washington | RI | 2023-01-15 | 2022-12-15 | 2025-06-13 | NG feeder 88F1, Tower Hill substation | NA | TRUE | TRUE | NGRID | PD | RI
| 958 | 2025-06-16 13:47 | G | 2020-03-18 | Wood River - NG Western RI DG Area Study | PV | SUN | 6.474 | 6.474 | 6.474 | Washington | RI | 2022-01-24 | 2022-01-17 | 2025-06-13 | NG feeder 85T2, Wood River Substation | NA | TRUE | TRUE | NGRID | PD | RI
| 959 | 2025-01-13 10:53 | G | 2020-03-18 | Chase Hill Substation - NG Western RI DG Area Study | PV | SUN | 6.75 | 6.75 | 6.75 | Washington | RI | 2021-08-15 | 2021-08-01 |  | NG feeder 88F1, Chase Hill Substation | NA | TRUE | TRUE | NGRID | PD | RI
| 960 | 2025-06-16 13:48 | G | 2020-03-18 | Chase Hill Substation - NG Western RI DG Area Study | PV | SUN | 6.339 | 6.339 | 6.339 | Washington | RI | 2021-08-15 | 2021-08-01 | 2025-06-13 | NG Chase Hill Substation | NA | TRUE | TRUE | NGRID | PD | RI
| 961 | 2025-06-16 13:50 | G | 2020-03-18 | Wolf Hill substation - NG Western RI DG Area Study | PV | SUN | 2.2 | 2.2 | 2.2 | Providence | RI | 2021-08-15 | 2021-08-01 | 2025-06-13 | NG Wolf Hill Substation | NA | TRUE | TRUE | NGRID | PD | RI
| 962 | 2025-06-16 13:50 | G | 2020-03-18 | Drumrock - NG Western RI DG Area Study | PV | SUN | 3.85 | 3.85 | 3.85 | Kent | RI | 2021-08-15 | 2021-08-01 | 2025-06-13 | NG Drumrock | NA | TRUE | TRUE | NGRID | PD | RI
| 963 | 2025-06-16 13:54 | G | 2020-03-18 | Johnston Substation - NG Western RI DG Area Study | PV | SUN | 4.25 | 4.25 | 4.25 | Providence | RI | 2021-08-15 | 2021-08-01 | 2025-06-13 | NG Johnston Substation | NA | TRUE | TRUE | NGRID | PD | RI
| 964 | 2025-06-16 13:55 | G | 2020-03-18 | Kenyon Substation - NG Western RI DG Area Study | PV | SUN | 3.5 | 3.5 | 3.5 | Washington | RI | 2021-08-15 | 2021-08-01 | 2025-06-13 | NG Kenyon Substation | NA | TRUE | TRUE | NGRID | PD | RI
| 965 | 2025-06-16 13:56 | G | 2020-03-18 | Kent County Substation - NG Western RI DG Area Study | PV | SUN | 10.368 | 10.368 | 10.368 | Kent | RI | 2021-08-15 | 2021-08-01 | 2025-06-13 | NG Lafayette No. 30 (supplied by Kent County Substation) | NA | TRUE | TRUE | NGRID | PD | RI
| 966 | 2025-06-16 13:56 | G | 2020-03-18 | New London Substation - NG Western RI DG Area Study | PV | SUN | 3 | 3 | 3 | Kent | RI | 2021-08-15 | 2021-08-01 | 2025-06-13 | NG New London Substation | NA | FALSE | FALSE |  | PD | RI
| 967 | 2025-06-16 13:57 | G | 2020-03-18 | Old Baptist Road Substation - NG Western RI DG Area Study | PV | SUN | 4.422 | 4.422 | 4.422 | Washington | RI | 2021-08-15 | 2021-08-01 | 2025-06-13 | NG Old Baptist Road Substation | NA | TRUE | TRUE | NGRID | PD | RI
| 968 | 2025-06-16 13:58 | G | 2020-03-18 | Putnam Pike Substation - NG Western RI DG Area Study | PV | SUN | 5.62 | 5.62 | 5.62 | Providence | RI | 2021-08-15 | 2021-08-01 | 2025-06-13 | NG Putnam Pike Substation | NA | TRUE | TRUE | NGRID | PD | RI
| 969 | 2025-06-16 13:59 | G | 2020-03-18 | Tower Hill Substation - NG Western RI DG Area Study | PV | SUN | 2 | 2 | 2 | Washington | RI | 2021-08-15 | 2021-08-01 | 2025-06-13 | NG Tower Hill Substation | NA | TRUE | TRUE | NGRID | PD | RI
| 970 | 2025-06-16 14:00 | G | 2020-03-18 | Wood River Substation - NG Western RI DG Area Study | PV | SUN | 7.84 | 7.84 | 7.84 | Washington | RI | 2021-08-15 | 2021-08-01 | 2025-06-13 | NG Wood River Substation | NA | TRUE | TRUE | NGRID | PD | RI
| 971 | 2024-08-02 11:07 | G | 2020-03-26 | Combined Cycle Upgrade | CC | NG | 4 | 564 | 588 | Fairfield | CT | 2021-07-12 | 2021-07-12 |  | UI Singer Substation | CNR | FALSE | FALSE |  | PD | SWCT |  |  |  |  | Executed | In Service
| 972 | 2022-05-16 12:59 | G | 2020-03-25 | Rumford Power Repair for Performance Upgrade | CC | NG | 0.205 | 271 | 280 | Oxford | ME | 2021-11-15 | 2021-11-15 |  | Interconnection of Rumford Power’s 115 kV Bus to CMP’s 115kV bus, located on Rumford Power's support structure, extending to CMP’s 115kV Rumford Industrial Park Substation | CNR | FALSE | FALSE |  | PD | ME |  |  |  |  | Executed
| 973 | 2025-06-16 14:00 | G | 2020-03-25 | Eversource Group Study @ Brook St | OT | SUN BAT | 9.778 | 9.778 | 9.778 | Plymouth | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Brook St | NA | TRUE | TRUE | NSTAR | PD | SEMA
| 974 | 2025-06-16 14:03 | G | 2020-03-25 | Solar plus Battery | OT | SUN BAT | 4.999 | 4.999 | 4.999 | Bristol | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Cross Road 651 | NA | TRUE | TRUE | NSTAR | PD | SEMA
| 975 | 2025-06-16 14:04 | G | 2020-03-25 | Eversource Group Study @ Crystal Spring | OT | SUN BAT | 20.46 | 20.46 | 20.46 | Plymouth | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Crystal Spring 646 | NA | TRUE | TRUE | NSTAR | PD | SEMA
| 976 | 2025-06-16 14:04 | G | 2020-03-25 | Eversource Group Study @ Industrial Park | OT | SUN BAT | 11.338 | 11.338 | 11.338 | Bristol | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Industrial Park 636 | NA | TRUE | TRUE | NSTAR | PD | SEMA
| 977 | 2025-06-16 14:05 | G | 2020-03-25 | Eversource Group Study @ Wareham | OT | SUN BAT | 55.14 | 55.14 | 55.14 | Plymouth | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Wareham 714 | NA | TRUE | TRUE | NSTAR | PD | SEMA
| 978 | 2025-06-16 14:06 | G | 2020-03-25 | Eversource Group Study @ Wing Lane | PV | SUN | 5.08 | 5.08 | 5.08 | Bristol | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Wing Lane 624 | NA | TRUE | TRUE | NSTAR | PD | SEMA
| 979 | 2025-11-14 11:16 | ETU | 2020-03-26 | NECEC 1200 MW HVDC (controllable - import only) CNR | NA | N/A | 0 |  |  | Androscoggin | ME | 2026-01-07 | 2024-09-01 | 2023-03-07 | N/A | NI | FALSE | FALSE |  |  | ME |  |  |  |  | Executed
| 980 | 2021-03-05 16:21 | G | 2020-03-26 | Solar addition | PV | SUN | 10 | 20 | 20 | Sullivan | NH | 2022-11-15 | 2022-10-30 | 2021-03-05 | River Road 46 kV (Bus No 108291) is same as the previous interconnection QP799 | CNR | FALSE | FALSE |  | PD | NH |  | In Progress |  |  |  | Under Study
| 981 | 2022-03-24 09:58 | G | 2020-03-27 | Bridgeport Harbor Unit #5 Uprate | CC | DFO NG | 0.4 | 509.6 | 532.6 | Fairfield | CT | 2021-12-22 | 2021-12-22 |  | UI Singer Substation 345kv | CNR | FALSE | FALSE |  | PD | SWCT |  |  |  |  | Executed
| 982 | 2025-02-19 14:58 | G | 2020-03-30 | Wind | WT | WND | 3.8 | 3.8 | 3.8 | Litchfield | CT | 2024-09-01 | 2024-07-01 |  | Eversource Canton 5R | NA | FALSE | FALSE |  | PD | CT
| 983 | 2020-06-18 16:52 | G | 2020-03-31 | Solar | PV | SUN | 40 | 40 | 40 | Androscoggin | ME | 2022-11-15 | 2022-10-16 | 2020-06-18 | The project will connect at Central Maine Power 200A at Switch 200A-2 (115 kV) | CNR | FALSE | FALSE |  | PD | ME
| 984 | 2023-05-31 13:54 | G | 2020-04-01 | Storage | OT | BAT | 150 | 150 | 150 | Middlesex | MA | 2023-09-20 | 2023-05-31 | 2023-05-31 | National Grid 115kV line 1/2 mile to the East of Billerica 70 substation | CNR | TRUE | TRUE | ISO-NE |  | BOST |  | Document Posted |  |  | In Progress
| 985 | 2021-07-20 11:03 | G | 2020-04-02 | Solar | PV | SUN | 4 | 4 | 4 | Washington | ME | 2021-07-29 | 2021-07-15 | 2021-07-20 | Emera Maine 34.5kV Line 3 approximately 1.8 miles from Washington County Substation (WCS) | CNR | FALSE | FALSE |  |  | BHE |  | In Progress |  |  |  | Under Study
| 986 | 2025-11-12 17:15 | G | 2020-04-07 | Solar | PV | SUN | 19.99 | 19.99 | 19.99 | Penobscot | ME | 2028-12-31 | 2028-11-30 | 2025-11-12 | Graham Substation – 46 kV open bus tie/breaker -via a tapped existing line approximately 5.1 miles to the substation. (44 51 39.25 N 68 39 28.19 W) | NR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  | Not Started | In Progress
| 987 | 2025-01-13 17:41 | G | 2020-04-10 | Chariot Solar CNR only | PV | SUN | 0 | 49.5 | 49.5 | Cheshire | NH | 2024-12-15 | 2024-11-15 | 2025-01-13 | NGrid 115 kV Vernon Road tap to Vernon Road Substation, 2.5 mi from Vernon Road Substation | NR | FALSE | FALSE |  |  | NH |  |  |  |  | Executed
| 988 | 2021-11-01 08:14 | G | 2020-04-07 | Solar CNR only | PV | SUN | 0 | 30 | 30 | Cheshire | NH | 2024-07-30 | 2024-06-30 | 2021-10-31 | The Project will interconnect at National Grid’s 115 kV line I-135 via a new three circuit breaker ring bus switching station located at 2.9 miles from Eversource’s Fitzwilliam Substation and 20.5 miles from Fitchburg Gas & Electric Light Company’s Flagg Pond Substation. | CNR | FALSE | FALSE |  |  | NH |  |  |  |  | In Progress
| 989 | 2025-06-16 14:08 | G | 2020-04-09 | Eversource Group Study @ Blandford | PV | SUN | 12.48 | 12.48 | 12.48 | Hampden | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eersource Blandford station | NA | TRUE | TRUE | NU |  | WMA
| 990 | 2025-06-16 14:08 | G | 2020-04-09 | Solar | PV | SUN | 4.89 | 4.89 | 4.89 | Berkshire | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Partidge station | NA | TRUE | TRUE | NU |  | WMA
| 991 | 2025-06-16 14:09 | G | 2020-04-09 | Solar | PV | SUN | 2.5 | 2.5 | 2.5 | Franklin | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Cumberland station | NA | TRUE | TRUE | NU |  | WMA
| 992 | 2025-06-16 14:11 | G | 2020-04-09 | Eversource Group @ Arsene St 654 | OT | SUN BAT | 7 | 7 | 7 | Bristol | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Arsene Street #654 | NA | FALSE | FALSE |  | PD | SEMA
| 993 | 2025-06-16 14:11 | G | 2020-04-09 | Solar + Battery | OT | SUN BAT | 2 | 2 | 2 | Plymouth | MA | 2025-07-31 | 2025-07-31 | 2025-06-13 | Eversource Brook St 727 | NA | TRUE | TRUE | NU |  | SEMA
| 994 | 2025-06-16 14:12 | G | 2020-04-09 | Solar + battery | OT | SUN BAT | 5.5 | 5.5 | 5.5 | Middlesex | MA | 2025-05-21 | 2025-05-21 | 2025-06-13 | Eversource Burlington #391 | NA | TRUE | TRUE | NU |  | SEMA
| 995 | 2025-06-16 14:13 | G | 2020-04-09 | Solar + Battery | OT | SUN BAT | 5 | 5 | 5 | Norfolk | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Canton #470 | NA | FALSE | FALSE |  |  | SEMA
| 996 | 2025-06-16 14:14 | G | 2020-04-09 | Eversource Group @ Cross Rd 651 | OT | SUN BAT | 9.5 | 9.5 | 9.5 | Bristol | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Cross Rd #651 | NA | FALSE | FALSE |  |  | SEMA
| 997 | 2025-06-16 14:14 | G | 2020-04-09 | Eversource Group @ Crystal Spring 646 | OT | SUN BAT | 7.499 | 7.499 | 7.499 | Middlesex | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Crystal Spring 646 | NA | FALSE | FALSE |  |  | SEMA
| 998 | 2025-06-16 14:15 | G | 2020-04-09 | Eversource Group @ Falmouth 993 | OT | SUN BAT | 7.99 | 7.99 | 7.99 | Barnstable | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Falmouth 933 | NA | FALSE | FALSE |  |  | SEMA
| 999 | 2025-06-16 14:18 | G | 2020-04-09 | Eversource Group @ Fisher Rd Substation 657 | OT | SUN BAT | 27.948 | 27.948 | 27.948 | Bristol | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Fisher Rd 657 | NA | FALSE | FALSE |  |  | SEMA
| 1000 | 2025-06-16 14:18 | G | 2020-04-09 | Solar + battery | OT | SUN BAT | 3.15 | 3.15 | 3.15 | Barnstable | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Harwich 968 | NA | FALSE | FALSE |  |  | SEMA
| 1001 | 2025-06-16 14:21 | G | 2020-04-09 | Eversource Group @ Industrial Park 636 | OT | SUN BAT | 29.11 | 29.11 | 29.11 | Bristol | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Industrial Park 636 | NA | FALSE | FALSE |  |  | SEMA
| 1002 | 2025-06-16 14:23 | G | 2020-04-09 | Solar | PV | SUN | 2.76 | 2.76 | 2.76 | Plymouth | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Kingston 735 | NA | FALSE | FALSE |  |  | SEMA
| 1003 | 2025-06-16 14:24 | G | 2020-04-09 | Eversource Group @ Rochester #745 | OT | SUN BAT | 24.618 | 24.618 | 24.618 | Plymouth | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Rochester #745 | NA | FALSE | FALSE |  |  | SEMA
| 1004 | 2025-06-16 14:25 | G | 2020-04-09 | Eversource Group @ Sandwich 916 | OT | SUN BAT | 11.75 | 11.75 | 11.75 | Barnstable | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Sandwich 916 | NA | FALSE | FALSE |  |  | SEMA
| 1005 | 2025-06-16 14:35 | G | 2020-04-09 | Eversource Group @ Tremont Substation 713 | OT | SUN BAT | 33.735 | 33.735 | 33.735 | Plymouth | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Tremont 713 | NA | FALSE | FALSE |  |  | SEMA
| 1006 | 2025-06-16 14:36 | G | 2020-04-09 | Eversource Group @ Valley 715 | OT | SUN BAT | 9.98 | 9.98 | 9.98 | Barnstable | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Valley 715 | NA | FALSE | FALSE |  |  | SEMA
| 1007 | 2025-06-16 14:37 | G | 2020-04-09 | Eversource Group @ Wareham 714 | OT | SUN BAT | 48.019 | 48.019 | 48.019 | Plymouth | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Wareham #714 | NA | FALSE | FALSE |  |  | SEMA
| 1008 | 2025-06-16 14:37 | G | 2020-04-09 | Eversource Group @ West Pond 737 | OT | SUN BAT | 44.12 | 44.12 | 44.12 | Plymouth | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource West Pond #737 | NA | FALSE | FALSE |  |  | SEMA
| 1009 | 2025-06-16 14:43 | G | 2020-04-09 | Eversource Group @ Wing Lane 624 | OT | SUN BAT | 18.989 | 18.989 | 18.989 | Bristol | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Wing Lane #624 | NA | FALSE | FALSE |  |  | SEMA
| 1010 | 2021-12-01 09:14 | G | 2020-04-10 | Berkshire Wind CNR | WT | WND | 0 | 19.6 | 19.6 | Berkshire | MA | 2021-09-13 | 2021-09-13 |  | Eversource 15-E 4 circuit. Interconnection Circuit connects to 115 KV transmission system at Partridge Substation in Pittsfield MA | CNR | FALSE | FALSE |  |  | WMA |  |  |  |  | Executed
| 1011 | 2020-08-28 11:12 | G | 2020-04-20 | Combined Cycle | CC | NG | 800 | 800 | 850 | Suffolk | MA | 2024-06-01 | 2024-05-31 | 2020-08-28 | Eversource Mystic 345 kV station | CNR | FALSE | FALSE |  | PD | BOST |  | In Progress |  |  |  | Under Study
| 1012 | 2020-08-28 11:12 | G | 2020-04-20 | Combined Cycle | CC | NG | 800 | 800 | 850 | Suffolk | MA | 2024-06-01 | 2024-05-31 | 2020-08-28 | Eversource Mystic 115 kV station | CNR | FALSE | FALSE |  | PD | BOST |  | Not Started
| 1013 | 2025-09-26 16:51 | G | 2020-04-22 | Solar | PV | SUN | 17.2 | 17.07 | 17.07 | Sagadahoc | ME | 2030-10-31 | 2030-09-16 | 2025-09-26 | CMP 34.5kV line 43, pole 278 | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | In Progress
| 1014 | 2023-10-03 15:01 | G | 2020-04-22 | Battery Storage | OT | BAT | 112.2 | 112.2 | 112.2 | Penobscot | ME | 2024-06-01 | 2024-03-01 | 2023-08-22 | EMERA Keene Rd 115 kV substation | CNR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted
| 1015 | 2023-10-03 15:01 | G | 2020-04-22 | Battery Storage | OT | BAT | 112.2 | 112.2 | 112.2 | Penobscot | ME | 2024-12-01 | 2024-09-01 | 2023-08-22 | Orrington 115kV | CNR | TRUE | FALSE | ISO-NE | PD | BHE |  | Document Posted |  | Not Required
| 1016 | 2024-05-01 10:52 | G | 2020-04-24 | Solar | PV | SUN | 16 | 16 | 16 | Hillsborough | NH | 2024-11-25 | 2024-10-31 | 2024-05-01 | At the Eversource NH 314 line (34.5kV) out of the South Milford substation. | NR | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | In Progress
| 1017 | 2025-02-19 10:57 | G | 2020-04-24 | Battery Storage | OT | BAT | 200 | 200 | 200 | New Haven | CT | 2026-10-01 | 2026-07-01 | 2025-02-19 | Eversource East Devon 345 kV Substation | NR | TRUE | TRUE | ISO-NE |  | SWCT | Document Posted | Document Posted |  |  | In Progress
| 1018 | 2024-08-29 14:17 | G | 2020-04-24 | Passadumkeag Wind CNR | WT | WND | 0 | 39.97 | 39.97 | Peneobscot | ME | 2021-11-15 | 2021-11-15 |  | Interconnection shall be at the point where the leads from the switch located on the high side of the 115 kV/34.5 kV transformer connect into the 115 kV ring bus at the Passadumkeag Substation in Greenbush, Maine | NR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed
| 1019 | 2023-09-19 09:19 | G | 2020-04-24 | Battery Storage | OT | BAT | 20 | 20 | 20 | Penobscot | ME | 2024-04-01 | 2024-01-01 | 2023-09-19 | Chester 46 kV | NR | TRUE | FALSE | ISO-NE | PD | BHE |  | Document Posted |  |  | In Progress | Under Study
| 1020 | 2022-12-14 09:12 | G | 2020-04-24 | Silver Maple Wind CNR | WT | WND | 0 | 20 | 20 | Penobscot | ME | 2022-12-14 | 2022-09-24 |  | Emera Maine 115kV Transmission Line 66, between Graham Substation and Rebel Hill substation, adjacent to Pisgah Mountain Wind Farm. | CNR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed | In Service
| 1021 | 2024-07-11 13:31 | G | 2020-04-27 | Emery Meadow Solar | PV | SUN | 16.425 | 16.425 | 16.425 | York | ME | 2026-09-30 | 2026-08-01 |  | CMP 34.5 kV, Section 182 | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 1022 | 2022-02-22 13:52 | G | 2020-04-24 | Cranberry Highway Solar + Battery Storage | OT | SUN BAT | 2.2 |  |  | Plymouth | MA | 2022-02-15 | 2022-02-05 |  | The primary connection of the proposed project to Eversource Energy is located on Tremont Station 713 Transformer #1 Line #86. The site is located approximately 2.29 circuit miles from Substation 713 near CYME® node 1200910-295. Circuit 3-86-966 | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed
| 1023 | 2022-03-04 09:19 | G | 2020-04-24 | Solar + Battery Storage | OT | SUN BAT | 2.425 | 2.425 | 2.425 | Bristol | MA | 2021-10-20 | 2021-10-20 | 2022-03-04 | Eversource 13.2 kV Circuit #522 approximately 5.95 miles from Fisher Road substation | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Not Started
| 1024 | 2024-09-25 10:36 | G | 2020-04-28 | ENA Old Falmouth Road PV + Storage | OT | SUN BAT | 4.85 | 4.85 | 4.85 | Barnstable | MA | 2024-08-08 | 2024-07-05 |  | The facility is located approximately 5.5 miles from MASHPEE Substation, via the 23 kV#88 circuit. | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed
| 1025 | 2020-08-25 10:27 | G | 2020-04-27 | Solar Increase | PV | SUN | 5 | 20 | 20 | Androscoggin | ME | 2021-11-01 | 2021-10-01 | 2020-08-25 | 34.5 kV line from Gulf island to Crowleys substation. 102159-97000-101460 | CNR | FALSE | FALSE |  | PD | ME
| 1026 | 2020-06-23 17:10 | G | 2020-05-08 | Solar | PV | SUN | 90 | 90 | 90 | Oxford | ME | 2021-11-22 | 2021-10-25 | 2020-06-23 | CMP Rumford substation 115 kV | NR | FALSE | FALSE |  | PD | ME
| 1027 | 2022-09-13 09:49 | G | 2020-05-14 | Solar + Battery Storage | OT | SUN BAT | 2 | 2 | 2 | Berkshire | MA | 2022-12-15 | 2022-12-01 | 2022-09-13 | National Grid, 13.8kV, DISTRIBUTION CIRCUIT #09-1102W1 | CNR | TRUE | TRUE | ISO-NE |  | WMA |  |  |  |  | In Progress
| 1028 | 2024-03-06 13:34 | G | 2020-05-28 | Western Maine Wind Project | WT | WND | 58.8 | 58.8 | 58.8 | Somerset | ME | 2025-10-31 | 2025-04-29 |  | CMP 115 kV Section 222 - coordinates 45° 9'30.90"N, 69°51'1.40"W | NR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed
| 1029 | 2024-02-06 09:48 | G | 2020-05-29 | Solar | PV | SUN | 120 | 120 | 120 | Penobscot | ME | 2023-12-01 | 2023-10-02 | 2024-02-06 | Emera Maine 115 kV Line 97 BHE, (Passadumkeag to Graham) | NR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  | Document Posted | In Progress
| 1030 | 2025-08-19 14:27 | G | 2020-06-02 | Gravel Pit Solar Increase | PV | SUN | 45 | 120 | 120 | Hartford | CT | 2025-08-13 | 2024-10-28 |  | Line cut and three-breaker ring bus of the 115 kV Connecticut Light & Power Company line between Barbour Hill and Windsor Locks. | CNR | TRUE | TRUE | ISO-NE | PD | CT |  | Document Posted |  |  | Executed
| 1031 | 2022-10-19 15:48 | G | 2020-06-18 | Solar | PV | SUN | 40 | 40 | 40 | Hampshire | MA | 2023-10-01 | 2023-08-08 | 2022-10-19 | NATIONAL GRID 69 kV LINE F-6W, WARE - DEERFIELD Latitude: 42.287024° Longitude: -72.289276° | CNR | TRUE | FALSE | ISO-NE |  | WMA | Document Posted | Document Posted |  |  | In Progress | Under Study
| 1032 | 2025-06-16 14:44 | G | 2020-06-23 | Eversource Group @ Bell Rock #661 | OT | SUN BAT | 11.992 | 11.992 | 11.992 | Bristol | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Bell Rock #661 | NA | FALSE | FALSE |  |  | SEMA
| 1033 | 2025-06-16 14:45 | G | 2020-06-24 | Solar | PV | SUN | 6 | 6 | 6 | Ellington | CT | 2024-09-01 | 2024-08-01 | 2025-06-13 | Eversource Scitico #27H9 | NA | TRUE | TRUE | NU |  | CT
| 1034 | 2021-05-03 10:09 | G | 2020-06-29 | Solar | PV | SUN | 60 | 60 | 60 | Coos | NH | 2023-12-30 | 2023-11-30 | 2021-04-30 | Eversource Whitefield to Berlin 115 kV S136 line (44.36675, -71.52688) 4.3 miles from Whitefield Substation | CNR | FALSE | FALSE |  | PD | NH | Document Posted | Not Started
| 1035 | 2020-09-23 09:29 | G | 2020-06-29 | Solar | PV | SUN | 60 | 60 | 60 | Coos | NH | 2023-12-30 | 2023-11-30 | 2020-09-22 | Eversource Berlin to Lost Nation 115 kV Line W179; 44.564565, -71.19104; 9.69 miles from Berlin substation, 18.27 miles from Lost Nation substation | CNR | FALSE | FALSE |  | PD | NH
| 1036 | 2020-08-28 08:07 | G | 2020-07-20 | Solar plus battery storage | OT | SUN BAT | 85 | 85 | 85 | Carroll | NH | 2023-10-31 | 2023-10-02 | 2020-08-27 | 115 kV bus at Eversource's White Lake Substation in Tamworth, New Hampshire (43.848851, -71.2444465) | CNR | FALSE | FALSE |  | PD | NH
| 1037 | 2021-04-22 14:29 | G | 2020-08-04 | Battery Storage | OT | BAT | 700 | 700 | 700 | Suffolk | MA | 2024-06-01 | 2024-03-01 | 2021-04-22 | The Mystic 345 kV substation. | NR | FALSE | FALSE |  | PD | BOST | Document Posted | Not Started |  |  |  | Under Study
| 1038 | 2025-06-18 09:36 | G | 2020-08-07 | Solar | PV | SUN | 76.25 | 76.25 | 76.25 | Merrimack | NH | 2025-10-31 | 2025-10-05 | 2025-06-17 | 3-breaker ring bus tap of the existing Comerford - Dunbarton Tap 230 kV line. This line is owned by National Grid and has the designation of Line B202 N. Latitude/ Longitude : 43.268, -71.66 | CNR | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | Not Started
| 1039 | 2025-06-16 14:45 | G | 2020-08-19 | Warren Substation – NG RI-Warren-20-Comp-1 Study | PV | SUN | 6.93 | 6.93 | 6.93 | Kent | RI | 2024-08-02 | 2024-06-28 | 2025-06-13 | NG feeder 5F2, Warren Substation | NA | TRUE | TRUE | NGRID | PD | RI
| 1040 | 2025-06-16 14:46 | G | 2020-08-19 | Farnum Pike - NG WRI DG Area Study #2 >5 MW | PV | SUN | 8 | 8 | 8 | Providence | RI | 2022-12-29 | 2022-12-15 | 2025-06-13 | NG Drumrock sustation, feeder 23F3 | NA | TRUE | TRUE | NGRID | PD | RI
| 1041 | 2025-06-16 14:46 | G | 2020-08-19 | Kent County - NG WRI DG Area Study #2 >5 MW | PV | SUN | 49.75 | 49.75 | 49.75 | Kent | RI | 2025-07-07 | 2024-04-14 | 2025-06-13 | NG Kent County Substation, feeders 3309 and 3310 | NA | TRUE | TRUE | NGRID | PD | RI
| 1042 | 2024-10-08 15:49 | G | 2020-08-19 | Wood River - NG WRI DG Area Study #2 >5 MW | PV | SUN | 34.375 | 34.375 | 34.375 | Washington | RI | 2025-06-30 | 2025-06-15 | 2024-10-08 | NG Wood River Substation, feeder 85T2 | NA | TRUE | TRUE | NGRID | PD | RI
| 1043 | 2024-10-08 15:49 | G | 2020-08-19 | Chase Hill - NG WRI DG Area Study #2 <5 MW | PV | SUN | 7.325 | 7.325 | 7.325 | Washington | RI | 2025-06-30 | 2025-06-15 | 2024-10-08 | NG Chase Hillk substation | NA | TRUE | TRUE | NGRID | PD | RI
| 1044 | 2025-06-16 14:47 | G | 2020-08-19 | Drumrock - NG WRI DG Area Study #2 <5 MW | PV | SUN | 4.975 | 4.975 | 4.975 | Kent | RI | 2022-04-01 | 2022-03-15 | 2025-06-13 | NG Drumrock sustation, feeder 14F4 | NA | TRUE | TRUE | NGRID | PD | RI
| 1045 | 2025-06-16 14:48 | G | 2020-08-19 | Hopkins Hill - NG WRI DG Area Study #2 <5 MW | PV | SUN | 3.5 | 3.5 | 3.5 | Kent | RI | 2022-04-01 | 2022-03-15 | 2025-06-13 | NG Hopkins Hill substation, feeder 63F3 | NA | TRUE | TRUE | NGRID | PD | RI
| 1046 | 2025-06-16 14:48 | G | 2020-08-19 | Johnston - NG WRI DG Area Study #2 <5 MW | PV | SUN | 4.875 | 4.875 | 4.875 | Povidence | RI | 2022-04-01 | 2022-03-15 | 2025-06-13 | NG Johnston substation | NA | TRUE | TRUE | NGRID | PD | RI
| 1047 | 2025-06-16 14:49 | G | 2020-08-19 | Kent County - NG WRI DG Area Study #2 <5 MW | PV | SUN | 13.525 | 13.525 | 13.525 | Kent | RI | 2022-04-01 | 2022-03-15 | 2025-06-13 | NG Kent County Substation, feeders 3309, 22F1 and 3311 | NA | TRUE | TRUE | NGRID | PD | RI
| 1048 | 2021-09-15 12:28 | G | 2020-08-19 | New London - NG WRI DG Area Study #2 <5 MW | PV | SUN | 4.875 | 4.875 | 4.875 | Kent | RI | 2022-04-01 | 2022-03-15 | 2021-09-14 | NG New London substation, feeder 150F4 | NA | TRUE | TRUE | NGRID | PD | RI
| 1049 | 2021-09-15 12:29 | G | 2020-08-19 | Old Baptist Road - NG WRI DG Area Study #2 <5 MW | PV | SUN | 4 | 4 | 4 | Washington | RI | 2022-04-01 | 2022-03-15 | 2021-09-14 | NG Old Baptisst Road substation, feeder 46F3 | NA | TRUE | TRUE | NGRID | PD | RI
| 1050 | 2025-06-16 14:52 | G | 2020-08-19 | Putnam Pike - NG WRI DG Area Study #2 <5 MW | PV | SUN | 3 | 3 | 3 | Providence | RI | 2021-08-31 | 2021-08-15 | 2025-06-13 | NG Putnam Pike substation, feeder 38F3 | NA | FALSE | FALSE |  | PD | RI
| 1051 | 2024-10-08 15:50 | G | 2020-08-19 | Tower Hill - NG WRI DG Area Study #2 <5 MW | PV | SUN | 3.06 | 3.06 | 3.06 | Washington | RI | 2025-06-30 | 2025-06-15 | 2024-10-08 | NG Tower Hill substation, feeder 88F7 | NA | TRUE | TRUE | NGRID | PD | RI
| 1052 | 2021-09-15 12:23 | G | 2020-08-19 | West Cranston - NG WRI DG Area Study #2 <5 MW | PV | SUN | 1.56 | 1.56 | 1.56 | Washington | RI | 2022-04-01 | 2022-03-15 | 2021-09-14 | NG West Cranston substation, feeder 21F2 | NA | TRUE | TRUE | NGRID | PD | RI
| 1053 | 2021-09-15 12:24 | G | 2020-08-19 | Westerly - NG WRI DG Area Study #2 <5 MW | PV | SUN | 4.875 | 4.875 | 4.875 | Washington | RI | 2025-06-30 | 2025-06-15 | 2021-09-14 | NR Westerly substation, feeder 16F2 | NA | TRUE | TRUE | NGRID | PD | RI
| 1054 | 2024-10-08 15:51 | G | 2020-08-19 | Wood River - NG WRI DG Area Study #2 <5 MW | PV | SUN | 9.75 | 9.75 | 9.75 | Washington | RI | 2025-06-30 | 2025-06-15 | 2024-10-08 | NG Wood River Substation, feeder 85T2 | NA | TRUE | TRUE | NGRID | PD | RI
| 1055 | 2024-04-29 10:39 | G | 2020-08-26 | Fuel Cell | FC | NG | 14.4 | 14.4 | 14.4 | New Haven | CT | 2024-03-21 | 2023-10-12 |  | UI 13.8kV Indian Well Substation | NA | TRUE | TRUE | UI | PD | SWCT
| 1056 | 2021-03-04 08:05 | G | 2020-08-28 | Battery Storage | OT | BAT | 50 | 50 | 50 | New Haven | CT | 2022-06-01 | 2022-03-01 | 2021-03-03 | June Street substation | CNR | FALSE | FALSE |  |  | SWCT | Document Posted | Not Started |  |  |  | Under Study
| 1057 | 2021-04-22 14:30 | G | 2020-08-28 | Battery Storage | OT | BAT | 500 | 500 | 500 | Middlesex | MA | 2025-06-01 | 2025-03-01 | 2021-04-22 | Mystic 345 kV | NR | FALSE | FALSE |  | PD | BOST | Document Posted | Not Started |  |  |  | Under Study
| 1058 | 2025-10-08 08:49 | G | 2020-09-09 | Offshore Wind | WT | WND | 1200 | 1266.72 | 1266.72 | NA | CT | 2027-11-30 | 2027-03-31 | 2025-10-08 | Eversource (CL&P) Millstone 345 kV substation | CNR | TRUE | FALSE | ISO-NE | PD | CT | Document Posted | Document Posted
| 1059 | 2022-12-14 09:48 | G | 2020-09-09 | Offshore Wind | WT | WND | 1200 | 1278.9 | 1278.9 | NA | MA | 2027-11-30 | 2027-03-31 | 2022-12-13 | Eversource NSTAR Pilgrim 345 kV substation | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
| 1060 | 2025-10-08 08:49 | G | 2020-09-09 | Offshore Wind Increase | WT | WND | 0 | 1200 | 1200 | NA | CT | 2027-11-30 | 2027-03-31 | 2025-10-08 | Eversource (CL&P) Millstone 345 kV substation | CNR | FALSE | FALSE | ISO-NE | PD | CT | Document Posted
| 1061 | 2021-07-19 16:22 | G | 2020-09-10 | Solar | PV | SUN | 135 | 135 | 135 | Hartford | CT | 2022-10-31 | 2022-09-30 | 2021-07-19 | The project will connect at North East Simsbury Substation (115 kV), with an alternate POI at the North East Simsbury to North Bloomfield 115 kV line in close proximity to the N.E. Simsbury substation. | NR | FALSE | FALSE |  | PD | CT | Document Posted |  |  |  |  | Under Study
| 1062 | 2020-12-03 11:06 | G | 2020-09-10 | Battery Storage | OT | BAT | 100 | 100 | 100 | Fairfield | CT | 2023-06-01 | 2023-03-01 | 2020-12-03 | Baird substation | CNR | FALSE | FALSE |  | PD | SWCT
| 1063 | 2021-12-23 11:16 | G | 2020-09-15 | Syncarpha Blandford Solar plus battery storage | OT | SUN BAT | 4.99 | 9.998 | 9.998 | Berkshire | MA | 2021-12-14 | 2021-12-09 |  | Eversource 23 kv 19J2 | CNR | FALSE | FALSE |  |  | WMA |  | Document Posted |  |  | Executed | In Service
| 1064 | 2020-12-01 11:15 | G | 2020-09-17 | Solar | PV | SUN | 11.8 | 11.8 | 11.8 | Washington | ME | 2023-09-15 | 2023-08-20 | 2020-12-01 | Emera Maine 34.5 kV Line 19, connecting Scott’s Hill Substation and Pembroke Substation Latitude: 44.873 Longitude: -67.356 | CNR | FALSE | FALSE |  | PD | BHE
| 1065 | 2020-10-09 17:58 | G | 2020-09-25 | Solar | PV | SUN | 100 | 100 | 100 | Penobscot | ME | 2024-11-30 | 2024-11-30 | 2020-10-09 | BHE 115kV Line 97 | NR | FALSE | FALSE |  | PD | BHE
| 1066 | 2025-06-16 14:59 | G | 2020-10-02 | Augusta E. Side 115 kV SS - Augusta Area Study | PV | SUN | 2 | 2 | 2 | Kennebec | ME | 2024-03-01 | 2024-03-01 | 2025-06-13 | CMP AUGUSTA K5 Substation, Circuit 200D2 | NA | TRUE | TRUE | CMP | PD | ME
| 1067 | 2023-03-14 16:09 | G | 2020-10-02 | Augusta E. Side 115 kV SS - Augusta Area Study | OT | SUN BAT | 3.75 | 3.75 | 3.75 | Kennebec | ME | 2022-05-03 | 2022-05-03 |  | CMP BLAIR ROAD Substation, Circuit 207D2 | NA | TRUE | TRUE | CMP | PD | ME
| 1068 | 2025-06-16 14:59 | G | 2020-10-02 | Augusta E. Side 115 kV SS - Augusta Area Study | PV | SUN | 9.998 | 9.998 | 9.998 | Kennebec | ME | 2024-10-21 | 2024-10-21 | 2025-06-13 | CMP CONY ROAD Substation, Circuit 216D1 and 216D2 | NA | TRUE | TRUE | CMP | PD | ME
| 1069 | 2023-03-14 16:12 | G | 2020-10-02 | Augusta E. Side 115 kV SS - Augusta Area Study | PV | SUN | 4 | 4 | 4 | Kennebec | ME | 2022-03-25 | 2022-03-25 |  | CMP SIDNEY Substation, Circuit 242D1 | NA | TRUE | TRUE | CMP | PD | ME
| 1070 | 2023-03-14 16:13 | G | 2020-10-02 | Augusta E. Side 115 kV SS - Augusta Area Study | OT | SUN BAT | 4.25 | 4.25 | 4.25 | Kennebec | ME | 2022-12-13 | 2022-12-13 |  | CMP SOUTH CHINA Substation, Circuit 244D2 | NA | TRUE | TRUE | CMP | PD | ME
| 1071 | 2023-03-14 16:14 | G | 2020-10-02 | Bowman Street 115 kV SS - Augusta Area Study | OT | SUN BAT | 9.94 | 9.94 | 9.94 | Kennebec | ME | 2022-12-30 | 2022-09-30 |  | CMP BOWMAN STREET Substation, Circuit 263D1 | NA | TRUE | TRUE | CMP | PD | ME
| 1072 | 2025-06-16 15:00 | G | 2020-10-02 | Bowman Street 115 kV SS - Augusta Area Study | PV | SUN | 1.703 | 1.703 | 1.703 | Kennebec | ME | 2023-06-15 | 2023-06-15 | 2025-06-13 | CMP CAPITOL STREET Substation, Circuit 215D3 | NA | TRUE | TRUE | CMP | PD | ME
| 1073 | 2023-03-14 16:17 | G | 2020-10-02 | Bowman Street 115 kV SS - Augusta Area Study | PV | SUN | 3.25 | 3.25 | 3.25 | Kennebec | ME | 2022-06-28 | 2022-06-28 |  | CMP GARDINER Substation, Circuit 226D2 | NA | TRUE | TRUE | CMP |  | ME
| 1074 | 2023-04-18 10:58 | G | 2020-10-02 | Bowman Street 115 kV SS - Augusta Area Study | OT | SUN BAT | 9.475 | 9.475 | 9.475 | Kennebec | ME | 2023-03-28 | 2023-03-01 |  | CMP MANCHESTER Substation, Circuit 233D1 and 233D2 | NA | TRUE | TRUE | CMP | PD | ME
| 1075 | 2025-06-16 15:00 | G | 2020-10-02 | Bowman Street 115 kV SS - Augusta Area Study | PV | SUN | 1.75 | 1.75 | 1.75 | Sagadahoc | ME | 2023-09-12 | 2023-09-12 | 2025-06-13 | CMP RICHMOND Substation, Circuit 240D1 | NA | TRUE | TRUE | CMP | PD | ME
| 1076 | 2025-06-16 15:01 | G | 2020-10-02 | Bowman Street 115 kV SS - Augusta Area Study | OT | SUN BAT | 4.975 | 4.975 | 4.975 | Kennebec | ME | 2023-06-27 | 2023-06-27 | 2025-06-13 | CMP WEST STREET Substation, Circuit 255D1 | NA | TRUE | TRUE | CMP | PD | ME
| 1077 | 2025-06-16 15:01 | G | 2020-10-02 | Puddledock Road 115 kV SS - Augusta Area Study | PV | SUN | 4.875 | 4.875 | 4.875 | Kennebec | ME | 2024-01-04 | 2024-01-04 | 2025-06-13 | CMP BOND BROOK Substation, Circuit 208D1 | NA | TRUE | TRUE | CMP | PD | ME
| 1078 | 2025-06-16 15:26 | G | 2020-10-02 | Puddledock Road 115 kV SS - Augusta Area Study | PV | SUN | 4.95 | 4.95 | 4.95 | Kennebec | ME | 2023-05-16 | 2023-05-16 | 2025-06-13 | CMP PUDDLEDOCK ROAD Substation, Circuit 262D1 | NA | TRUE | TRUE | CMP |  | ME
| 1079 | 2025-06-16 15:04 | G | 2020-10-02 | Puddledock Road 115 kV SS - Augusta Area Study | PV | SUN | 2.5 | 2.5 | 2.5 | Kennebec | ME | 2023-05-23 | 2023-05-23 | 2025-06-13 | CMP WINTHROP Substation, Circuit 256D3 | NA | TRUE | TRUE | CMP | PD | ME
| 1080 | 2024-10-18 16:29 | G | 2020-10-08 | Solar | PV | SUN | 65 | 66.5 | 66.5 | Oxford | ME | 2024-10-24 | 2024-10-03 | 2024-10-18 | Ludden Lane 115 kV substation (Riley 115 kV line) | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  | Document Posted | In Progress
| 1081 | 2020-10-21 14:09 | G | 2020-10-09 | Solar | PV | SUN | 100 | 100 | 100 | Penobscot | ME | 2024-12-30 | 2024-11-30 | 2020-10-21 | BHE 115kV Line 97 | CNR | FALSE | FALSE |  | PD | BHE
| 1082 | 2021-05-07 15:50 | G | 2020-10-29 | Battery Storage | OT | BAT | 204 | 204 | 204 | Middlesex | MA | 2025-06-01 | 2025-02-01 | 2021-05-07 | Mystic 115kV | NR | FALSE | FALSE |  | PD | BOST | In Progress |  |  |  |  | Under Study
| 1083 | 2020-11-30 14:09 | G | 2020-10-29 | Battery Storage | OT | BAT | 200 | 204 | 204 | Middlesex | MA | 2023-12-01 | 2023-10-01 | 2020-11-30 | Mystic 115kV | NR | FALSE | FALSE |  | PD | BOST
| 1084 | 2021-02-08 14:50 | G | 2020-11-04 | Battery Storage | OT | BAT | 102 | 102 | 102 | Kennebec | ME | 2023-12-01 | 2023-09-01 | 2021-01-27 | Bowman st 115kV | CNR | FALSE | FALSE |  | PD | ME
| 1085 | 2021-01-21 17:48 | G | 2020-11-17 | Solar | PV | SUN | 100 | 100 | 100 | Penobscot | ME | 2024-12-30 | 2024-11-30 | 2021-01-21 | BHE 115kV Line 64 | CNR | FALSE | FALSE |  | PD | BHE
| 1086 | 2025-10-24 15:18 | G | 2020-11-30 | Warren Meadow Solar | PV | SUN | 74.5 | 74.5 | 74.5 | Knox | ME | 2026-11-30 | 2026-10-31 |  | CMP 115kV line Section 80 | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 1087 | 2024-08-12 12:45 | G | 2020-12-17 | SolarFairfield | PV | SUN | 18.14 | 18.14 | 18.14 | Somerset | ME | 2027-06-30 | 2027-01-01 |  | New Rice Rips 34.5 kV Substation in Oakland Maine | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 1088 | 2023-03-09 15:05 | G | 2020-12-07 | Solar | PV | SUN | 27 | 27 | 27 | Grafton | NH | 2022-06-01 | 2022-05-01 | 2023-03-09 | Littleton W&L Section 30 34.5 kv line or 12.47 kv distrivution line | NA | FALSE | FALSE |  |  | NH
| 1089 | 2023-10-20 12:54 | G | 2021-01-08 | Naugatuck Avenue Battery Storage | OT | BAT | 205.32 | 205.32 | 205.32 | New Haven | CT | 2027-05-31 | 2027-04-15 |  | Devon 115 kV open position between 4T and 5T | NR | TRUE | TRUE | ISO-NE | PD | SWCT | Document Posted | Document Posted |  |  | Executed
| 1091 | 2021-11-01 08:28 | G | 2021-01-14 | Battery Storage | OT | BAT | 50.4 | 50.4 | 50.4 | Providence | RI | 2022-05-02 | 2022-05-02 | 2021-11-01 | The proposed POI is off the 115kV H17 transmission line owned by NEP via a spare buss position located in the Iron Mine HIll Substation owned by NEC. | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
| 1092 | 2025-06-16 15:05 | G | 2021-01-20 | Solar | PV | SUN | 26 | 26 | 26 | Hartford | CT | 2024-09-01 | 2024-08-01 | 2025-06-13 | Eversource North Bloomfield 2A | NA | FALSE | FALSE |  |  | CT
| 1093 | 2023-12-12 09:03 | ETU | 2021-02-05 | NB TA#1365950 HVDC | OT | N/A | 0 | 0 | 0 | Salisbury, New Brunswick | NB | 2030-01-01 | 2030-01-01 | 2023-12-12 | Salisbury, New Brunswick | N/A | FALSE | FALSE |  | NA | N/A
| 1094 | 2025-06-16 15:06 | G | 2021-02-04 | CMP County Road 115 kV SS - Winslow-Lakewood Areas Study | OT | SUN BAT | 7.8 | 7.8 | 7.8 | Kennebec | ME | 2024-04-30 | 2024-04-30 | 2025-06-13 | CMP County Road 115 kV SS | NA | TRUE | TRUE | CMP | PD | ME
| 1095 | 2025-06-16 15:08 | G | 2021-02-04 | CMP Lakewood 115 kV SS - Winslow-Lakewood Areas Study | PV | SUN | 28.72 | 28.72 | 28.72 | Somerset | ME | 2024-04-30 | 2024-04-30 | 2025-06-13 | CMP Lakewood 115 kV SS | NA | TRUE | TRUE | CMP | PD | ME
| 1096 | 2025-06-16 15:08 | G | 2021-02-04 | CMP Winslow 115 kV SS - Winslow-Lakewood Areas Study | OT | SUN BAT | 18.728 | 18.728 | 18.728 | Somerset/Kennebec | ME | 2024-04-30 | 2024-04-30 | 2025-06-13 | CMP Winslow 115 kV SS | NA | TRUE | TRUE | CMP | PD | ME
| 1097 | 2025-10-17 13:38 | G | 2021-02-15 | Green Apple Solar | PV | SUN | 178.59 | 178.59 | 178.59 | Androscoggin | ME | 2027-11-01 | 2027-05-15 |  | 44.172365, -70.104225 CMP 115kv Line 212 | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  | Document Posted | Executed
| 1098 | 2024-04-01 08:55 | G | 2021-02-19 | Solar | PV | SUN | 51.4 | 51.4 | 51.4 | Hancock | ME | 2024-12-31 | 2024-12-15 | 2024-04-01 | 34.5 kV bus at Versant Power Trenton substation at 44°26'19.81"N, 68°22'29.11"W | CNR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  |  | Not Started
| 1099 | 2022-12-15 11:44 | G | 2021-02-19 | Solar | PV | SUN | 31.4 | 31.4 | 31.4 | Knox | ME | 2024-12-31 | 2024-12-15 | 2022-12-15 | Central Maine Power 34.5 kV Line Section 51A (S51A Tap – Highland) @ 44°07'59.3"N, 69°11'43.5"W | CNR | TRUE | FALSE | ISO-NE | PD | ME | Document Posted | In Progress |  |  |  | Under Study
| 1100 | 2025-10-07 14:53 | G | 2021-02-19 | Solar | PV | SUN | 164.56 | 143.3 | 143.3 | Somerset | ME | 2029-11-29 | 2029-02-08 |  | The proposed POI is on Central Maine Power 115 kV line Section 82 (Athens – Hartland), approximately 7.5 circuit miles to Athens Substation and approximately 4.3 circuit miles to Hartland station. Approximate POI coordinates: 44.8759° N, 69.5423° W | NR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed
| 1101 | 2025-05-19 06:13 | ETU | 2021-02-26 | Objective ETU - upgrade alternative | NA | N/A |  |  |  | NA | NH | 2025-09-14 | 2025-09-14 | 2025-05-16 | N/A | N/A | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | In Progress
| 1102 | 2021-11-26 10:39 | G | 2021-03-01 | Battery Storage | OT | BAT | 200 | 200 | 200 | Kent | RI | 2023-03-01 | 2023-03-01 | 2021-11-26 | NEC 115 kV G-185S-2 | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
| 1103 | 2024-01-02 14:12 | G | 2021-03-10 | Berlin Energy Uprate and Battery Addition | OT | WAT BAT | 15 | 44.2 | 44.2 | Coos | NH | 2023-12-19 | 2023-09-25 |  | 22kV bus at Brookfield owned Goebel St Substation connected to the Eversource Berlin 115kV substation. | CNR | TRUE | TRUE | ISO-NE | PD | NH |  | Document Posted |  |  | Executed | In Service
| 1104 | 2023-04-20 12:40 | G | 2021-03-11 | Bonny Eagle Energy Storage - Uprate | OT | WAT BAT | 8 | 25.5 | 25.5 | York | ME | 2023-04-20 | 2023-03-13 |  | The battery will connect to Brookfield owned 34.5kV bus inside the Bonny Eagle Power station. The Bonny Eagle Power Station 34.5kV bus ties in to the CMP owned Bonny Eagle substation. | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 1105 | 2021-10-21 11:29 | G | 2021-03-15 | Battery Storage | OT | BAT | 104.5 | 104.5 | 104.5 | Worcester | MA | 2025-05-15 | 2025-02-15 | 2021-10-20 | National Grid 115 kV Paxton Line A127-4 | CNR | FALSE | FALSE |  |  | CMA | Document Posted | Not Started |  |  |  | Under Study
| 1106 | 2021-04-23 08:38 | G | 2021-03-15 | Battery Storage | OT | BAT | 55.05 | 55.05 | 55.05 | Franklin | MA | 2025-05-15 | 2025-02-15 | 2021-04-22 | Eversource 115 kv Ashfield substation | CNR | FALSE | FALSE |  |  | WMA
| 1107 | 2025-01-08 16:48 | G | 2021-03-16 | Battery Storage | OT | BAT | 189 | 182.23 | 182.23 | Plymouth | MA | 2027-05-14 | 2027-02-14 | 2025-01-08 | Eversource (NSTAR - South) 115 kV Wareham Line 108 | CNR | TRUE | FALSE |  | PD | SEMA | Document Posted | Document Posted |  |  | Not Started
| 1108 | 2024-11-15 08:53 | G | 2021-03-16 | Battery Storage | OT | BAT | 188.96 | 188.96 | 188.96 | Plymouth | MA | 2027-05-14 | 2027-02-12 | 2024-11-15 | Eversource (NSTAR - South) 115 kV Line 116, 0.31 miles from Brook St 115 kV substation and 4.55 miles from Carver 115 kV substation | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
| 1109 | 2025-10-17 13:45 | G | 2021-03-17 | Offshore Wind Inc. (Q806) | WT | WND | 487 | 1314 | 1314 | NA | MA | 2032-12-31 | 2032-05-01 |  | Eversource 345kV West Barnstable (921) | NR | TRUE | TRUE | ISO-NE | PD | SEMA |  | Document Posted |  | In Progress |  | Under Study
| 1110 | 2023-10-25 08:54 | G | 2021-03-18 | Norman Street Battery Storage | OT | BAT | 204 | 204 | 204 | Middlesex | MA | 2028-03-18 | 2028-02-15 |  | Mystic 115kV | CNR | TRUE | TRUE | ISO-NE | PD | BOST | Document Posted | Document Posted |  |  | Executed
| 1111 | 2023-09-21 17:44 | G | 2021-03-22 | Battery Storage | OT | BAT | 20 | 20 | 20 | Norfolk | MA | 2026-03-01 | 2026-02-15 | 2023-09-21 | Ever Source 115kV Ring Station 150 (@ spare bay in breaker and-a-half switchyard) | CNR | TRUE | TRUE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  |  | Not Started
| 1112 | 2024-07-03 15:02 | G | 2021-03-24 | Battery Storage | OT | BAT | 105 | 105 | 105 | Franklin | MA | 2029-12-30 | 2029-07-09 | 2024-07-03 | 115 kV B128 line; 18.88 miles from Barre B128 and 5.3 miles from French King | NR | TRUE | TRUE | ISO-NE | PD | WMA | Document Posted | Document Posted |  | Document Posted | In Progress
| 1113 | 2023-05-05 15:22 | G | 2021-03-24 | Rumford Uprate and Battery addition | OT | WAT BAT | 8.5 | 52.5 | 52.5 | Oxford | ME | 2023-05-05 | 2023-03-24 |  | 11.5kV bus at Brookfield owned existing Rumford Falls Substation which is connected to the CMP 115kV 218 Line. | CNR | TRUE | FALSE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 1114 | 2021-04-21 09:12 | G | 2021-04-01 | Solar | PV | SUN | 103 | 103 | 103 | Somerset | ME | 2024-01-31 | 2023-11-30 | 2021-04-20 | New Substation Tapping CMP 115 kV Circuit, Section 241 | CNR | FALSE | FALSE |  | PD | ME
| 1115 | 2023-09-15 08:43 | G | 2021-04-08 | Hecate Energy Eastern Ave Energy Center | OT | BAT | 250 | 250 | 250 | Suffolk | MA | 2026-11-09 | 2026-09-14 |  | Sta 488 Chelsea 115 kV substation | CNR | TRUE | TRUE | ISO-NE | PD | BOST | Document Posted | Document Posted |  |  | Executed
| 1117 | 2025-04-28 14:43 | G | 2021-04-15 | Streamfield | OT | BAT | 202.4 | 202.4 | 202.4 | Hampden | MA | 2027-05-31 | 2027-04-15 | 2025-04-28 | The proposed POI is Buck Pond 115 kV substation, the alternative POI is to build a new substation next to Buck pond 115 kV in the north side by breaking Line 1657 | CNR | TRUE | TRUE | ISO-NE |  | WMA | Document Posted | Document Posted |  |  | Executed
| 1118 | 2024-02-13 08:50 | G | 2021-04-15 | Offshore wind Increase (QP909) | WT | WND | 386 | 1200 | 1200 | NA | MA | 2027-09-30 | 2027-03-31 | 2024-02-13 | National Grid 115kV Bell Rock, | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
| 1119 | 2022-04-25 16:29 | G | 2021-04-14 | Offshore wind | WT | WND | 1320 | 1320 | 1320 | NA | MA | 2027-09-01 | 2027-03-01 | 2022-04-25 | Primary National Grid Brayton Point 345kV, Alt Kent County 345 kV | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted |  |  |  |  | Under Study
| 1120 | 2022-04-22 13:27 | G | 2021-04-14 | Battery Storage | OT | BAT | 204.64 | 204.64 | 204.64 | Windham | CT | 2025-05-01 | 2025-02-15 | 2022-04-22 | Eversource Killingly 345kV Substation | NR | TRUE | FALSE | ISO-NE | PD | CT |  | Document Posted |  |  | In Progress | Under Study
| 1121 | 2025-10-17 15:01 | G | 2021-04-19 | Offshore wind | WT | WND | 1200 | 1200 | 1200 | NA | MA | 2033-05-31 | 2032-12-01 | 2025-10-11 | Brayton Point 345 kV | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted
| 1122 | 2021-06-16 13:46 | G | 2021-04-19 | Battery Storage | OT | BAT | 20 | 20 | 20 | Addison | VT | 2022-12-31 | 2022-08-31 | 2021-06-16 | VELCO Middlebury Substation @ 46kV bus | CNR | FALSE | FALSE |  |  | VT
| 1124 | 2023-06-26 08:46 | G | 2021-04-21 | Battery Storage | OT | BAT | 107.5 | 107.5 | 107.5 | Hampden | MA | 2025-01-01 | 2024-10-01 | 2023-06-26 | Eversource 345kV Ludlow substation via the 115kV Stony Brook Substation | CNR | FALSE | FALSE |  |  | WMA | Document Posted | In Progress |  |  |  | Under Study
| 1125 | 2023-09-28 15:43 | G | 2021-04-21 | Solar | PV | SUN | 72 | 72 | 72 | Somerset | ME | 2024-01-31 | 2023-12-01 | 2023-09-28 | 44°36'30.65"N 69°38'23.26"W. CMP Line 241, new substation on 115kV line between Heywood Road Substation and County Road Substation. | CNR | FALSE | FALSE |  | PD | ME | Document Posted | In Progress |  |  |  | Under Study
| 1126 | 2022-09-16 13:47 | G | 2021-04-21 | Solar + Battery Storage | OT | SUN BAT | 4 | 4 | 4 | Barnstable | MA | 2022-02-28 | 2022-02-17 | 2022-09-16 | Eversource West 22.8kV CKT #4-77-450 (POLE#429/8) | CNR | FALSE | FALSE |  |  | SEMA |  | Document Posted |  |  | In Progress | Under Study
| 1127 | 2022-09-16 13:48 | G | 2021-04-21 | Solar + Battery Storage | OT | SUN BAT | 0.999 | 0.999 | 0.999 | Barnstable | MA | 2022-02-28 | 2022-02-17 | 2022-09-16 | Eversource East 22.8kV CKT #4-77-450 (Pole# 429/5) | NR | FALSE | FALSE |  |  | SEMA |  | Document Posted |  |  | In Progress | Under Study
| 1128 | 2022-09-13 09:51 | G | 2021-04-21 | Solar + Battery Storage | OT | SUN BAT | 4.536 | 4.536 | 4.536 | Berkshire | MA | 2022-07-15 | 2022-07-08 | 2022-09-12 | Eversource 22.8Kv feeder 15E2 Name of substation = Partridge 15E substation | CNR | FALSE | FALSE |  | PD | WMA |  | Document Posted |  |  | In Progress | Under Study
| 1129 | 2022-10-04 12:23 | G | 2021-04-22 | Solar + Battery Storage | OT | SUN BAT | 2.456 | 2.456 | 2.456 | Bristol | MA | 2021-12-31 | 2021-10-31 | 2022-10-04 | The primary connection of the proposed project to Eversource Energy is located at the Wing Lane substation #624 Transformer #1 Line #240. The site is located approximately 0.26 circuit miles from Substation 624 near PSS/E node 111293(Wing Lane 13.2 KV) | CNR | FALSE | FALSE |  |  | SEMA |  | Document Posted |  |  | Not Started
| 1130 | 2022-09-14 10:51 | G | 2021-04-23 | Solar + Battery Storage | OT | SUN BAT | 2 | 2 | 2 | Franklin | MA | 2022-04-30 | 2022-04-30 | 2022-09-14 | Eversource 13.8kV 22B3 feeder | CNR | FALSE | FALSE |  |  | WMA |  | Document Posted |  |  | Not Started | Under Study
| 1131 | 2022-09-21 08:31 | G | 2021-04-23 | Solar + Battery Storage | OT | SUN BAT | 4.95 | 9.9 | 9.9 | Barnstable | MA | 2021-12-31 | 2021-12-31 | 2022-09-20 | Falmouth Station #933 Line #98 Pole# 9105/16 | CNR | TRUE | FALSE | ISO-NE |  | SEMA |  | Document Posted |  |  |  | Under Study
| 1132 | 2022-09-14 10:52 | G | 2021-04-23 | Solar + Battery Storage | OT | SUN BAT | 3 | 3 | 3 | Hampshire | MA | 2021-12-28 | 2021-12-28 | 2022-09-14 | 13.2 Kv, Circuit #527L1, POI Pole# 52/42-2-3-1 | CNR | FALSE | FALSE |  |  | WMA |  | In Progress |  |  |  | Under Study
| 1133 | 2024-09-10 11:29 | G | 2021-04-27 | Stored Solar Fitchburg CNR Only | ST | WDS | 0 | 17 | 17 | Worcester | MA | 2024-08-08 | 2024-08-08 |  | Flagg Pond 69kv | CNR | FALSE | FALSE |  |  | CMA |  |  |  |  | Executed
| 1134 | 2025-06-16 15:11 | G | 2021-05-06 | Noresco Navy | IC | NG | 10.8 | 10.8 | 10.8 | New London | CT | 2023-04-15 | 2023-03-01 | 2025-06-13 | GU 323 | NA | TRUE | FALSE |  |  | CT
| 1135 | 2023-02-02 14:30 | G | 2021-05-13 | Solar + Battery Storage | OT | SUN BAT | 113.01 | 113.01 | 113.01 | Coos | NH | 2025-05-15 | 2025-02-15 | 2023-02-02 | Eversource W179-1 115 kV Line between Berlin and Pontook Hydro Substations, 11.5 miles from the Berlin Substation | CNR | FALSE | FALSE |  | PD | NH | Document Posted | In Progress |  |  |  | Under Study
| 1136 | 2025-01-22 13:58 | G | 2021-05-20 | Nutes Solar | PV | SUN | 20 | 20 | 20 | Strafford | NH | 2026-05-15 | 2026-04-15 |  | 43°23'7.50"N, 71° 1'23.45"W, Direct Tap, Circuit #3174 34.5 kV | CNR | TRUE | TRUE | ISO-NE | NA | NH | Document Posted | Document Posted |  |  | Executed
| 1137 | 2025-06-16 15:14 | G | 2021-05-25 | Nasonville Substation – NG RI-Nasonville-21-Comp-1 Study | PV | SUN | 9.5 | 9.5 | 9.5 | Providence | RI | 2023-03-15 | 2023-03-15 | 2025-06-13 | NG feeder 127W43, Nasonville Substation | NA | FALSE | FALSE |  | PD | RI
| 1138 | 2025-10-17 13:48 | G | 2021-06-03 | Husky Solar | PV | SUN | 50.159 | 50.159 | 50.159 | Windham | CT | 2029-05-10 | 2029-05-01 |  | The POI will be located about 6.9 miles from the 1607/1505 line ROW (Exeter Tap) and about 1.1 miles from the Exeter Sub 54N along the 115 kV underground line to the Exeter Sub 54N. | NR | TRUE | TRUE | ISO-NE | PD | CT | Document Posted | Document Posted | Not Required | Not Required | Executed
| 1139 | 2025-10-24 15:22 | G | 2021-06-04 | Turner Meadow Solar | PV | SUN | 20 | 20 | 20 | Androscoggin | ME | 2026-11-20 | 2026-11-15 |  | CMP 34.5kV Line 50 | NR | TRUE | TRUE | ISO-NE | NA | ME |  | Document Posted |  |  | Executed
| 1140 | 2022-01-11 15:10 | TS | 2021-06-03 | Regional Network Service Request | NA | N/A | 395 | 395 | 316 | Hampden | MA | 2023-10-01 | 2023-10-01 | 2022-01-11 | Eversource 115 kV Lines 1293 & 1302 | N/A | FALSE | FALSE |  | NA | WMA
| 1141 | 2021-09-03 11:20 | ETU | 2021-06-07 | 1200 MW DC Bidirectional Transmission line | NA | N/A |  |  |  | Suffolk/Barnstable | MA | 2027-09-30 | 2027-07-31 | 2021-09-02 | Mystic 345 kV Substation associated terminals Everett, MA Bourne 345 kV Substation associated terminals Sandwich, MA |  | FALSE | FALSE |  | NA | BOST
| 1142 | 2022-12-19 09:18 | ETU | 2021-06-07 | 1200 MW DC Bidirectional Transmission line | NA | N/A |  |  |  | Suffolk/Barnstable | MA | 2027-09-30 | 2027-07-31 | 2022-12-19 | K Street 345 kV Substation associated terminals Boston, MA Bourne 345 kV Substation associated terminals Sandwich, MA | N/A | FALSE | FALSE |  | NA | BOST
| 1143 | 2024-04-11 11:53 | G | 2021-06-15 | Battery Storage | OT | BAT | 508.248 | 508.248 | 508.248 | Middlesex | MA | 2028-05-31 | 2027-12-01 |  | Mystic 345 kV between breaker 101, 106 and 107 | CNR | TRUE | TRUE | ISO-NE | NA | BOST | Document Posted | Document Posted |  |  | Executed
| 1144 | 2021-10-27 10:27 | G | 2021-06-17 | Solar | OT | SUN BAT | 1 | 1 | 1 | Dukes | MA | 2022-11-01 | 2022-10-01 | 2021-10-26 | Eversource 23 kV Line 4-99-99 | CNR | FALSE | FALSE |  |  | SEMA
| 1145 | 2025-05-21 13:11 | G | 2021-07-07 | Solar | PV | SUN | 20.7 | 20.7 | 20.7 | Hancock | ME | 2024-07-08 | 2024-06-24 | 2025-05-21 | Versant 115 kV Trenton substation bus; Alternate POI - Versant 115kV Line 57 | CNR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  |  | In Progress
| 1146 | 2024-11-12 17:11 | G | 2021-07-07 | Swain Solar | PV | SUN | 40.355 | 40.91 | 40.91 | Oxford | ME | 2027-07-09 | 2027-06-25 | 2024-10-30 | CMP 115kV Line 270 | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 1147 | 2021-07-12 10:51 | G | 2021-07-08 | Solar | PV | SUN | 20 | 20 | 20 | Rensselaer | NY | 2022-12-30 | 2022-11-30 |  | National Grid’s North Troy – Hoosick 115kV Line #5 | NA | FALSE | FALSE |  | PD | N/A
| 1149 | 2025-10-21 12:49 | G | 2021-08-06 | Battery addition | OT | WAT BAT | 6.7 |  |  | Franklin | MA | 2027-03-19 | 2027-02-05 |  | National Grid's PTF (E-5B, F-6 West PTF transmission lines) | NR | TRUE | FALSE |  |  | WMA | Document Posted | Document Posted |  |  | Executed
| 1150 | 2023-05-22 13:35 | G | 2021-07-29 | Offshore Wind | WT | WND | 11.55 | 11.55 | 11.55 | NA | ME | 2023-09-01 | 2023-08-01 | 2023-05-22 | CMP Boothbay Harbor 34.5kV substation | CNR | FALSE | FALSE |  |  | ME |  | In Progress |  |  |  | Under Study
| 1151 | 2025-10-17 13:56 | G | 2021-08-04 | 13665 Felt Road Solar | OT | SUN BAT | 1.968 |  |  | Oxford | ME | 2024-12-03 | 2024-12-03 |  | CMP 34.5 kV Feeder 452K1, Woodstock Substation | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
| 1152 | 2022-09-08 10:21 | G | 2021-08-04 | Solar + Battery Storage | OT | SUN BAT | 9.998 | 9.998 | 9.998 | Hampshire | MA | 2022-09-01 | 2022-09-01 | 2022-09-08 | National Grid 13.8 kV 909W4 | CNR | FALSE | FALSE |  |  | WMA |  | Document Posted |  |  | Not Started
| 1153 | 2022-09-28 11:50 | G | 2021-08-11 | Offshore wind | WT | WND | 440 | 440 | 440 | NA | MA | 2026-11-01 | 2026-09-01 | 2022-09-28 | Eversource 115kV Acushnet, lines 112/114, Alternative Eversource Pine Street 115kV | CNR | FALSE | FALSE |  | PD | SEMA | In Progress |  |  |  |  | Under Study
| 1154 | 2025-10-17 13:58 | G | 2021-08-13 | Offshore wind Inc (QP700) | WT | WND | 18 | 856.2 | 856.2 | NA | MA | 2026-10-30 | 2026-03-14 |  | Eversource 345kV West Barnstable (921) | NR | TRUE | TRUE | ISO-NE | PD | SEMA |  | Document Posted |  | In Progress |  | Under Study
| 1155 | 2021-09-21 12:10 | G | 2021-08-16 | Solar | PV | SUN | 101.09 | 101.09 | 101.09 | Hartford | CT | 2024-10-15 | 2024-09-15 | 2021-09-21 | N. Bloomfield to Agawam 345kV Line. POI is approximately 3.6 mi north of N. Bloomfield (345kV) and 11.5 mi south of Agawam (345kV). | CNR | FALSE | FALSE |  | PD | CT
| 1156 | 2021-09-21 12:10 | G | 2021-08-16 | Solar | PV | SUN | 101.164 | 101.164 | 101.164 | Hartford | CT | 2024-10-15 | 2024-09-15 | 2021-09-21 | N. Bloomfield to NE Simsbury 115kV Line. POI is 200 feet east of the NE Simsbury Substation(115kV) and 2.25 miles west of N.Bloomfield(115kV). | CNR | FALSE | FALSE |  | PD | CT
| 1157 | 2022-12-19 09:18 | ETU | 2021-08-19 | 1200 MW DC Transmission Line | NA | N/A | 1200 |  |  |  | MA | 2028-05-31 | 2028-02-29 | 2022-12-19 | Mystic 345 kV Substation | N/A | FALSE | FALSE |  |  | BOST | Not Started |  |  |  |  | Under Study
| 1158 | 2023-06-21 16:46 | ETU | 2021-08-19 | 1200 MW DC Transmission Line | NA | N/A | 1200 |  |  |  | MA | 2028-05-31 | 2028-02-29 | 2023-06-21 | Mystic 345 kV Substation | N/A | FALSE | FALSE |  |  | BOST | In Progress |  |  |  |  | Under Study
| 1159 | 2023-08-18 16:10 | G | 2021-08-27 | Battery Storage | OT | BAT | 276 | 276 | 276 | Suffolk | MA | 2023-12-30 | 2023-12-05 | 2023-08-18 | Primary POI - Mystic 115 kV Station, Alternative POI - Mystic 345 kV Station | NR | FALSE | FALSE |  | PD | BOST | In Progress |  |  |  |  | Under Study
| 1160 | 2022-09-13 09:52 | G | 2021-08-31 | Solar plus Battery | OT | SUN BAT | 4.536 | 4.536 | 4.536 | Berkshire | MA | 2022-07-01 | 2022-06-15 | 2022-09-12 | Eversource 22.8Kv feeder 15E1 Name of the substation = Partridge 15E substation | CNR | TRUE | FALSE | ISO-NE | PD | WMA | Not Required | Document Posted |  |  |  | Under Study
| 1161 | 2022-09-13 09:53 | G | 2021-09-08 | Solar plus Battery | OT | SUN BAT | 3.6 | 3.6 | 3.6 | Berkshire | MA | 2022-07-01 | 2022-06-15 | 2022-09-12 | Eversource 22.8Kv feeder 15E1 Name of the substation = Partridge 15E substation | CNR | TRUE | FALSE | ISO-NE | PD | WMA | Not Required | Document Posted |  |  |  | Under Study
| 1162 | 2023-06-01 16:38 | G | 2021-09-21 | Solar with Battery | OT | SUN BAT | 87 | 95.6 | 95.6 | Windham | CT | 2023-12-31 | 2023-11-30 | 2023-06-01 | POI will be the three breaker ring bus at the 1607 Line. Approximate Coordinates 41.7119, -71.9379. | CNR | FALSE | FALSE |  | PD | CT | Document Posted | Not Started |  |  |  | Under Study
| 1163 | 2025-11-25 11:21 | G | 2021-09-22 | Battery Storage | OT | BAT | 205 | 201.43 | 201.43 | Washington | RI | 2029-12-07 | 2029-09-28 |  | RIE L190-2 (0.615 miles from Davisville and 1.935 miles from Old Baptist substations). | NR | TRUE | TRUE |  |  | RI | Document Posted | Document Posted |  |  | Executed
| 1164 | 2022-12-07 13:11 | G | 2021-09-23 | Solar | PV | SUN | 20 | 20 | 20 | Coos | NH | 2023-11-01 | 2023-11-01 | 2022-12-07 | Eversource 34.5 kV Line 384, Pole 4 | CNR | FALSE | FALSE |  | PD | NH | In Progress |  |  |  |  | Under Study
| 1165 | 2025-06-02 14:57 | G | 2021-10-22 | Solar | PV | SUN | 0.999 |  |  | Hancock | ME | 2023-07-15 | 2023-07-15 | 2025-06-02 | 34.5kV Line on Bar Harbor Road. The 34.5 kV line from Ellsworth to Trenton is not explicitly modeled in the power flow. We added a model for this line and then tapped it at tap 30% of the total line length from Trenton for the POI. | CNR | TRUE | TRUE | ISO-NE |  | BHE |  | Document Posted |  |  | In Progress
| 1166 | 2025-06-16 15:14 | G | 2021-10-04 | Battery Storage | OT | BAT | 20 | 20 | 20 | New Haven | CT | 2024-09-01 | 2024-08-01 | 2025-06-13 | Eversource Oxford 26N Substation | NA | FALSE | FALSE |  | PD | CT
| 1167 | 2023-01-31 10:35 | G | 2021-10-04 | Solar | PV | SUN | 4 | 4 | 4 | Windham | CT | 2023-01-31 | 2022-12-31 | 2023-01-30 | Eversource Tracy 14M substation circuit 14M9 | NA | TRUE | TRUE | NU | PD | CT
| 1168 | 2025-06-16 15:15 | G | 2021-10-04 | Fuel Cell | FC | NG | 8.7 | 8.7 | 8.7 | Hartford | CT | 2023-10-15 | 2023-10-01 | 2025-06-13 | Eversource Northwest Hartford 2N substation circuit 2N17 | NA | TRUE | TRUE | NU | PD | CT
| 1169 | 2023-10-11 10:23 | G | 2021-10-22 | Roxbury Solar | PV | SUN | 1.999 | 1.999 | 1.999 | Oxford | ME | 2026-12-15 | 2026-12-01 |  | CMP 12.47 kV distribution circuit 447D1 out of CMP Rumford Substation | NR | TRUE | TRUE | ISO-NE |  | ME |  | Document Posted |  |  | Executed
| 1170 | 2023-10-11 14:38 | G | 2021-10-22 | Battery Storage | OT | BAT | 100 | 100 | 100 | Franklin | MA | 2023-01-11 | 2022-12-14 | 2023-10-11 | National Grid's PTF (115kV Y-177 line), located at 42.730250 degrees north latitude, -72.931858 degrees west longitude. | CNR | FALSE | FALSE |  | PD | WMA | Document Posted |  |  |  |  | Under Study
| 1172 | 2024-10-02 14:39 | G | 2021-10-27 | Solar plus Battery | OT | SUN BAT | 53.07 | 53.07 | 53.07 | Merrimack | NH | 2025-07-31 | 2025-05-31 | 2024-10-02 | Eversource 115kV F139 line | CNR | TRUE | FALSE |  |  | NH | Document Posted | Document Posted |  |  | Not Started
| 1173 | 2025-06-16 15:16 | G | 2021-10-27 | Barre Substation - NG WMA Group 3 | OT | SUN BAT | 12.398 | 12.398 | 12.398 | Worcester | MA | 2027-12-31 | 2027-12-31 | 2025-06-13 | NG Barre Substation | NA | FALSE | FALSE |  | PD | WMA
| 1174 | 2025-06-16 15:16 | G | 2021-10-27 | Crystal Lake Substation - NG WMA Group 3 | OT | BAT | 7.998 | 7.998 | 7.998 | Worcester | MA | 2026-12-31 | 2026-12-31 | 2025-06-13 | NG Crystal Lake Substation | NA | FALSE | FALSE |  | PD | WMA
| 1175 | 2025-06-16 15:20 | G | 2021-10-27 | E. Westminster Substation - NG WMA Group 3 | OT | SUN BAT | 4.99 | 4.99 | 4.99 | Worcester | MA | 2026-12-31 | 2026-12-31 | 2025-06-13 | NG E. Westminster Substation | NA | FALSE | FALSE |  | PD | WMA
| 1176 | 2025-06-16 15:21 | G | 2021-10-27 | E. Winchendon Substation - NG WMA Group 3 | OT | SUN BAT | 34.975 | 34.975 | 34.975 | Worcester | MA | 2026-12-31 | 2026-12-31 | 2025-06-13 | NG E. Winchendon Substation | NA | FALSE | FALSE |  | PD | WMA
| 1177 | 2025-06-16 15:23 | G | 2021-10-27 | Lashaway Substation - NG WMA Group 3 | OT | BAT | 14.94 | 14.94 | 14.94 | Worcester | MA | 2027-12-31 | 2027-12-31 | 2025-06-13 | NG Lashaway Substation | NA | FALSE | FALSE |  | PD | WMA
| 1178 | 2025-06-16 15:27 | G | 2021-10-27 | Little Rest Rd Substation - NG WMA Group 3 | OT | SUN BAT | 5.8 | 5.8 | 5.8 | Worcester | MA | 2027-12-31 | 2027-12-31 | 2025-06-13 | NG Little Rest Rd Substation | NA | FALSE | FALSE |  | PD | WMA
| 1179 | 2025-06-16 15:27 | G | 2021-10-27 | Meadow Street 552 Substation - NG WMA Group 3 | OT | SUN BAT | 13.799 | 13.799 | 13.799 | Worcester | MA | 2027-12-31 | 2027-12-31 | 2025-06-13 | NG Meadow Street 552 Substation | NA | FALSE | FALSE |  | PD | WMA
| 1180 | 2025-06-16 15:30 | G | 2021-10-27 | Millbury Substation - NG WMA Group 3 | OT | SUN BAT | 11.742 | 11.742 | 11.742 | Worcester | MA | 2027-12-31 | 2027-12-31 | 2025-06-13 | NG Millbury Substation | NA | FALSE | FALSE |  | PD | WMA
| 1181 | 2025-06-16 15:31 | G | 2021-10-27 | N. Oxford Substation - NG WMA Group 3 | OT | SUN BAT | 20.396 | 20.396 | 20.396 | Worcester | MA | 2027-12-31 | 2027-12-31 | 2025-06-13 | NG N. Oxford Substation | NA | FALSE | FALSE |  | PD | WMA
| 1182 | 2025-06-16 15:31 | G | 2021-10-27 | Pratts Junc. Substation - NG WMA Group 3 | OT | BAT | 14.94 | 14.94 | 14.94 | Worcester | MA | 2027-12-31 | 2027-12-31 | 2025-06-13 | NG Pratts Junc. Substation | NA | FALSE | FALSE |  | PD | WMA
| 1183 | 2025-06-16 15:32 | G | 2021-10-27 | Royalston Substation - NG WMA Group 3 | OT | SUN BAT | 5 | 5 | 5 | Worcester | MA | 2027-12-31 | 2027-12-31 | 2025-06-13 | NG Royalston Substation | NA | FALSE | FALSE |  | PD | WMA
| 1184 | 2025-06-16 15:33 | G | 2021-10-27 | Snow St. Substation - NG WMA Group 3 | OT | SUN BAT | 27.836 | 27.836 | 27.836 | Worcester | MA | 2027-12-31 | 2027-12-31 | 2025-06-13 | NG Snow St. Substation | NA | FALSE | FALSE |  | PD | WMA
| 1185 | 2025-06-16 15:33 | G | 2021-10-27 | Stafford St. Substation - NG WMA Group 3 | OT | SUN BAT | 22.448 | 22.448 | 22.448 | Worcester | MA | 2027-12-31 | 2027-12-31 | 2025-06-13 | NG Stafford St. Substation | NA | FALSE | FALSE |  | PD | WMA
| 1186 | 2025-06-16 15:34 | G | 2021-10-27 | Treasure Valley Substation - NG WMA Group 3 | OT | BAT | 9.992 | 9.992 | 9.992 | Worcester | MA | 2027-12-31 | 2027-12-31 | 2025-06-13 | NG treasure Valley Substation | NA | FALSE | FALSE |  | PD | WMA
| 1187 | 2025-06-16 15:36 | G | 2021-10-27 | W. Charlton Substation - NG WMA Group 3 | OT | BAT | 19.984 | 19.984 | 19.984 | Worcester | MA | 2027-12-31 | 2027-12-31 | 2025-06-13 | NG W. Charlton Substation | NA | FALSE | FALSE |  | PD | WMA
| 1188 | 2025-06-16 15:37 | G | 2021-10-27 | Ware Substation - NG WMA Group 3 | OT | SUN BAT | 11 | 11 | 11 | Hampshire | MA | 2027-12-31 | 2027-12-31 | 2025-06-13 | NG Ware Substation | NA | FALSE | FALSE |  | PD | WMA
| 1189 | 2025-06-16 15:37 | G | 2021-10-27 | Wendall Depot Substation - NG WMA Group 3 | OT | SUN BAT | 27.981 | 27.981 | 27.981 | Franklin | MA | 2027-12-31 | 2027-12-31 | 2025-06-13 | NG Wendall Depot Substation | NA | FALSE | FALSE |  | PD | WMA
| 1190 | 2025-10-24 15:23 | G | 2021-10-28 | Solar Knox | PV | SUN | 33.5 | 33.5 | 33.5 | Knox | ME | 2027-03-31 | 2027-02-28 |  | CMP 115kV Line 80 | NR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed
| 1191 | 2021-11-09 13:11 | G | 2021-11-03 | Increase to Pumping load | PS | WAT | 0 | 333 | 333 | Berkshire | MA | 2021-11-03 | 2021-11-03 | 2021-11-09 | The current Bear Swamp interconnection points | NR | FALSE | FALSE |  |  | WMA
| 1192 | 2025-10-17 14:00 | G | 2021-11-04 | Broadleaf Solar | PV | SUN | 101.128 | 101.128 | 101.128 | Hartford | CT | 2027-10-15 | 2027-09-24 |  | N. Bloomfield to Agawam 345kV Line. POI is approximately 3.6 mi north of N. Bloomfield (345kV) and 11.5 mi south of Agawam (345kV). | NR | TRUE | TRUE | ISO-NE |  | CT | Document Posted | Document Posted |  |  | Executed
| 1193 | 2025-05-30 13:23 | G | 2021-11-09 | Battery Storage | OT | BAT | 325 | 325 | 325 | Windham | CT | 2028-05-12 | 2028-04-14 | 2025-05-30 | CL&P 345 kV 3271 Line | NR | TRUE | TRUE |  | PD | CT | Document Posted | Document Posted |  |  | In Progress
| 1194 | 2021-12-06 15:07 | G | 2021-11-09 | Bear Swamp Pumping Load Increase | PS | WAT | 0 | 333 | 333 | Berkshire | MA | 2021-11-09 | 2021-11-09 |  | The existing POI of the Bear Swamp generating station | NR | FALSE | FALSE |  |  | WMA |  |  |  |  | Executed
| 1195 | 2025-02-25 16:36 | TS | 2021-11-23 | Regional Network Service | NA | N/A | 6.3 | 6.3 | 6.3 | Middlesex | MA | 2024-11-20 | 2024-10-07 |  | NSTAR 115 kV Line 875-539 | N/A | TRUE | FALSE | ISO-NE |  | BOST
| 1196 | 2022-03-08 13:31 | G | 2021-12-14 | Energy Storage | OT | BAT | 99.9 | 99.9 | 99.9 | Hampden | MA | 2024-10-01 | 2024-08-01 | 2022-03-08 | National Grid Hampden Substation, 115 kV. Secondary is 115 kV Line 1976. | CNR | FALSE | FALSE |  | PD | WMA
| 1197 | 2025-10-17 15:01 | G | 2021-12-20 | Battery Storage | OT | BAT | 150 | 150 | 150 | Bristol | MA | 2027-12-31 | 2027-10-28 | 2025-10-11 | Eversource 115kV Cross Road Line 111 | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted
| 1198 | 2025-09-25 17:07 | G | 2021-12-30 | Storage | OT | BAT | 241.8 | 241.8 | 241.8 | Bristol | MA | 2028-05-12 | 2028-02-14 | 2025-09-25 | Looping the D-182S line adjacent to National Grid’s 115 kV Reynold’s Ave Substation | CNR | FALSE | FALSE |  |  | RI | Document Posted
| 1199 | 2025-06-16 15:38 | G | 2021-12-28 | USS Vineyard Solar, Somers Rd | PV | SUN | 4 | 4 | 4 | Tolland | CT | 2022-09-30 | 2022-09-30 | 2025-06-13 | Scitico 27H | NA | FALSE | FALSE |  | PD | CT
| 1200 | 2025-06-16 15:39 | G | 2021-12-28 | Verogy - Thrall Rd, East Windsor | OT | SUN | 4 | 4 | 4 | Hartford | CT | 2023-07-01 | 2023-07-01 | 2025-06-13 | Rockville 14W or Barbour Hill 23J | NA | FALSE | FALSE |  |  | CT
| 1201 | 2025-06-16 15:40 | G | 2021-12-28 | Verogy - Tripp RD | OT | SUN | 2 | 2 | 2 | Hartford | CT | 2023-07-01 | 2023-07-01 | 2025-06-13 | Rockville 14W | NA | FALSE | FALSE |  |  | CT
| 1202 | 2025-06-16 15:40 | G | 2021-12-28 | Community Power Group, 24 Middle Road, Ellington, CT | OT | SUN | 4 | 4 | 4 | Tolland | CT | 2023-07-01 | 2023-07-01 | 2025-06-13 | Rockville 14W | NA | FALSE | FALSE |  |  | CT
| 1203 | 2025-06-16 15:41 | G | 2021-12-28 | CTEC Solar 186 Foster St, South Windsor | OT | SUN | 1.875 | 1.875 | 1.875 | Hartford | CT | 2023-07-01 | 2023-07-01 | 2025-06-13 | Barbour Hill 23J | NA | FALSE | FALSE |  |  | CT
| 1204 | 2025-06-16 15:42 | G | 2021-12-28 | LSE Scorpuis | OT | SUN | 1.82 | 1.82 | 1.82 | Putnam | CT | 2023-12-31 | 2023-10-31 | 2025-06-13 | Tracy 14M | NA | TRUE | TRUE | NU |  | CT
| 1205 | 2025-06-16 15:43 | G | 2021-12-30 | Hamilton Sunstrand | OT | SUN | 2 | 2 | 2 | Hartford | CT | 2023-04-01 | 2023-04-01 | 2025-06-13 | Windsor Locks 14K | NA | TRUE | TRUE | NU |  | CT
| 1206 | 2022-03-08 12:44 | G | 2021-12-30 | Battery Storage | OT | BAT | 200 | 200 | 200 | Berkshire | MA | 2024-12-31 | 2024-12-01 | 2022-03-08 | MA_NGRID Adams 115kV substation Bus ID: 113005 | NR | FALSE | FALSE |  | PD | WMA
| 1207 | 2022-01-28 07:47 | G | 2021-12-30 | Battery Storage | OT | BAT | 200 | 200 | 200 | Barnstable | MA | 2024-12-31 | 2024-12-01 | 2022-01-28 | MA_NSTAR_CE Canal 115KV substation | NR | FALSE | FALSE |  | PD | SEMA
| 1208 | 2022-03-08 12:57 | G | 2021-12-30 | Battery Storage | OT | BAT | 160 | 160 | 160 | New Haven | CT | 2024-12-31 | 2024-12-01 | 2022-03-08 | CT_UI June Street 115KV substation/ Bus ID: 123416 | NR | FALSE | FALSE |  | PD | CT
| 1209 | 2022-03-08 12:42 | G | 2021-12-30 | Battery Storage | OT | BAT | 170 | 170 | 170 | Providence | RI | 2024-12-31 | 2024-12-01 | 2022-03-08 | RI_NGRID Hartford 115kV substation/ Bus ID: 117351 | NR | FALSE | FALSE |  | PD | RI
| 1210 | 2025-10-17 15:02 | G | 2022-01-07 | Wind | WT | WND | 500 | 572 | 572 | Aroostook | ME | 2025-11-28 | 2025-09-03 | 2025-10-11 | Orrington-Albion Rd 345kV line (3023) near the town of Pittsfield (approximately 19 miles from Albion Rd Substation) | CNR | FALSE | FALSE |  | PD | ME
| 1211 | 2025-10-17 15:05 | G | 2022-01-10 | Wind | WT | WND | 500 | 527 | 527 | Aroostook | ME | 2026-11-27 | 2026-09-03 | 2025-10-11 | Orrington-Albion Rd 345kV line (3023) near the town of Pittsfield (approximately 19 miles from Albion Rd Substation) | CNR | FALSE | FALSE |  | PD | ME
| 1212 | 2024-01-26 11:10 | G | 2022-01-14 | Hopkinton 126 - EMA ASO | OT | SUN BAT | 3.9 | 3.9 | 3.9 | Middlesex | MA | 2023-11-30 | 2023-09-30 | 2024-01-25 | Eversource Hopkinton 126 | NA | TRUE | FALSE | NU | PD | BOST
| 1213 | 2025-06-16 15:43 | G | 2022-01-14 | Holliston 130 - EMA ASO | OT | BAT | 4.99 | 4.99 | 4.99 | Middlesex | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Holliston 130 | NA | TRUE | FALSE | NU | PD | BOST
| 1214 | 2025-06-16 15:44 | G | 2022-01-14 | Group @ Medway 65 - EMA ASO | OT | SUN BAT | 17.497 | 17.497 | 17.497 | Middlesex/Norfolk | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Medway 65 | NA | TRUE | FALSE | NU | PD | BOST
| 1215 | 2025-06-16 15:45 | G | 2022-01-14 | Group @ Maynard 416 - EMA ASO | OT | SUN BAT | 8.476 | 8.476 | 8.476 | Middlesex | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Maynard 416 | NA | TRUE | FALSE | NU | PD | BOST
| 1216 | 2025-06-16 15:46 | G | 2022-01-14 | Group @ Podick - WMA ASO | OT | SUN BAT | 7.7 | 7.7 | 7.7 | Hampden/Franklin | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Podick | NA | FALSE | FALSE |  | PD | WMA
| 1217 | 2025-06-16 15:46 | G | 2022-01-14 | Oswald - WMA ASO | OT | SUN BAT | 2.49 | 2.49 | 2.49 | Franklin | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Oswald | NA | FALSE | FALSE |  | PD | WMA
| 1218 | 2025-06-16 15:47 | G | 2022-01-14 | Group @ Montigue - WMA ASO | OT | SUN BAT | 9.86 | 9.86 | 9.86 | Franklin | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Montigue | NA | TRUE | TRUE | NU | PD | WMA
| 1219 | 2025-06-16 15:48 | G | 2022-01-14 | Group @ French King - WMA ASO | OT | SUN BAT | 8.9 | 8.9 | 8.9 | Franklin/Hampshire | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource French King | NA | FALSE | FALSE |  | PD | WMA
| 1220 | 2025-06-16 15:48 | G | 2022-01-14 | Group @ Blandford 19J - WMA ASO | OT | SUN BAT | 6.99 | 6.99 | 6.99 | Berkshire | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Blandford 19J | NA | FALSE | FALSE |  | PD | WMA
| 1221 | 2025-06-16 15:49 | G | 2022-01-14 | Cumberland 22B - WMA ASO | OT | SUN BAT | 4.99 | 4.99 | 4.99 | Hampden | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Cumberland 22B | NA | FALSE | FALSE |  | PD | WMA
| 1222 | 2025-06-16 15:50 | G | 2022-01-14 | Group @ Berkshire 18C | OT | SUN BAT | 7.65 | 7.65 | 7.65 | Hampden | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Berkshire 18C | NA | FALSE | FALSE |  | PD | WMA
| 1223 | 2022-03-15 15:52 | G | 2022-01-18 | Battery Storage | OT | BAT | 9.99 | 9.99 | 9.992 | Worcester | MA | 2022-04-29 | 2022-03-31 | 2022-03-15 | ZP Battery DevCo, LLC, 13.2kV, National Grid Feeder #413L3 | CNR | FALSE | FALSE |  |  | CMA
| 1224 | 2022-09-14 10:54 | G | 2022-01-25 | Solar plus Battery | OT | SUN BAT | 1 | 1 | 1 | Worcester | MA | 2022-04-29 | 2022-04-29 | 2022-09-14 | National Grid MA 13.8 kV, Whitins Pond 320W5 | CNR | FALSE | FALSE |  |  | CMA |  |  |  |  | In Progress
| 1225 | 2025-09-30 15:37 | G | 2022-02-03 | Offshore Wind | WT | WND | 1200 | 1200 | 1200 | NA | MA | 2029-01-31 | 2028-09-30 | 2025-09-30 | Bourne 345 kV Switching Station | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted
| 1226 | 2025-03-20 12:41 | G | 2022-03-04 | Grissom Solar | PV | SUN | 4.99 | 4.99 | 4.99 | Sullivan | NH | 2026-12-30 | 2026-12-15 |  | 46 kV subtransmission line between GMP Maple Avenue B-42 and the 4402 breaker at the GMP/NGRID demarc considered at Bellows Falls | NR | TRUE | TRUE | ISO-NE | NA | NH |  | Document Posted |  |  | Executed
| 1227 | 2024-09-04 16:32 | ETU | 2022-02-16 | 1200 MW non-controllable ETU - N to S flow only | NA | N/A | 1200 |  |  | Somerset/Aroostook | ME | 2026-12-09 | 2026-10-08 | 2024-09-04 | New substation on Line 3023 near the Detroit Substation near Pittsfield, Maine. | N/A | FALSE | FALSE |  | PD | ME
| 1228 | 2024-09-04 16:32 | ETU | 2022-02-16 | 1200 MW non-controllable ETU - N to S flow only | NA | N/A | 1200 |  |  | Hancock/Aroostook | ME | 2026-12-09 | 2026-10-08 | 2024-09-04 | New substation on Line 388 | N/A | FALSE | FALSE |  | PD | ME
| 1229 | 2022-09-14 10:55 | G | 2022-02-22 | Solar plus Battery | OT | SUN BAT | 3 | 3 | 3 | Hampshire | MA | 2022-12-31 | 2022-09-30 | 2022-09-14 | Eversource 13.8kV Circuit 18G4 | CNR | FALSE | FALSE |  |  | WMA |  | In Progress |  |  |  | Under Study
| 1230 | 2025-10-17 15:03 | ETU | 2022-03-04 | 1200 MW non-controllable ETU - N to S flow only | NA | N/A | 1200 |  |  | Somerset/Aroostook | ME | 2027-12-01 | 2027-10-01 | 2025-10-11 | The Point of Interconnection will be a new station about 30 miles from Orrington that taps the existing segment 3023 between Orrington and Albion Rd. Hammond, ME to Pittsfield ME (see map) | N/A | FALSE | FALSE |  | PD | ME
| 1231 | 2022-04-22 13:35 | G | 2022-03-04 | Battery Storage CNR Only | OT | BAT | 0 | 204.64 | 204.64 | Windham | CT | 2025-05-01 | 2025-02-15 | 2022-04-22 | Eversource Killingly 345kV Substation | CNR | FALSE | FALSE |  |  | CT
| 1232 | 2024-10-27 17:03 | G | 2022-03-04 | Battery Storage | OT | BAT | 27.44 | 27.44 | 27.44 | Providence | RI | 2025-12-31 | 2025-12-15 | 2024-10-23 | NEC 115/34.5kV Iron Mine Hill Substation #1203 spare buss position #2 | CNR | FALSE | FALSE |  | PD | RI |  | Not Started |  |  |  | Under Study
| 1233 | 2022-08-12 08:53 | G | 2022-03-14 | Battery Storage | OT | BAT | 20 | 20 | 20 | Bristol | MA | 2024-12-31 | 2024-10-28 | 2022-08-11 | Eversource's Cross Road 13.2kV Circuit 541 | CNR | FALSE | FALSE |  | PD | SEMA
| 1234 | 2022-08-12 08:53 | G | 2022-03-14 | Battery Storage | OT | BAT | 20 | 20 | 20 | Bristol | MA | 2024-12-31 | 2024-10-28 | 2022-08-11 | Eversource's Cross Road 13.2kV Circuit 533 | CNR | FALSE | FALSE |  | PD | SEMA
| 1235 | 2022-08-12 08:54 | G | 2022-03-14 | Battery Storage | OT | BAT | 20 | 20 | 20 | Bristol | MA | 2024-12-31 | 2024-10-28 | 2022-08-11 | Eversource's Cross Road 13.2kV Circuit 532 | CNR | FALSE | FALSE |  | PD | SEMA
| 1236 | 2025-08-13 10:46 | ETU | 2022-03-21 | 1200 MW non-controllable ETU - N to S flow only | NA | N/A | 1200 |  |  | Aroostook/Somerset | ME | 2028-06-01 | 2028-06-01 | 2025-08-13 | Transmission Line connects between the new Aroostook station and Pittsfield Station. Pittsfield 345 kV substation is located between the existing Orrington - Albion Road line in Somerset County at lat/long 44.795/-69.386. The Aroostook station will be located in Aroostook county at lat/long 45.7634/-68.0278. | N/A | FALSE | FALSE |  | PD | ME
| 1237 | 2025-10-10 10:36 | G | 2022-03-21 | Battery Storage CNR only | OT | BAT | 0 | 205 | 205 | Washinton | RI | 2029-12-07 | 2029-09-28 | 2025-10-10 | Primary - NEP L190-2, Alt NEP G185S | CNR | FALSE | FALSE |  |  | RI
| 1239 | 2025-10-02 16:41 | G | 2022-03-25 | Solar plus Battery | OT | SUN BAT | 129 | 183.6 | 183.6 | Oxford | ME | 2029-12-31 | 2029-12-03 | 2025-10-02 | CMP 115kV Woodstock S/S | CNR | TRUE | TRUE |  | PD | ME | Document Posted | Document Posted |  |  | In Progress
| 1240 | 2024-10-27 17:03 | G | 2022-03-25 | Battery Storage | OT | BAT | 62.84 | 62.84 | 62.84 | Kent | RI | 2025-12-31 | 2025-12-15 | 2024-10-23 | National Grid Kent County Substation - 115kV open line position between 4T3T and 3T10 breakers. | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
| 1241 | 2025-06-16 15:54 | G | 2022-03-28 | Sanford/Quaker Hill CMP Cluster 4 | OT | SUN BAT | 21.184 | 21.184 | 21.184 | York | ME | 2028-06-30 | 2026-06-30 | 2025-06-13 | CMP Sandford/Quaker Hill | NA | TRUE | TRUE | CMP | PD | ME
| 1242 | 2025-06-16 15:55 | G | 2022-03-28 | Lewiston CMP Cluster 5 | OT | SUN BAT | 52.464 | 52.464 | 52.464 | Oxford/Androscoggin | ME | 2028-06-30 | 2028-06-30 | 2025-06-13 | CMP Lewiston | NA | TRUE | TRUE | CMP | PD | ME
| 1243 | 2025-10-17 15:03 | G | 2022-03-31 | Solar | PV | SUN | 300 | 300 | 300 | Aroostook | ME | 2026-11-01 | 2026-10-01 | 2025-10-11 | 345kV line between Orrington(PSSE Bus Number: 100002) -Albion Rd (PSSE Bus Number: 100092) near the town of Pittsfield | NR | FALSE | FALSE |  | PD | ME
| 1244 | 2023-01-10 16:36 | G | 2022-03-31 | Solar | PV | SUN | 75 | 75 | 75 | Franklin | ME | 2025-11-01 | 2025-10-01 | 2022-11-14 | 115 kV New Sturtevant Substation (PSSE Bus Number: 100116) | NR | FALSE | FALSE |  | PD | ME | In Progress |  |  |  |  | Under Study
| 1245 | 2024-10-01 14:11 | G | 2022-03-31 | Solar | PV | SUN | 150 | 150 | 150 | Hartford | CT | 2028-10-31 | 2028-09-24 |  | 345kV Line 3419 Tap between Meekville Junction/Barbour Hill (PSSE Bus Number: 119103) To LudlowPSSE Bus Number: 116045) | NR | TRUE | TRUE |  | PD | CT | Document Posted | Document Posted |  |  | In Progress
| 1246 | 2023-07-25 15:47 | G | 2022-03-31 | Solar | PV | SUN | 150 | 150 | 150 | Grafton | NH | 2025-11-01 | 2025-10-01 | 2023-07-25 | 230 kV Comerford to North Litchfield A201Line; alternative POI is B-202. | NR | FALSE | FALSE |  | PD | NH | In Progress |  |  |  |  | Under Study
| 1247 | 2025-10-17 14:04 | G | 2022-04-05 | Solar | PV | SUN | 25 | 25 | 25 | Hartford | CT | 2027-11-15 | 2027-10-01 |  | To interconnect at the POI of Gravel Pit Solar QP 1030, via a Shared Facility, QP 1030 is described as a line cut and three-breaker ring bus of the 115 kV Connecticut Light & Power Company line between Barbour Hill and Windsor Locks. | NR | TRUE | TRUE | ISO-NE | PD | CT |  | Document Posted |  |  | In Progress
| 1248 | 2025-10-17 15:04 | G | 2022-04-06 | Battery Storage | OT | BAT | 154.656 | 154.656 | 154.656 | Bristol | MA | 2026-05-31 | 2026-03-01 | 2025-10-11 | NGRID 115kV Robinson Ave substation | CNR | FALSE | FALSE |  | PD | RI | Document Posted
| 1249 | 2023-03-28 10:14 | G | 2022-04-19 | Battery Storage Addition | OT | BAT | 0 | 16.02 | 16.02 | New London | CT | 2027-05-14 | 2027-03-12 | 2023-03-28 | Tunnel 23 kV Substation | CNR | FALSE | FALSE |  |  | CT | Document Posted | Not Started |  |  |  | Under Study
| 1250 | 2023-05-19 09:10 | G | 2022-04-14 | Battery Storage | OT | BAT | 50.7 | 50.7 | 50.7 | York | ME | 2024-11-01 | 2024-09-01 | 2023-05-18 | CMP Goosefare 115kV Substation 43 31 22 N 70 26 59 W | CNR | FALSE | FALSE |  |  | ME | Not Started |  |  |  |  | Under Study
| 1251 | 2022-08-26 10:43 | G | 2022-04-11 | Battery Storage | OT | BAT | 60 | 60 | 60 | Hartford | CT | 2024-12-31 | 2024-10-15 | 2022-08-26 | To interconnect at the POI of Gravel Pit Solar QP 1030, via a Shared Facility, QP 1030 is described as a line cut and three-breaker ring bus of the 115 kV Connecticut Light & Power Company line between Barbour Hill and Windsor Locks. | CNR | FALSE | FALSE |  | PD | CT | In Progress |  |  |  |  | Under Study
| 1253 | 2023-11-14 16:22 | G | 2022-04-27 | Battery Storage CNR Only (see QP887) | OT | BAT | 0 | 150 | 150 | Norfolk | MA | 2026-05-31 | 2026-04-30 | 2023-11-14 | Wareham Substation 115kV, Eversource Line 113 | CNR | FALSE | FALSE |  |  | SEMA
| 1254 | 2025-06-16 15:56 | G | 2022-05-02 | Kimball DG Area Study | OT | SUN BAT | 7.894 | 7.894 | 7.894 | York/Oxford/Cumberland | ME | 2028-06-30 | 2028-06-30 | 2025-06-13 | CMP Kimball Road/Lovell 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
| 1255 | 2025-06-16 15:57 | G | 2022-05-02 | Detroit/Guilford/Belfast DG Area Study | OT | SUN BAT | 57.72 | 57.72 | 57.72 | Piscataquis/Penobscot/Somerset/Waldo/Hancock | ME | 2027-12-31 | 2027-12-31 | 2025-06-13 | CMP Detroit 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
| 1256 | 2025-10-17 15:04 | G | 2022-05-03 | Wind | WT | WND | 905 | 905 | 905 | Aroostook | ME | 2026-12-09 | 2026-10-08 | 2025-10-11 | Pittsfield Station. Pittsfield 345 kV substation is located between the existing Orrington - Albion Road line (3023) near town of Pittsfield. | CNR | FALSE | FALSE |  | PD | BHE
| 1257 | 2025-10-17 15:04 | G | 2022-05-03 | Solar | PV | SUN | 319.2 | 319.2 | 319.2 | Aroostook | ME | 2026-12-09 | 2026-10-08 | 2025-10-11 | Pittsfield Station. Pittsfield 345 kV substation is located between the existing Orrington - Albion Road line (3023) near town of Pittsfield. | CNR | FALSE | FALSE |  | PD | BHE
| 1258 | 2025-10-17 15:05 | G | 2022-05-03 | Battery Storage CNR Only | OT | BAT | 0 | 170 | 170 | Norfolk | MA | 2027-07-26 | 2027-06-26 | 2025-10-11 | National Grid's South Wrentham 115kV Substation | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed
| 1259 | 2025-08-01 15:37 | G | 2022-06-15 | Battery Storage | OT | BAT | 20 | 20 | 20 | Berkshire | MA | 2027-06-28 | 2027-03-28 | 2025-08-01 | Eversource 115 kV Line 1231 (Berkshire - Plainfield) | NR | TRUE | FALSE | ISO-NE |  | WMA |  | Document Posted |  |  | Not Started
| 1260 | 2022-08-31 09:26 | G | 2022-05-06 | Solar plus Battery | OT | SUN BAT | 2.772 | 2.6888 | 2.6888 | Hampden | MA | 2023-06-01 | 2023-06-01 | 2022-08-31 | Eversource 13.8 kV Line 19S1 | CNR | FALSE | FALSE |  |  | WMA
| 1261 | 2025-10-24 15:19 | G | 2022-05-17 | Battery Storage Addition (to QP1086) | OT | SUN BAT | 0 | 160 | 160 | Knox | ME | 2026-11-30 | 2026-10-31 |  | CMP 115kV line Section 80 | NR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed
| 1262 | 2024-08-29 16:57 | G | 2022-05-17 | Battery Storage | OT | BAT | 80.875 | 80.875 | 80.875 | Middlesex | CT | 2026-07-06 | 2026-06-18 | 2024-08-29 | Haddam 115kV BUS [HADDAM(120632)]; 41°27'38.74"N, 72°28'38.23"W | CNR | TRUE | FALSE |  | PD | CT | Document Posted | Document Posted |  |  | Not Started
| 1263 | 2023-07-13 09:56 | G | 2022-07-01 | Battery Storage | OT | BAT | 18.87 |  |  | Hampshire | MA | 2023-10-27 | 2023-10-20 | 2023-07-13 | POI Coordinates: 42.42649, -72.53956, Feeder: 18G6, Express feeder, Owner of POI: WMECO (Eversource), Distribution Voltage Level: 13.8 kV, Substation Voltage Level: 115 kV - 13.8 kV | CNR | FALSE | FALSE |  | PD | WMA | In Progress |  |  |  |  | Under Study
| 1264 | 2023-01-12 13:58 | G | 2022-05-19 | Bear Swamp Pump Load increase | PS | WAT | 0 | 333 | 333 | Berkshire | MA | 2023-01-06 | 2023-01-04 |  | The existing POI of the Bear Swamp generating station. | NR | TRUE | FALSE | ISO-NE | PD | WMA |  | Document Posted |  |  | Executed
| 1265 | 2025-06-09 14:26 | G | 2022-05-23 | Revolution Offshore Wind CNR only | WT | WND | 0 | 750.75 | 750.75 | NA | RI | 2026-11-05 | 2026-05-08 |  | NG 115 kV Davisville Substation, Washington County | CNR | FALSE | FALSE |  |  | RI |  |  |  |  | Executed
| 1266 | 2024-09-04 09:58 | G | 2022-05-23 | Battery Storage | OT | BAT | 100 | 100 | 100 | Hartford | CT | 2025-08-04 | 2025-07-03 | 2024-08-28 | 115kV Manchester Substation (Bus# 120074) Geographic coordinates: 41.76948781166102, -72.56130136574556 | CNR | FALSE | FALSE |  | PD | CT |  | Document Posted |  |  | Not Started
| 1267 | 2022-06-27 09:23 | G | 2022-05-20 | Battery Storage | OT | BAT | 51.73 | 51.73 | 51.73 | New London | CT | 2025-08-08 | 2025-07-25 | 2022-06-24 | Groton Utilities Buddington Substation, 69kV bus (future 115kV) Alternate POI: Groton Utilities Buddington Substation, 34.5kV bus | CNR | FALSE | FALSE |  | PD | CT
| 1268 | 2022-12-07 10:53 | G | 2022-05-24 | Coolidge Solar CNR Only | PV | SUN | 0 | 19.9 | 19.9 | Windsor | VT | 2018-12-20 | 2018-12-12 |  | 115 kV Coolidge Substation | CNR | FALSE | FALSE |  |  | VT |  |  |  |  | Executed
| 1269 | 2023-08-10 15:06 | G | 2022-05-27 | Sanford Airport Solar CNR Only | PV | SUN | 0 | 50 | 50 | York | ME | 2023-08-02 | 2023-08-02 |  | Cyro Drive substation 115 kV | CNR | FALSE | FALSE |  |  | ME |  |  |  |  | Executed | In Service
| 1270 | 2023-07-24 13:32 | G | 2022-05-31 | Nutmeg Solar CNR Only | PV | SUN | 0 | 19.9 | 19.9 | Hartford | CT | 2020-12-07 | 2020-11-15 |  | Scitico 115 kV | CNR | FALSE | FALSE |  |  | CT |  |  |  |  | Executed | In Service
| 1271 | 2025-10-17 15:05 | ETU | 2022-06-07 | Non-Controllable ETU - Pittsfield to Coopers Mills flow only | NA | N/A |  |  |  | Somerset/Lincoln | ME | 2027-12-01 | 2027-10-01 | 2025-10-11 | New Pittsfield substation (per QP1230) Pittsfield Somerset ME 04967 Coopers Mills substation Windsor Kennebec ME 04363 | N/A | FALSE | FALSE |  | PD | ME
| 1272 | 2025-10-17 14:05 | G | 2022-06-08 | West Springfield 45 MW BESS | OT | BAT | 45 | 45 | 45 | Hampden | MA | 2029-05-04 | 2029-04-06 |  | West Springfield Station, 115kV Bus (existing 8C-3X 140 MVA transformer; position WS#2). | NR | TRUE | TRUE | ISO-NE | PD | WMA |  | Document Posted |  |  | Executed
| 1273 | 2025-06-16 15:57 | G | 2022-06-08 | Canton 470 - EMA ASO | OT | SUN BAT | 4.999 | 4.999 | 4.999 | Norfolk | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Canton 470 | NA | FALSE | FALSE |  | PD | SEMA
| 1274 | 2025-06-16 15:58 | G | 2022-06-08 | Crystal Spring 646 - EMA ASO | OT | SUN BAT | 1.7 | 1.7 | 1.7 | Plymouth | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Crystal Spring 646 | NA | FALSE | FALSE |  | PD | SEMA
| 1275 | 2025-06-16 16:00 | G | 2022-06-08 | Group @ Duxbury 738 - EMA ASO | OT | SUN BAT | 6.782 | 6.782 | 6.782 | Plymouth | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Duxbury 738 | NA | FALSE | FALSE |  | PD | SEMA
| 1276 | 2025-06-16 16:01 | G | 2022-06-08 | Falmouth 933 - EMA ASO | OT | SUN BAT | 3.5 | 3.5 | 3.5 | Barnstable | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Falmouth 933 | NA | FALSE | FALSE |  | PD | SEMA
| 1277 | 2025-06-16 16:02 | G | 2022-06-08 | Fisher Road 657 - EMA ASO | OT | SUN BAT | 3 | 3 | 3 | Bristol | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Fisher Road 657 | NA | FALSE | FALSE |  | PD | SEMA
| 1278 | 2025-06-16 16:03 | G | 2022-06-08 | Harwich 968 - EMA ASO | OT | SUN BAT | 3.998 | 3.998 | 3.998 | Barnstable | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Harwich 968 | NA | FALSE | FALSE |  | PD | SEMA
| 1279 | 2025-06-16 16:03 | G | 2022-06-08 | Group @ Hatchville 936 - EMA ASO | OT | SUN BAT | 18.486 | 18.486 | 18.486 | Barnstable | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Hatchville 936 | NA | FALSE | FALSE |  | PD | SEMA
| 1280 | 2025-06-16 16:04 | G | 2022-06-08 | Hyannis 961 - EMA ASO | OT | SUN BAT | 4.993 | 4.993 | 4.993 | Barnstable | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Hyannis 961 | NA | FALSE | FALSE |  | PD | SEMA
| 1281 | 2025-06-16 16:05 | G | 2022-06-08 | Group @ Industrial Park 636 - EMA ASO | OT | SUN BAT | 16.514 | 16.514 | 16.514 | Bristol | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Industrial Park 636 | NA | FALSE | FALSE |  | PD | SEMA
| 1282 | 2025-06-16 16:05 | G | 2022-06-08 | Marshfield 739 - EMA ASO | OT | SUN BAT | 4.6 | 4.6 | 4.6 | Plymouth | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Marshfield 739 | NA | FALSE | FALSE |  | PD | SEMA
| 1283 | 2025-06-16 16:08 | G | 2022-06-08 | Mashpee 946 - EMA ASO | OT | SUN BAT | 1.49 | 1.49 | 1.49 | Barnstable | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Mashpee 946 | NA | FALSE | FALSE |  | PD | SEMA
| 1284 | 2025-06-16 16:08 | G | 2022-06-08 | Group @ Orleans 975 - EMA ASO | OT | SUN BAT | 9.998 | 9.998 | 9.998 | Barnstable | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Orleans 975 | NA | FALSE | FALSE |  | PD | SEMA
| 1285 | 2025-06-16 16:09 | G | 2022-06-08 | Sandwich 916 - EMA ASO | OT | SUN BAT | 4.6 | 4.6 | 4.6 | Barnstable | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Sandwich 916 | NA | FALSE | FALSE |  | PD | SEMA
| 1286 | 2025-06-16 16:09 | G | 2022-06-08 | Tremont 713 - EMA ASO | OT | SUN BAT | 4.996 | 4.996 | 4.996 | Plymouth | MA | 2025-07-31 | 2025-07-31 | 2025-06-13 | Eversource Tremont 713 | NA | TRUE | TRUE | NU | PD | SEMA
| 1287 | 2025-06-16 16:10 | G | 2022-06-08 | Valley 715 - EMA ASO | OT | SUN BAT | 3.7 | 3.7 | 3.7 | Plymouth | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Valley 715 | NA | FALSE | FALSE |  | PD | SEMA
| 1288 | 2025-06-16 16:10 | G | 2022-06-08 | Wellfleet 976 - EMA ASO | OT | SUN BAT | 4.107 | 4.107 | 4.107 | Barnstable | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Wellfleet 976 | NA | FALSE | FALSE |  | PD | SEMA
| 1289 | 2025-06-16 16:11 | G | 2022-06-08 | Group @ West Pond 737 - EMA ASO | OT | SUN BAT | 6.982 | 6.982 | 6.982 | Middlesex | MA | 2025-07-31 | 2025-07-31 | 2025-06-13 | Eversource West Pond 737 | NA | TRUE | TRUE | NU | PD | SEMA
| 1290 | 2025-06-16 16:12 | G | 2022-06-08 | Group @ Wing Lane 624 - EMA ASO | OT | SUN BAT | 14.979 | 14.979 | 14.979 | Bristol | MA | 2023-11-30 | 2023-09-30 | 2025-06-13 | Eversource Wing Lane 624 | NA | FALSE | FALSE |  | PD | SEMA
| 1291 | 2022-12-06 16:36 | G | 2022-06-09 | Turners Falls CNR | HD | WAT | 0 | 0.937 | 0.937 | Franklin | MA | 2022-11-15 | 2022-11-15 |  | The POI is at 13.8 kV where the conductors from WMECO's pole 70/460H1 attach to the Interconnection Customer's building on the other side of the canal. | CNR | FALSE | FALSE |  |  | WMA |  |  |  |  | Executed
| 1292 | 2023-05-01 11:50 | G | 2022-07-12 | Battery Storage | OT | BAT | 95 | 95 | 95 | Worcester | MA | 2023-09-30 | 2023-08-30 | 2023-05-01 | National Grid 115 kV E-157W line three-breaker ring bus location: 0.32 miles north of Millbury 2 station along transmission line; 2.62 miles south of Wyman station along transmission line (the length of the Millbury 2 - Wyman Gordon line is 2.94 miles). Three-breaker ring bus will be located <0.01 miles east of POI. | CNR | FALSE | FALSE |  | PD | CMA | In Progress |  |  |  |  | Under Study
| 1293 | 2023-11-21 13:28 | TS | 2022-07-13 | GRID RNS | NA | N/A | 12 | 183.7 | 183.7 | Middlesex | MA | 2025-08-01 | 2025-08-01 |  | NGRID 115 kV T146 line | N/A | TRUE | TRUE | ISO-NE | PD | BOST
| 1294 | 2023-06-06 09:21 | G | 2022-07-27 | Solar | PV | SUN | 75.32 | 75.32 | 75.32 | Washington | ME | 2026-08-04 | 2026-07-21 | 2023-06-06 | Ring Bus constructed for QP760 on Versant 115kV Line 52 | CNR | FALSE | FALSE |  | PD | BHE | In Progress |  |  |  |  | Under Study
| 1295 | 2024-08-13 18:01 | G | 2022-08-09 | Solar plus Battery | OT | SUN BAT | 205 | 205 | 205 | Aroostook | ME | 2025-11-28 | 2025-09-03 | 2024-08-13 | Orrington-Albion Rd 345kV line (3023) near the town of Pittsfield (approximately 19 miles from Albion Rd Substation) | CNR | FALSE | FALSE |  | PD | ME
| 1296 | 2024-12-10 10:19 | G | 2022-08-10 | Battery Storage | OT | BAT | 125 | 125 | 125 | Hartford | CT | 2027-04-01 | 2027-03-15 | 2024-12-10 | Eversource Energy Corporation 115 kV line 1756 | CNR | TRUE | FALSE |  | PD | CT | Document Posted | Document Posted |  |  | Not Started
| 1297 | 2022-09-13 13:59 | G | 2022-08-15 | Offshore Wind | WT | WND | 1200 | 1200 | 1200 | NA | MA | 2029-05-31 | 2029-01-31 | 2022-09-13 | National Grid Brayton Point 345 kV Substation | CNR | FALSE | FALSE |  | PD | SEMA
| 1298 | 2024-06-04 08:15 | G | 2022-08-16 | Battery Storage | OT | BAT | 157.92 | 157.92 | 157.92 | Worcester | MA | 2027-06-30 | 2027-06-15 | 2024-05-31 | Eversource 345 kV Line 3361, approximately 3.2 miles from Sherman Road and 7.6 miles from Blackstone. | CNR | FALSE | FALSE |  | PD | CMA | Document Posted | Not Started
| 1299 | 2025-05-21 13:11 | G | 2022-08-18 | Solar Increase (QP1145) | PV | SUN | 54.1 | 74.8 | 74.8 | Hancock | ME | 2026-09-25 | 2026-09-11 | 2025-05-21 | Versant 115kV Line 57 (new ring bus located 0.7 miles north of Versant's 115kV substation). | CNR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  |  | In Progress
| 1300 | 2022-10-04 12:23 | G | 2022-08-19 | Solar plus Battery Increase (QP1129) | OT | SUN BAT | 0.04 | 2.5 | 2.5 | Bristol | MA | 2022-08-31 | 2021-08-31 | 2022-10-04 | The primary connection of the proposed project to Eversource Energy is located at the Wing Lane substation #624 Transformer #1 Line #240. The site is located approximately 0.26 circuit miles from Substation 624 near PSS/E node 111293(Wing Lane 13.2 KV) | CNR | FALSE | FALSE |  |  | SEMA
| 1301 | 2022-12-09 19:22 | G | 2022-09-06 | Battery Storage | OT | BAT | 10 | 10 | 10 | Worcester | MA | 2025-05-15 | 2025-03-15 | 2022-12-09 | National Grid Feeder 01-21W1, Leicester Substation, 13.8 kV | CNR | FALSE | FALSE |  | PD | CMA
| 1302 | 2023-03-24 10:30 | G | 2022-09-22 | Battery Storage | OT | BAT | 9.11 | 8.5 | 8.5 | Franklin | MA | 2027-05-28 | 2027-02-26 | 2023-03-24 | Eversource 21C1, Montague Substation,13.8 kV | CNR | FALSE | FALSE |  | PD | WMA | Not Started |  |  |  |  | Under Study
| 1303 | 2023-05-25 13:22 | G | 2022-09-22 | Battery Storage | OT | BAT | 11.9 | 11.9 | 11.9 | Franklin | MA | 2027-05-28 | 2027-02-26 | 2023-05-25 | Eversource 21B8, 13.8 kV | CNR | FALSE | FALSE |  | PD | WMA
| 1304 | 2025-06-16 16:12 | G | 2022-09-09 | Uxbridge Substation – NG Hopedale West Group Study | OT | BAT | 4.99 | 4.99 | 4.99 | Worcester | MA | 2025-12-31 | 2025-11-15 | 2025-06-13 | NG Feeder 321W6, Uxbridge T2 | NA | TRUE | FALSE | NGRID | PD | SEMA
| 1305 | 2025-06-16 16:13 | G | 2022-09-09 | Depot Street Substation – NG Hopedale West Group Study | OT | SUN BAT | 1.5 | 1.5 | 1.5 | Worcester | MA | 2025-12-31 | 2025-11-15 | 2025-06-13 | NG Feeder 335W1 (7U), Depot Street T1 and T2 | NA | TRUE | FALSE | NGRID | PD | SEMA
| 1306 | 2025-06-16 16:14 | G | 2022-09-09 | Whitins Pond Substation – NG Hopedale West Group Study | OT | BAT | 4.948 | 4.948 | 4.948 | Worcester | MA | 2025-12-31 | 2025-11-15 | 2025-06-13 | NG Feeder 320W4, Whitins Pond T2 | NA | TRUE | FALSE | NGRID | PD | SEMA
| 1307 | 2025-06-16 16:14 | G | 2022-09-09 | Whitins Pond Substation – NG Hopedale West Group Study | OT | BAT | 4.948 | 4.948 | 4.948 | Worcester | MA | 2025-12-31 | 2025-11-15 | 2025-06-13 | NG Feeder 320W5, Whitins Pond T1 | NA | TRUE | FALSE | NGRID | PD | SEMA
| 1308 | 2025-06-16 16:15 | G | 2022-09-09 | Uxbridge Substation – NG Hopedale West Group Study | OT | BAT | 6.994 | 6.994 | 6.994 | Worcester | MA | 2025-12-31 | 2025-11-15 | 2025-06-13 | NG Feeder 321W6, Uxbridge T2 | NA | TRUE | FALSE | NGRID | PD | SEMA
| 1309 | 2024-11-13 11:56 | ETU | 2022-09-23 | non-controllable objective ETU to enable 1200 MW injection near Millstone substation | NA | N/A | 1200 |  |  | New London | CT | 2029-12-30 | 2029-05-01 | 2024-11-12 | N/A | N/A | FALSE | FALSE |  | PD | CT | Document Posted | Not Started |  |  |  | Under Study
| 1310 | 2023-12-11 11:56 | G | 2022-09-23 | Battery Storage | OT | BAT | 118.75 | 118.75 | 118.75 | Berkshire | MA | 2025-10-31 | 2025-09-30 | 2023-12-08 | 115 kV Transmission line (1211 - Present between Doreen and Oswald substation) | CNR | FALSE | FALSE |  | PD | WMA | Document Posted | Not Started |  |  |  | Under Study
| 1311 | 2024-10-01 12:23 | TS | 2022-09-23 | RNS - move load to new substation | NA | N/A | 20 | 85.32 | 50.6 | Plymouth | MA | 2026-07-01 | 2026-07-01 |  | Wareham Street to new South Middleborough Substation | N/A | TRUE | TRUE | ISO-NE | PD | SEMA
| 1312 | 2025-10-10 14:34 | ETU | 2022-09-26 | non-controllable ETU - inc the simultaneous injection capacity to 2400 MW at Brayton Pt 345 kV sub | NA | N/A |  |  |  | Somerset | MA | 2028-12-30 | 2028-09-29 | 2025-10-10 | N/A | N/A | FALSE | FALSE |  | PD | RI | Document Posted
| 1313 | 2022-09-26 13:28 | ETU | 2022-09-23 | NY ETU QP1125 | NA | N/A | 0 | 0 | 0 | St. Lawrence-Lewis | NY | 2025-12-31 | 2025-12-01 |  | Moses/Adirondack/Poter Path | N/A | FALSE | FALSE |  | PD | N/A
| 1314 | 2024-10-15 09:45 | G | 2022-09-27 | Offshore Wind | WT | WND | 470 | 470 | 470 | NA | MA | 2029-11-01 | 2029-09-01 | 2024-10-14 | Eversource 115kV Acushnet, lines 112/114 | NR | FALSE | FALSE |  | PD | SEMA |  | Not Started |  |  |  | Under Study
| 1315 | 2024-10-02 13:00 | G | 2022-09-29 | Battery Storage | OT | BAT | 106.97 | 106.97 | 106.97 | Windham | CT | 2026-06-12 | 2026-06-09 | 2024-10-02 | Eversource Killingly Substation,115kV BUS, Tracy Rd, Killingly, CT 06241, 41.881384, -71.891162 | CNR | FALSE | FALSE |  | PD | CT | In Progress
| 1316 | 2023-08-28 08:14 | G | 2022-09-30 | Solar plus Battery | OT | SUN BAT | 102 | 102 | 102 | Cheshire | NH | 2027-10-28 | 2027-10-28 | 2023-08-25 | Eversource 115kV line L163 | CNR | FALSE | FALSE |  |  | NH | In Progress |  |  |  |  | Under Study
| 1317 | 2024-01-18 12:42 | ETU | 2022-09-30 | non-controllable objective ETU to enable 1200 MW injection near Norwalk substation | NA | N/A |  |  |  | Fairfield | CT | 2029-12-30 | 2029-05-01 | 2024-01-18 | N/A | N/A | FALSE | FALSE |  |  | SWCT | Document Posted | Not Started |  |  |  | Under Study
| 1318 | 2023-07-20 17:10 | TS | 2022-10-03 | GRID LNS | NA | N/A | 9 | 45 | 39 | Middlesex/Worcester | MA | 2023-10-03 | 2023-10-01 | 2023-07-03 | GRID 69 kV transmission lines U-21S and U-21E | N/A | FALSE | FALSE |  | PD | CMA
| 1319 | 2025-11-12 12:29 | G | 2022-10-07 | Battery Storage | OT | BAT | 141.6 | 141.6 | 141.6 | Litchfield | CT | 2029-04-01 | 2029-03-15 |  | 115 kV line between Rocky River and Bulls Bridge substations | CNR | TRUE | TRUE |  |  | CT |  | Document Posted |  |  | Executed
| 1320 | 2025-05-05 16:26 | G | 2022-10-07 | Battery Storage | OT | BAT | 203.95 | 203.95 | 203.95 | Worcester | MA | 2026-12-31 | 2026-12-16 |  | National Grid 115KV Line R144 between Millbury No. 2 and Woonsocket substations - approximately 5.8 circuit miles from Woonsocket substation. | CNR | TRUE | TRUE |  | PD | SEMA |  | Document Posted |  |  | Executed
| 1321 | 2022-12-01 09:26 | TS | 2022-10-06 | NEP LNS | NA | N/A | 17.56 | 17.56 | 17.56 | Somerset | MA | 2024-12-01 | 2024-12-01 | 2022-11-30 | NEP 115 kV Brayton Point | N/A | FALSE | FALSE |  | PD | SEMA
| 1322 | 2022-11-28 12:54 | ETU | 2022-10-11 | Non-controllable ETU from Line 388 substation to Coopers Mills substation | NA | N/A |  |  |  |  | ME | 2027-12-31 | 2027-10-08 | 2022-11-02 | New substation on line 388 (per QP1228 ) to Coopers Mills Substation, Windsor Kennebec, ME, 04363 | N/A | FALSE | FALSE |  | PD | ME
| 1323 | 2022-11-28 12:55 | ETU | 2022-10-11 | Non-controllable ETU from Line 3023 substation to Coopers Mills substation | NA | N/A |  |  |  |  | ME | 2027-12-31 | 2027-10-08 | 2022-11-02 | New substation on line 3023 (per QP1227 ) to Coopers Mills Substation, Windsor Kennebec, ME, 04363 | N/A | FALSE | FALSE |  | PD | ME
| 1324 | 2024-10-27 17:04 | G | 2022-10-18 | Battery Storage | OT | BAT | 55 | 55 | 55 | Providence | RI | 2027-12-30 | 2027-12-15 | 2024-10-23 | 115 kV Line T-172N approximately 1.38 mi from Farnum Pike and 1.09 mi from Putnam Pike Substations | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
| 1325 | 2024-06-04 08:16 | G | 2022-10-19 | Battery Storage | OT | BAT | 305 | 307.8 | 307.8 | Providence | RI | 2027-12-30 | 2027-12-15 | 2024-05-31 | NEP transmission line: 345 kV line 359, approximately 10.55 miles from West Farnum and 10.81 miles from Kent County substations. | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
| 1326 | 2023-10-13 16:23 | G | 2022-10-19 | Battery Storage | OT | BAT | 40 | 40 | 40 | Kent | RI | 2027-12-30 | 2027-12-15 | 2023-10-13 | Line tap on the S-171 South 115 kV transmission line, roughly 4 miles from West Cranston Substation and 1.5 miles from Drumrock Substation. | NR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
| 1327 | 2023-02-14 11:19 | G | 2022-10-20 | Battery Storage | OT | BAT | 270 | 270 | 270 | Norfolk | MA | 2023-12-02 | 2023-11-02 | 2023-02-14 | West Walpole substation | CNR | FALSE | FALSE |  | PD | SEMA
| 1328 | 2023-04-28 11:07 | G | 2022-10-24 | Solar | PV | SUN | 21.44 | 21.44 | 21.44 | Grafton | NH | 2024-06-05 | 2024-05-15 | 2023-04-27 | 44.336047°, -71.874785°, National Grid 230 kV Substation | CNR | FALSE | FALSE |  | PD | NH | In Progress |  |  |  |  | Under Study
| 1329 | 2023-05-19 07:57 | G | 2022-10-24 | Solar | PV | SUN | 54.4 | 54.4 | 54.4 | Grafton | NH | 2024-06-05 | 2024-05-15 | 2023-05-19 | POI: (44.321330°, -72.003124°), National Grid's PTF 230 kV bus at Comerford No. 18 station | CNR | FALSE | FALSE |  | PD | NH | Document Posted |  |  |  |  | Under Study
| 1330 | 2022-12-19 08:10 | G | 2022-11-01 | Solar | PV | SUN | 46.5 | 46.5 | 46.5 | Sullivan | NH | 2023-12-20 | 2023-11-17 | 2022-12-16 | 43.177488°, -72.434553° - National Grid 115kV line | CNR | FALSE | FALSE |  |  | NH
| 1331 | 2023-12-19 09:00 | G | 2022-11-02 | Battery Storage | OT | BAT | 300 | 300 | 300 | Hampden | MA | 2025-12-23 | 2025-12-16 | 2023-12-19 | Interconnecting to POI coordinates (42.148537, -72.300019) on 115 kV Transmission line X-176, approximately 0.3 miles north of Palmer #503 substation and 5.76 miles from Thorndike #523 substation. | CNR | FALSE | FALSE |  | PD | WMA | Document Posted | Not Started |  |  |  | Under Study
| 1332 | 2023-11-22 11:41 | ETU | 2022-11-08 | Enable 1200 MW injection at Mystic | NA | N/A | 1200 |  |  |  | MA | 2029-12-30 | 2029-05-01 | 2023-11-22 | N/A | N/A | FALSE | FALSE |  | PD | BOST | Document Posted | Not Started |  |  |  | Under Study
| 1333 | 2024-01-30 15:32 | ETU | 2022-11-08 | 2400 controllable ETU - unidirectional | NA | N/A | 1100 |  |  |  | CT | 2028-05-31 | 2028-03-31 | 2024-01-30 | 1. Singer 345kV Substation existing available circuit breaker position and new circuit breaker position. 2. Offshore platform at the MA/RI BOEM Wind Energy Areas | N/A | FALSE | FALSE |  |  | SWCT | Not Started |  |  |  |  | Under Study
| 1334 | 2024-10-09 08:30 | G | 2022-11-10 | Battery Storage | OT | BAT | 93.2 | 93.2 | 93.2 | New London | CT | 2027-05-01 | 2027-04-01 | 2024-10-08 | 115 kV line 1070 between Ft Hill Farms and Stockhouse Substations, interconnected by a new three-breaker ring bus approximately 2.5 miles from Ft Hill Farms substation. | CNR | FALSE | FALSE |  | PD | CT |  | Not Started
| 1335 | 2024-10-09 08:30 | G | 2022-11-10 | Battery Storage | OT | BAT | 205.8 | 205.8 | 205.8 | Bristol | MA | 2027-04-01 | 2027-03-01 | 2024-10-08 | Non-PTF 115KV lines ET and W owned by TMLP between Cleary Flood Substation and Substation #16 (W Water St), approximately 1.26 miles from Cleary Flood. Project would interconnect half of the net MW capability to each line. | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started
| 1336 | 2024-01-05 12:11 | G | 2022-11-22 | Battery Storage | OT | BAT | 130 | 130 | 130 | Worcester | MA | 2026-12-31 | 2026-07-01 | 2024-01-05 | Carpenter Hill - North Oxford - Millbury #2 115 kV (V-174) line (2.57 miles from the N. Oxford substation and 6.92 miles from the Millbury #2 substation). | CNR | FALSE | FALSE |  | PD | CMA | Document Posted | Not Started |  |  |  | Under Study
| 1337 | 2023-11-17 10:07 | G | 2022-11-22 | Battery Storage | OT | BAT | 130 | 130 | 130 | Berkshire | MA | 2026-12-31 | 2026-07-01 | 2023-11-17 | 7,500' to Adams - NG Q117 VEL - 65,000' Bennington 115 kV line (42.72482385, -73.09931100). (The project site is on the western side of the transmission line off a gravel bank road and on the opposite side of the small solar array) | CNR | FALSE | FALSE |  | PD | WMA | Document Posted | Not Started |  |  |  | Under Study
| 1338 | 2024-07-30 17:23 | G | 2022-12-06 | Battery Storage | OT | BAT | 275.06 | 275.06 | 275.06 | Hampden | MA | 2027-06-30 | 2027-06-15 | 2024-07-30 | Agawam to Ludlow - 345kV line, 2.5 miles west of Ludlow substation | CNR | TRUE | FALSE | ISO-NE | PD | WMA |  | Document Posted |  |  | Not Started
| 1339 | 2023-01-30 15:17 | G | 2022-12-06 | Battery Storage | OT | BAT | 257.06 | 257.06 | 257.06 | Bristol | MA | 2027-06-30 | 2027-06-15 | 2023-01-30 | National Grid's Brayton Point 345kV Substation, Somerset MA. | CNR | FALSE | FALSE |  | PD | SEMA
| 1340 | 2023-01-30 15:17 | G | 2022-12-06 | Battery Storage | OT | BAT | 292.52 | 550.12 | 550.12 | Bristol | MA | 2027-06-30 | 2027-06-15 | 2023-01-30 | National Grid's Brayton Point 345kV Substation, Somerset MA. | CNR | FALSE | FALSE |  | PD | SEMA
| 1341 | 2023-01-30 15:17 | G | 2022-12-06 | Battery Storage | OT | BAT | 117.3 | 667.425 | 667.425 | Bristol | MA | 2027-06-30 | 2027-06-15 | 2023-01-30 | National Grid's Brayton Point 345kV Substation, Somerset MA. | CNR | FALSE | FALSE |  | PD | SEMA
| 1342 | 2025-10-17 15:09 | G | 2022-12-15 | Western Maine Wind CNR | WT | WND | 0 | 58.8 | 58.8 | Somerset | ME | 2025-09-24 | 2025-04-29 | 2025-10-11 | CMP 115 kV Section 222 - coordinates 45° 9'30.90"N, 69°51'1.40"W | CNR | FALSE | FALSE |  |  | ME
| 1343 | 2025-10-10 15:02 | G | 2022-12-19 | Offshore Wind | WT | WND | 1200 | 1200 | 1200 | NA | MA | 2029-12-15 | 2029-07-15 | 2025-10-10 | National Grid 115 kV Pottersville | CNR | FALSE | FALSE |  |  | SEMA | Document Posted
| 1344 | 2025-10-17 15:09 | G | 2022-12-28 | Offshore Wind CNR only | WT | WND | 0 | 827 | 827 | NA | MA | 2025-10-15 | 2025-08-15 | 2025-10-11 | Eversource 345 kV West Barnstable Substation | CNR | FALSE | FALSE |  |  | SEMA
| 1345 | 2025-10-17 15:09 | G | 2023-01-10 | Battery Storage | OT | BAT | 75 | 75 | 75 | New London | CT | 2028-06-01 | 2028-04-01 | 2025-10-11 | Shunock 115kV Substation, Pendleton Hill Substation, North Stonington, CT 06359 | CNR | FALSE | FALSE |  | PD | CT
| 1346 | 2024-10-09 14:14 | G | 2023-01-12 | Battery Storage | OT | BAT | 196.468 | 196.468 | 196.468 | Hartford | CT | 2026-09-15 | 2026-09-08 | 2024-10-09 | Eversource, North Bloomfield Substation, 345kV BUS. | CNR | FALSE | FALSE |  | PD | CT | In Progress
| 1347 | 2025-06-16 16:15 | G | 2023-01-26 | Enfield DG Cluster | OT | SUN BAT | 18.77 | 18.77 | 18.77 | Hartford | CT | 2025-07-27 | 2023-12-31 | 2025-06-13 | Eversource Enfield 12C/Windsor Locks 14K | NA | FALSE | FALSE |  | PD | CT
| 1348 | 2025-06-16 16:16 | G | 2023-01-26 | Battery Storage | OT | BAT | 5.057 | 5.057 | 5.057 | Middlesex | CT | 2025-07-27 | 2025-06-25 | 2025-06-13 | Eversource Portland 21H | NA | FALSE | FALSE |  | PD | CT
| 1349 | 2025-06-16 16:17 | G | 2023-01-26 | Scitico DG Cluster | OT | SUN BAT | 5.2 | 5.2 | 5.2 | Hartford | CT | 2023-12-31 | 2023-07-01 | 2025-06-13 | Eversource Scitico 27H/27H1 | NA | FALSE | FALSE |  | PD | CT
| 1350 | 2023-08-24 16:18 | ETU | 2023-01-31 | 1200 MW Controllable ETU | NA | N/A | 1200 |  |  |  | RI | 2029-12-31 | 2029-09-01 | 2023-08-24 | POI at Rhode Island Energy's Kent county Substations, See assocation reference drawings | N/A | FALSE | FALSE |  | PD | RI
| 1351 | 2025-10-10 09:23 | G | 2023-02-06 | Battery Storage | OT | BAT | 156.24 | 156.24 | 156.24 | Fairfield | CT | 2027-10-01 | 2027-08-01 | 2025-10-10 | Owner: UI, Substation: Singer 345 kV | CNR | FALSE | FALSE |  | PD | SWCT
| 1352 | 2025-10-10 09:26 | G | 2023-02-06 | Battery Storage | OT | BAT | 262.68 | 262.68 | 262.68 | New Haven | CT | 2027-10-01 | 2027-09-01 | 2025-10-10 | POI: East Shore Substation 115 kV | CNR | FALSE | FALSE |  | PD | CT
| 1353 | 2025-10-10 09:23 | G | 2023-02-06 | Battery Storage | OT | BAT | 289.29 | 289.29 | 289.29 | New London | CT | 2027-10-01 | 2027-09-01 | 2025-10-10 | Montville 4J between 4J-11T-2 and 4J-12T-2. Interconnected with Montville Unit 6. New Montville Unit 6 Generator breaker will be installed for sync control. | CNR | FALSE | FALSE |  | PD | CT
| 1354 | 2023-04-13 16:07 | G | 2023-02-06 | Battery Storage | OT | BAT | 289.29 | 289.29 | 289.29 | Middlesex | CT | 2024-10-01 | 2024-09-01 | 2023-04-13 | POI between 5A-5T-2 and 5A-6T-2; Northeast Utilities 11631 Substation - Middletown | CNR | FALSE | FALSE |  | PD | CT
| 1355 | 2025-10-10 09:24 | G | 2023-02-06 | Battery Storage | OT | BAT | 136.32 | 136.32 | 136.32 | New Haven | CT | 2027-10-01 | 2027-09-01 | 2025-10-10 | POI is the Devon 115 kV Bus 2 between 7R-19T2 and 7R-23T-2 breakers | NR | FALSE | FALSE |  | PD | SWCT
| 1356 | 2024-10-15 09:46 | G | 2023-02-09 | (Offshore wind Increase (Q700 +Q1154) | WT | WND | 38.8 | 895 | 895 | NA | MA | 2026-10-30 | 2026-03-14 | 2024-10-14 | Eversource 345kV West Barnstable (921) | CNR | FALSE | FALSE |  | PD | SEMA
| 1357 | 2025-10-17 14:07 | G | 2023-02-16 | Solar Increase | PV | SUN | 5 | 152.045 | 152.045 | Hartford | CT | 2027-11-15 | 2027-10-01 |  | To interconnect at the POI of Gravel Pit Solar (QP 1030 + QP 1247), as an increase to QP 1030 and QP1247, the POI is the new Gravel Pit Solar substation at the new three-breaker ring bus on the 115 kV Connecticut Light & Power Company 1200 line between Barbour Hill and Windsor Locks. | NR | TRUE | TRUE |  | PD | CT |  | Document Posted |  |  | In Progress
| 1358 | 2025-10-17 15:10 | G | 2023-02-21 | Battery Storage | OT | BAT | 100 | 100 | 100 | Hartford | CT | 2026-07-31 | 2026-06-30 | 2025-10-11 | Tap on South Windsor to Manchester 115kV line. | CNR | FALSE | FALSE |  | PD | CT
| 1359 | 2025-06-16 16:18 | G | 2023-02-22 | Fuel Cell | FC | FC | 1.84 | 1.84 | 1.84 | Hartford | CT | 2024-12-31 | 2024-11-30 | 2025-06-13 | CLP Northwest Hartford 2N, Circuit 2N14 | NA | FALSE | FALSE |  |  | CT
| 1360 | 2025-06-16 16:19 | G | 2023-02-22 | Battery Storage | OT | BAT | 10 | 10 | 10 | Middlesex | CT | 2024-06-15 | 2024-06-01 | 2025-06-13 | CLP 11C Haddam, Circuit 11C13 | NA | FALSE | FALSE |  | PD | CT
| 1361 | 2023-09-08 13:05 | G | 2023-02-24 | Offshore Wind | WT | WND | 882 | 882 | 882 | NA | MA | 2030-02-15 | 2029-10-01 | 2023-09-08 | RIE, Jepson 115 kV Substation | CNR | FALSE | FALSE |  | PD | SEMA | In Progress
| 1362 | 2025-10-10 14:30 | G | 2023-02-24 | Battery Storage Increase (QP1238) | OT | BAT | 301.26 | 602.52 | 602.52 | Norfolk | MA | 2027-11-12 | 2027-06-25 | 2025-10-10 | Eversource's West Medway 345kV station | CNR | FALSE | FALSE |  | PD | SEMA
| 1363 | 2025-10-10 14:30 | G | 2023-03-01 | Battery Storage | OT | BAT | 301.26 | 301.26 | 301.26 | Hampden | MA | 2026-11-20 | 2026-06-12 | 2025-10-10 | Ludlow 345 kV station | CNR | FALSE | FALSE |  | PD | WMA | Document Posted
| 1364 | 2025-01-13 12:23 | G | 2023-03-01 | Battery Storage | OT | BAT | 401.68 | 401.68 | 401.68 | Rockingham | NH | 2026-11-20 | 2026-06-12 | 2025-01-13 | Timber Swamp Rd 345 kV station | CNR | FALSE | FALSE |  | PD | NH | Document Posted | Not Started |  |  |  | Under Study
| 1366 | 2024-08-19 12:42 | G | 2023-03-09 | Battery Storage | OT | BAT | 200.84 | 200.84 | 200.84 | Fairfield | CT | 2026-11-20 | 2026-06-12 | 2024-08-19 | Peaceable 115 kV station | CNR | FALSE | FALSE |  | PD | SWCT | Document Posted
| 1367 | 2023-12-05 08:46 | G | 2023-03-09 | Battery Storage | OT | BAT | 271.4 | 271.4 | 271.4 | Bristol | MA | 2027-04-01 | 2027-03-01 | 2023-11-30 | National Grid 115KV Line U6 between Pottersville and Bridgewater substations - approximately 6.1 circuit miles from Bridgewater substation | CNR | FALSE | FALSE |  | PD | SEMA | In Progress |  |  |  |  | Under Study
| 1368 | 2023-04-12 08:12 | G | 2023-03-09 | Battery Storage | OT | BAT | 240.8 | 240.8 | 240.8 | Essex | MA | 2027-04-01 | 2027-03-01 | 2023-04-12 | National Grid 115KV Line Q169 - Approximately 0.5 Miles from Lynn Substation | CNR | FALSE | FALSE |  | PD | BOST
| 1369 | 2025-06-16 16:20 | G | 2023-03-08 | Athens 115 kV SS - CMP Wyman Area Study | PV | SUN | 1.992 | 1.992 | 1.992 | Somerset | ME | 2024-12-31 |  | 2025-06-13 | CMP Athens substation, Circuit 827D2 | NA | TRUE | TRUE | CMP | PD | ME
| 1370 | 2025-08-13 10:46 | ETU | 2023-03-15 | 1200 MW non-controllable ETU - N to S flow only | NA | N/A | 1200 |  |  | Aroostook/Somerset | ME | 2028-06-01 | 2028-06-01 | 2025-08-13 | Transmission line connects between the new Aroostook station and Pittsfield station. Pittsfield 345 kV substation is located between the existing Orrington - Albion Road line in Somerset county at Lat/Long 44.795/-69.386. The Aroostook station will be located in Aroostook county at Lat/Long 45.7634/-68.0278 | N/A | FALSE | FALSE |  |  | ME
| 1371 | 2025-08-13 10:45 | ETU | 2023-03-15 | Non-controllable ETU - N to S flow only | NA | N/A |  |  |  | Somerset /Lincoln | ME | 2028-06-01 | 2028-06-01 | 2025-08-13 | New Pittsfield Substation lat/long 44.795/-69.386 Existing Coopers Mills 345 kV Station lat/long 44.2966/-69.556771 | N/A | FALSE | FALSE |  |  | ME
| 1372 | 2023-05-03 09:10 | ETU | 2023-03-15 | Non-controllable ETU - bi-directional | NA | N/A |  |  |  | Lincoln | ME | 2028-06-01 | 2028-06-01 | 2023-05-03 | New 345 kV Transmission Line from Maine Yankee 345 Substation (existing) to Coopers Mills 345 Substation (existing) | N/A | FALSE | FALSE |  |  | ME
| 1373 | 2025-10-10 14:31 | G | 2023-03-15 | Battery Storage Increase (QP1362) | OT | BAT | 140.48 | 743 | 743 | Norfolk | MA | 2027-11-12 | 2027-06-25 | 2025-10-10 | Eversource's West Medway 345kV station | CNR | FALSE | FALSE |  | PD | SEMA
| 1374 | 2025-10-17 15:10 | G | 2023-03-28 | Battery Storage | OT | BAT | 226 | 226 | 226 | Merrimack | NH | 2027-04-07 | 2027-03-31 | 2025-10-11 | Eversource 115 kV Line C196. | CNR | FALSE | FALSE |  | PD | NH | Document Posted
| 1375 | 2025-10-17 15:10 | G | 2023-03-29 | Wind | WT | WND | 217 | 217 | 217 | Aroostook | ME | 2026-12-09 | 2026-10-08 | 2025-10-11 | Pittsfield Station. Pittsfield 345 kV substation is located between the existing Orrington - Albion Road line (3023) near the town of Pittsfield. | CNR | FALSE | FALSE |  | PD | BHE
| 1376 | 2024-10-09 08:32 | G | 2023-03-29 | Battery Storage | OT | BAT | 325.7 | 325.7 | 325.7 | New Haven | CT | 2027-04-01 | 2027-03-01 | 2024-10-08 | 115KV Line #1640 between Devon 2 & Wallingford substations, approximately 2.15 circuit miles from Wallingford substation | CNR | FALSE | FALSE |  | PD | CT | Document Posted
| 1377 | 2023-12-12 15:43 | G | 2023-04-03 | Battery Storage | OT | BAT | 180 | 180 | 180 | Windsor | VT | 2027-04-08 | 2027-03-08 | 2023-12-12 | Vermont Electric Power Company, Coolidge 115 kV | CNR | FALSE | FALSE |  |  | VT | In Progress |  |  |  |  | Under Study
| 1378 | 2023-12-12 15:44 | G | 2023-04-03 | Battery Storage | OT | BAT | 105 | 105 | 105 | Windsor | VT | 2027-04-08 | 2027-03-08 | 2023-12-12 | Vermont Electric Power Company, Ascutney 115 kV. | CNR | FALSE | FALSE |  | PD | VT | In Progress |  |  |  |  | Under Study
| 1379 | 2025-10-17 15:10 | G | 2023-04-06 | Solar | PV | SUN | 218.4 | 218.4 | 218.4 | Aroostook | ME | 2028-10-31 | 2028-09-30 | 2025-10-11 | Pittsfield Station. Pittsfield 345 kV substation is located between the existing Orrington - Albion Road line (3023) near the town of Pittsfield. | CNR | FALSE | FALSE |  | PD | BHE
| 1380 | 2025-01-14 09:18 | G | 2023-04-06 | Fuel Cell CNR | FC | FC | 0 | 20.1 | 20.1 | Hartford | CT | 2024-12-12 | 2024-05-28 |  | The electrical connection where Eversource's 69 kV 680 line span from pole 2742 connects to the Farmington River Power Company's 680 line at pole 2743's insulator. | CNR | FALSE | FALSE |  |  | CT |  |  |  |  | Executed | In Service
| 1381 | 2025-03-27 07:11 | ETU | 2023-04-11 | 1200 MW (+/- 400 kV) HVDC External ETU | NA | N/A | 1200 |  |  | Grafton | NH | 2029-07-01 | 2029-01-01 | 2025-03-26 | In New Hampshire, the point of interconnection is near the old Monroe yard (AC capacitors and reactors and Phase II filters presently reside in this yard). The project will tie into the currently existing Comerford 230 kV substation. The northern section of the project will connect with the Hydro-Quebec system at the US-Canada border near Canaan, Vermont. | NI | FALSE | FALSE | ISO-NE | NA | NH | In Progress |  |  |  |  | Under Study
| 1382 | 2025-06-11 16:50 | G | 2023-04-11 | Vineyard Offshore Wind CNR | WT | WND | 0 | 843.2 | 843.2 | N/A | MA | 2025-12-30 | 2024-01-02 |  | Eversource (NSTAR) 115kV Barnstable Switch Station (958) | CNR | FALSE | FALSE | ISO-NE | NA | SEMA
| 1383 | 2023-12-15 16:34 | G | 2023-04-13 | Solar and Battery | PV | SUN BAT | 139 | 139 | 139 | Penoboscot | ME | 2028-12-31 | 2028-09-01 | 2023-12-15 | 44°46'22.13"N, 68°29'5.84"W new switching station to tie into Versant 115 kV line in Clifton | CNR | FALSE | FALSE | ISO-NE | NA | BHE | Document Posted | Not Started |  |  |  | Under Study
| 1384 | 2024-10-23 09:31 | G | 2023-04-26 | Battery Storage | OT | BAT | 300 | 300 | 300 | Worcester | MA | 2026-12-31 | 2026-09-01 | 2024-07-29 | National Grid's Pratts Junction - Sandy Pond L138W-2 line (115 kV). 2.92 miles from Pratts Junction and 11.95 miles from Sandy Pond (on 115 kV line). Coordinates: 42.493249051839484, -71.7028083287439 | CNR | FALSE | FALSE |  | PD | CMA | Document Posted | Not Started
| 1385 | 2024-10-23 09:30 | G | 2023-04-26 | Battery Storage | OT | BAT | 200 | 233 | 233 | Worcester | MA | 2026-12-31 | 2026-09-01 | 2024-07-29 | National Grid's: Bellows Fall (37.18 mi) - E. Winchendon Tap (2.07 mi) 115kV line (J136N) | NR | FALSE | FALSE |  | PD | CMA | In Progress
| 1386 | 2024-10-04 10:15 | G | 2023-04-26 | Battery Storage | OT | BAT | 100 | 100 | 100 | Berkshire | MA | 2026-12-31 | 2026-10-31 | 2024-10-04 | National Grid Berkshire - Plainfield 115 kV line Lat/Long: 42.49627608454711, -73.01015449707741 | CNR | FALSE | FALSE |  | PD | WMA | In Progress |  |  |  |  | Under Study
| 1387 | 2024-11-13 11:56 | ETU | 2023-04-27 | Non-controllable objective ETU to enable 1200 MW offshore wind/300 MW solar at Crystal Springs sub | NA | N/A |  |  |  | Plymouth | MA | 2030-12-30 | 2029-12-31 | 2024-11-12 | N/A | N/A | FALSE | FALSE |  | PD | SEMA | In Progress |  |  |  |  | Under Study
| 1388 | 2025-06-11 16:51 | G | 2023-04-28 | Wind CNR | WT | WND | 0 | 61.2 | 61.2 | Penobscot | ME | 2023-11-01 | 2023-11-01 |  | Keene Rd Substation via through a 115kV Line 55 & Line 56 from Rollins Mountain115/34.5kV | CNR | FALSE | FALSE |  |  | BHE |  | Not Required
| 1389 | 2025-06-11 16:52 | G | 2023-04-28 | Wind CNR | WT | WND | 0 | 58.14 | 58.14 | Washington | ME | 2023-11-01 | 2023-11-01 |  | Keene Rd Substation via through a 115kV Line 56 from Stetson Mountain115/34.5kV substation | CNR | FALSE | FALSE |  |  | BHE |  | Not Required
| 1390 | 2025-10-17 15:11 | G | 2023-04-28 | Wind CNR | WT | WND | 0 | 34.485 | 34.485 | Hancock | ME | 2023-11-01 | 2023-11-01 | 2025-10-11 | Bull Hill 115 kV Switching Station | CNR | FALSE | FALSE |  |  | BHE |  | Not Required
| 1391 | 2025-06-11 16:52 | G | 2023-04-28 | Wind CNR | WT | WND | 0 | 26.01 | 26.01 | Washington | ME | 2023-11-01 | 2023-11-01 |  | Keene Rd Substation via through a 115kV Line 56 from Stetson Mountain115/34.5kV substation | CNR | FALSE | FALSE |  |  | BHE |  | Not Required
| 1392 | 2025-09-23 14:11 | G | 2023-05-03 | Battery Storage | OT | BAT | 53.74 | 53.74 | 53.74 | New Haven | CT | 2026-09-15 | 2026-08-15 | 2025-09-23 | Latitude: 41.492036°, Longitude: -72.762080° -Owner: Connecticut Light and Power Company, Voltage 115 kV, Substation Name: North Wallingford 115 kV Station. | CNR | FALSE | FALSE |  | PD | CT
| 1393 | 2023-09-13 11:41 | G | 2023-05-03 | Gas Turbine | GT | NG | 233 | 233 | 233 | Fairfield | CT | 2026-06-01 | 2026-05-04 | 2023-09-13 | Eversource Middleriver substation 115kv | CNR | FALSE | FALSE |  | PD | SWCT
| 1394 | 2025-10-10 09:27 | G | 2023-05-04 | Battery Storage Addition | OT | BAT | 0 | 284.05 | 284.05 | Middlesex | CT | 2026-07-01 | 2026-05-01 | 2025-10-10 | POI between 10F-2T-2 and 10F-1T-1 breakers on the 345 kV bus; Northeast Utilities 11631 Substation - Middletown. | CNR | FALSE | FALSE |  | PD | CT
| 1395 | 2023-10-13 16:05 | G | 2023-05-05 | Battery Storage | OT | BAT | 20 | 20 | 20 | Hampshire | MA | 2027-06-30 | 2027-06-30 | 2023-05-22 | National Grid 115 kV Line 1134 | CNR | FALSE | FALSE |  | PD | WMA
| 1396 | 2025-10-08 09:18 | G | 2023-05-05 | Battery Storage | OT | BAT | 101.97 | 101.97 | 101.97 | Providence | RI | 2026-12-31 | 2026-07-31 | 2025-10-08 | 41.82919444, -71.52111667, Hartford 115 kV Substation | CNR | FALSE | FALSE |  | PD | RI | Document Posted
| 1397 | 2025-10-08 09:19 | G | 2023-05-05 | Battery Storage | OT | BAT | 100.24 | 100.2358 | 100.2358 | Worcester | MA | 2026-12-31 | 2026-07-31 | 2025-10-08 | 42.31815556, -71.98500556, Treasure Valley 115 kV Substation | CNR | FALSE | FALSE |  | PD | CMA | Document Posted
| 1398 | 2024-12-04 09:51 | G | 2023-05-08 | Battery Storage | OT | BAT | 101.97 | 101.97 | 101.97 | Worcester | MA | 2026-12-31 | 2026-07-31 | 2024-12-03 | A newly constructed three-breaker ring bus that will sectionalize National Grid’s Fitzwilliam to Flagg Pond 115 kV transmission line I-135 at about 7.48 miles from the East Winchendon Substation and 6.34 miles from the Flagg Pond Substation | CNR | FALSE | FALSE |  | PD | CMA | Document Posted | Not Started |  |  |  | Under Study
| 1399 | 2025-10-17 15:11 | G | 2023-05-18 | Battery Storage | OT | BAT | 92.438 | 92.438 | 92.438 | Hampden | MA | 2027-05-31 | 2027-03-31 | 2025-10-11 | The proposed POI is Buck Pond 115 kV substation, share gen leadline with QP1117. | CNR | FALSE | FALSE |  | PD | WMA
| 1400 | 2025-10-08 09:19 | G | 2023-05-18 | Battery Storage | OT | BAT | 101.97 | 101.97 | 101.97 | Hartford | CT | 2026-12-31 | 2026-07-31 | 2025-10-08 | 41.6317, -72.7289, Berlin 115 kV Substation | CNR | FALSE | FALSE |  | PD | CT
| 1401 | 2025-02-05 16:00 | ETU | 2023-06-07 | controllable 345 kV ETU - Brayton Point to Pottersville | NA | N/A |  |  |  | Bristol | MA | 2029-12-31 | 2029-06-30 | 2025-02-05 | N/A | N/A | FALSE | FALSE |  | PD | SEMA | In Progress
| 1402 | 2025-10-17 15:11 | G | 2023-06-07 | Battery Storage | OT | BAT | 171.6 | 171.6 | 171.6 | Hampden | MA | 2027-06-01 | 2027-05-01 | 2025-10-11 | POI interconnection coordinates: 42.068458, -72.462254 Interconnecting to the 115kV open bay at the NGRID West Hampden substation (connecting to T3's current position). | CNR | FALSE | FALSE |  | PD | WMA | Document Posted
| 1403 | 2025-01-13 17:35 | G | 2023-06-09 | Battery Storage | OT | BAT | 304.72 | 304.72 | 304.72 | Middlesex | CT | 2026-11-20 | 2026-06-12 | 2025-01-13 | Scoville 345kV substation | CNR | FALSE | FALSE |  | PD | CT | Not Started |  |  |  |  | Under Study
| 1404 | 2025-06-16 16:21 | G | 2023-06-13 | Individual @ French King | OT | SUN BAT | 2.2 | 2.2 | 2.2 | Franklin | MA |  | 2024-12-01 | 2025-06-13 | EE French King 21B | NA | FALSE | FALSE |  | PD | WMA
| 1405 | 2025-06-16 16:22 | G | 2023-06-13 | EE Group @ Southwick | OT | SUN BAT | 7 | 7 | 7 | Hampden | MA | 2024-12-31 | 2024-12-01 | 2025-06-13 | EE SOUTHWICK 29A | NA | FALSE | FALSE |  | PD | WMA
| 1406 | 2025-06-16 16:22 | G | 2023-06-13 | EE Group @ Doreen | OT | SUN BAT | 9.15 | 9.15 | 9.15 | Berkshire | MA | 2024-12-31 | 2024-12-01 | 2025-06-13 | EE Doreen 19A | NA | FALSE | FALSE |  | PD | WMA
| 1407 | 2025-06-16 16:23 | G | 2023-06-13 | EE Group @ Blandford | OT | SUN BAT | 28.936 | 28.926 | 28.936 | Hampshire | MA | 2024-12-31 | 2024-12-01 | 2025-06-13 | EE BLANDFORD 19J | NA | FALSE | FALSE |  | PD | WMA
| 1408 | 2025-06-16 16:24 | G | 2023-06-13 | Individual @ Partridge | OT | SUN BAT | 4 | 4 | 4 | Berkshire | MA | 2024-12-31 | 2024-12-01 | 2025-06-13 | EE Partridge 15E1 | NA | FALSE | FALSE |  | PD | WMA
| 1409 | 2025-06-16 16:24 | G | 2023-06-13 | Individual @ Montague | OT | BAT | 4.99 | 4.99 | 4.99 | Franklin | MA | 2024-12-31 | 2024-12-01 | 2025-06-13 | EE MONTAGUE 21C | NA | FALSE | FALSE |  | PD | WMA
| 1410 | 2025-06-16 16:25 | G | 2023-06-13 | Individual @ Amherst | OT | BAT | 2 | 2 | 2 | Hampshire | MA | 2024-12-31 | 2024-12-01 | 2025-06-13 | EE Amherst 17K | NA | FALSE | FALSE |  | PD | WMA
| 1411 | 2023-08-17 09:18 | ETU | 2023-06-20 | 1200 MW controllable ETU - unidirectional | NA | N/A | 1200 |  |  | Middlesex | MA | 2032-05-31 | 2031-12-31 | 2023-08-17 | Eversource Mystic 345 kV Substation | N/A | FALSE | FALSE |  | PD | BOST
| 1413 | 2025-06-16 16:26 | G | 2023-06-19 | Group @ Orchard | OT | SUN BAT | 4.04 | 4.04 | 4.04 | Hampden | MA | 2026-12-31 | 2026-12-31 | 2025-06-13 | EE Orchard 27A | NA | FALSE | FALSE |  | PD | WMA
| 1414 | 2025-06-16 16:26 | G | 2023-06-19 | Individual @ Piper | FC | FC | 4.1 | 4.1 | 4.1 | Hampden | MA | 2026-12-31 | 2026-12-31 | 2025-06-13 | EE Piper 21N | NA | FALSE | FALSE |  | PD | WMA
| 1415 | 2024-09-26 13:15 | G | 2023-06-20 | Battery Storage | OT | BAT | 261.9 | 261.9 | 261.9 | Worcester | MA | 2024-08-12 | 2024-07-12 | 2024-09-26 | POI interconnection coordinates: 42.471953, -71.734165 Interconnecting to National Grid 345kV line (line ID: 343) via line tap (approx. 8.5 mi from Wachusett Substation and 14.9 mi from Sandy Pond Substation). | CNR | FALSE | FALSE |  | PD | CMA | Not Started |  |  |  |  | Under Study
| 1416 | 2023-08-09 08:34 | G | 2023-06-26 | Battery Storage | OT | BAT | 196 | 196 | 196 | Hampshire | MA | 2027-05-19 | 2027-05-12 | 2023-08-08 | Eversource 115 KV Line Number 1447 | CNR | FALSE | FALSE |  | PD | WMA
| 1417 | 2024-12-11 13:07 | G | 2023-06-26 | Battery Storage | OT | BAT | 300 | 300 | 300 | Windham | CT | 2028-06-01 | 2028-04-01 | 2024-12-11 | Eversource 115kV Killingly Substation | CNR | FALSE | FALSE |  | PD | CT | In Progress |  |  |  |  | Under Study
| 1418 | 2023-12-05 08:47 | G | 2023-06-27 | Battery Storage | OT | BAT | 108.7 | 108.7 | 108.7 | Providence | RI | 2027-04-01 | 2027-03-01 | 2023-11-30 | 115KV Line Q143S-2 between Woonsocket and Franklin Square substations, approximately 10 miles from Woonsocket substation. | CNR | FALSE | FALSE |  | PD | RI | In Progress |  |  |  |  | Under Study
| 1419 | 2024-03-06 12:41 | G | 2023-06-28 | Battery Storage | OT | BAT | 108.7 | 108.7 | 108.7 | Bristol | MA | 2027-04-01 | 2027-03-01 | 2024-03-06 | National Grid 115KV Bates Street Substation | CNR | FALSE | FALSE |  | PD | SEMA | Not Started |  |  |  |  | Under Study
| 1420 | 2025-10-17 15:06 | G | 2023-06-29 | Battery Storage | OT | BAT | 175.097 | 175.097 | 175.097 | New London | CT | 2027-12-31 | 2027-09-30 | 2025-10-11 | Existing Eversource 115kV structure on Line 1410, West of 39 Dock Road (41.430126, -72.103424). | CNR | FALSE | FALSE |  | PD | CT
| 1421 | 2024-01-26 16:59 | G | 2023-07-06 | Battery Storage | OT | BAT | 175.67 | 175.67 | 175.67 | Bristol | MA | 2024-09-08 | 2024-08-08 | 2024-01-26 | 41.987864, -71.265095 Tapping to National Grid 115kV line C181 | CNR | FALSE | FALSE |  | PD | SEMA | In Progress |  |  |  |  | Under Study
| 1422 | 2025-04-25 10:03 | G | 2023-07-07 | Battery Storage | OT | BAT | 326 | 326 | 326 | Hartford | CT | 2029-02-02 | 2028-12-01 | 2025-04-25 | Barbour Hill Substation 115kV direct connection ( 41.854810, -72.528106) | CNR | FALSE | FALSE |  | PD | CT | Not Started |  |  |  |  | Under Study
| 1423 | 2024-09-25 16:46 | G | 2023-07-10 | Battery Storage | OT | BAT | 121.6 | 121.6 | 121.6 | Worcester | MA | 2026-09-01 | 2026-06-01 | 2024-09-04 | The Primary Point of Interconnection will be a new 3-breaker ring bus located on the IC’s property which will connect to National Grid T-Line H160 (Northboro Rd to Hudson) at 115 KV. The approximate line-break location will be 0.26 miles from Northboro Rd substation and 7.92 miles from Hudson Substation. The Alternative POI will be a new 3-breaker ring bus located on the IC’s property which connects to T-Line N166 (Northboro Rd to N.Marloboro) at 115 KV. | CNR | FALSE | FALSE |  | PD | CMA | In Progress |  |  |  |  | Under Study
| 1424 | 2023-08-15 14:32 | G | 2023-07-10 | Battery Storage | OT | BAT | 41.2 | 41.2 | 41.2 | Worcester | MA | 2026-09-01 | 2026-06-01 | 2023-08-15 | New England Power Company Westminster Switching Station (69KV Line) | CNR | FALSE | FALSE |  | PD | CMA
| 1425 | 2024-09-04 13:42 | G | 2023-07-10 | Battery Storage | OT | BAT | 151.596 | 151.596 | 151.596 | Hampden | MA | 2026-10-01 | 2026-07-01 | 2024-09-04 | Western Massachusetts Electric Co South Agawam Switching Station (115 kv) via a new breaker bay | CNR | FALSE | FALSE |  | PD | WMA | Not Started |  |  |  |  | Under Study
| 1426 | 2024-12-10 17:23 | G | 2023-07-14 | Battery Storage | OT | BAT | 528.75 | 528.75 | 529.61 | Bristol | MA | 2028-03-31 | 2028-03-15 | 2024-12-10 | Primary POI is a direct tap into the Pottersville substation in Somerset, MA utilizing shared interconnection facilities with QP1412. Secondary POI is a direct tap into the Pottersville substation. Tertiary POI is a customer substation with a tap into the "Bell Rock Road 118 to Pottersville Station 115 kV" line, 1/2 mile east of the Pottersville substation. | CNR | FALSE | FALSE |  | PD | SEMA | Not Started |  |  |  |  | Under Study
| 1429 | 2025-10-17 15:11 | G | 2023-08-08 | Wind | WT | WND | 197.4 | 197.4 | 197.4 | Aroostook | ME | 2028-10-01 | 2028-05-01 | 2025-10-11 | CMP Orrington - Albion Road 345kV line | CNR | FALSE | FALSE |  | PD | BHE
| 1430 | 2025-10-17 15:12 | G | 2023-08-09 | Battery Storage | OT | BAT | 237.545 | 237.545 | 237.545 | Bristol | MA | 2027-10-17 | 2027-09-16 | 2025-10-11 | 115 kV line C181N - Circuit 1. Alternate POI : 345 kV line 327 - Circuit 1 | CNR | FALSE | FALSE |  | PD | RI
| 1431 | 2025-06-16 16:27 | G | 2023-08-09 | Battery Storage | OT | BAT | 7 | 7 | 7 | Hartford | CT | 2024-12-29 | 2024-12-01 | 2025-06-13 | Eversource Northwest Hartford 2N | NA | FALSE | FALSE |  | PD | CT
| 1432 | 2024-08-15 11:21 | G | 2023-08-11 | Battery Storage | OT | BAT | 256.53 | 256.53 | 256.98 | New London | CT | 2028-09-30 | 2028-09-15 | 2024-08-15 | Direct tap into the 115kV Uncasville Substation | CNR | FALSE | FALSE |  | PD | CT |  | In Progress
| 1433 | 2024-06-20 12:12 | G | 2023-08-15 | Battery Storage | OT | BAT | 100 | 100 | 100 | Hampden | MA | 2027-12-31 | 2027-10-31 | 2024-06-19 | Lat Long is 42.13610456666797, -72.27784889556564 This is the National Grid's Little Red Road - Palmer 115 kV line (W-175). The POI is approximately 1.56 miles (23.9%) from the Palmer substation and 4.97 miles (76.1%) to the Little Rest Road substation | CNR | FALSE | FALSE |  | PD | WMA | Not Started
| 1434 | 2024-06-20 12:13 | G | 2023-08-15 | Battery Storage | OT | BAT | 160 | 160 | 160 | Franklin | MA | 2027-12-31 | 2027-10-31 | 2024-06-19 | Lat Long is 42.6254349775399, -72.56881378900127 The NG Harriman - Montague 115 kV line (Y-177) Distances: 3.35 miles to Montague and 20.67 miles to Harriman | CNR | FALSE | FALSE |  | PD | WMA | Not Started
| 1435 | 2024-11-13 11:57 | ETU | 2023-08-21 | Non-controllable objective ETU to enable additional 1200 MW (to QP1309) injection near Millstone sub | NA | N/A | 1200 |  |  | New London | CT | 2030-12-30 | 2030-05-01 | 2024-11-12 | N/A | N/A | FALSE | FALSE |  | PD | CT |  | Not Started |  |  |  | Under Study
| 1436 | 2025-10-17 15:12 | G | 2023-08-29 | Battery Storage | OT | BAT | 300 | 300 | 300 | New London | CT | 2028-06-01 | 2028-04-01 | 2025-10-11 | Line tap of the Eversource 1235 115 kV Line approximately 1200’ from Uncasville 115kV SS | CNR | FALSE | FALSE |  | PD | CT
| 1437 | 2025-09-30 11:33 | G | 2023-08-31 | Battery Storage | OT | BAT | 103.32 | 103.32 | 103.5 | New London | CT | 2029-02-01 | 2029-01-15 | 2025-09-30 | Montville to Gales Ferry 115kV line 1787, approximately 0.5mi north of Montville Substation | CNR | FALSE | FALSE |  | PD | CT
| 1438 | 2023-12-12 09:15 | G | 2023-10-10 | Solar | PV | SUN | 15.58 | 15.58 | 15.58 | York | ME | 2024-12-31 | 2024-12-15 | 2023-12-11 | CMP 34.5 kV, Section 182 | CNR | FALSE | FALSE |  | PD | ME
| 1439 | 2024-10-29 16:12 | G | 2023-09-18 | Battery Storage | OT | BAT | 151.306 | 151.306 | 151.306 | Hampshire | MA | 2027-05-31 | 2027-03-26 | 2024-10-29 | The Primary Point of Interconnection will be a new 3-breaker ring bus located on the IC’s property which connects to Eversource T line 1113 (Fairmont to Tillson) at 115 KV. The break in the line will take place 4.52 miles from the Fairmont Substation and 10.55 miles from the Tillson substation. The distance from the line break to the 3-breaker ring bus located on the IC’s property will be approximately 0.22 miles. The approximate latitude/longitude coordinates of the 3-breaker ring bus is 42.249111, -72.533752. The Alternative Point of Interconnection will be a new 3-breaker ring bus located on the IC’s property which connects to Eversource T line 1134 (Fairmont to Five Corners) at 115 KV. The break in the line will take place 4.52 miles from the Fairmont Substation and 0.11 miles from the Five Corners Substation. The distance from the line break to the 3-breaker ring bus located on the IC’s property will be approximately 0.22 miles. The approximate latitude/longitude coordinates of the 3-breaker ring bus is 42.249111, -72.533752. | CNR | FALSE | FALSE |  | BL | WMA | Document Posted |  |  |  |  | Under Study
| 1440 | 2025-04-10 09:23 | G | 2023-09-18 | Battery Storage | OT | BAT | 151.556 | 151.556 | 151.556 | Hampden | MA | 2027-05-31 | 2027-03-26 | 2025-04-09 | The Primary Point of Interconnection will be a new 3-breaker ring bus located on the IC’s property connecting to Eversource T line 1314 (Agawam to Chicopee) at 115 KV. The POI substation would be 3.39 miles from the Chicopee Substation and 3.66 miles from the Agawam substation. The electric line placement percentage from the Chicopee substation is 48%. Alternative POI: The Alternative Point of Interconnection will be a new 3-breaker ring bus located on the IC’s property connecting to T line 1904 (Piper to Memorial Drive) at 115 KV | CNR | FALSE | FALSE |  | PD | WMA | Document Posted | Not Started
| 1441 | 2023-11-02 12:17 | G | 2023-09-18 | Battery Storage | OT | BAT | 103 | 103 | 103 | Hampden | MA | 2027-05-31 | 2027-03-26 | 2023-11-02 | Eversource Southwick Substation (115 KV) | CNR | FALSE | FALSE |  | PD | WMA
| 1442 | 2024-09-04 13:41 | G | 2023-09-18 | Battery Storage | OT | BAT | 151.576 | 151.576 | 151.576 | Bristol | MA | 2027-05-31 | 2027-03-31 | 2024-09-04 | Primary: Eversource 115 kV Cross Road Line 111, alternate: line 109 | CNR | FALSE | FALSE |  | PD | SEMA | Not Started |  |  |  |  | Under Study
| 1443 | 2023-11-20 11:57 | G | 2023-09-20 | Battery Storage | OT | BAT | 200 | 202.6914 | 202.6914 | Rockingham | NH | 2026-12-30 | 2026-12-01 | 2023-11-20 | Project will interconnect will be a shared facility at QP-1428's POI - via tap at existing 115 kV line between Eversource 115kV Scobie Pond - Pulpit Rock Line A184 115kV. | CNR | FALSE | FALSE |  | PD | NH
| 1444 | 2023-11-06 13:51 | G | 2023-09-21 | Battery Storage | OT | BAT | 250 | 250 | 250 | Norfolk | MA | 2027-09-15 | 2027-07-15 | 2023-11-06 | National Grid’s 115kV South Wrentham substation | NR | FALSE | FALSE |  | PD | SEMA
| 1445 | 2023-12-15 16:31 | G | 2023-09-21 | Solar | PV | SUN | 51.5 | 51.5 | 51.5 | Somerset | ME | 2027-12-15 | 2027-10-15 | 2023-12-15 | The CMP 115 kV Chase Pond substation being built on Section 222. | CNR | FALSE | FALSE |  |  | ME
| 1446 | 2025-06-16 16:28 | G | 2023-09-29 | Raymond 115 kV SS - Raymond Area DG Study | PV | SUN | 9.949 | 9.949 | 9.949 | Cumberland | ME | 2025-06-20 | 2024-09-01 | 2025-06-13 | CMP Raymond 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
| 1447 | 2025-06-16 16:29 | G | 2023-09-29 | Leeds 115 kV SS - Sturtevant-Leeds-Livermore-Ludden-Riley Area DG Study | PV | SUN | 4.999 | 4.999 | 4.999 | Androscoggin | ME | 2024-09-01 | 2024-09-01 | 2025-06-13 | CMP Leeds 115 kV Substation | NA | FALSE | TRUE | CMP | PD | ME
| 1448 | 2025-06-16 16:30 | G | 2023-09-29 | Ludden Lane 115 kV SS - Sturtevant-Leeds-Livermore-Ludden-Riley Area DG Study | PV | SUN | 1.999 | 1.999 | 1.999 | Oxford | ME | 2024-06-01 | 2024-06-01 | 2025-06-13 | CMP Ludden Lane 115 kV Substation | NA | FALSE | TRUE | CMP | PD | ME
| 1449 | 2025-06-16 16:34 | G | 2023-09-29 | Sturtevant 115 kV SS - Sturtevant-Leeds-Livermore-Ludden-Riley Area Study | PV | SUN | 4.99 | 4.99 | 4.99 | Franklin | ME | 2024-12-30 | 2024-06-01 | 2025-06-13 | CMP Sturtevant 115 kV Substation | NA | FALSE | TRUE | CMP | PD | ME
| 1450 | 2025-01-08 09:39 | G | 2023-09-29 | Woodstock 115 kV SS - Roxbury-Rumford-Woodstock Area DG Study | PV | SUN | 1.623 | 1.623 | 1.623 | Oxford | ME | 2024-12-15 | 2024-12-15 | 2025-01-07 | CMP Woodstock 115 kV Substation | NA | FALSE | TRUE | CMP | PD | ME
| 1451 | 2024-07-30 11:46 | G | 2023-10-05 | Offshore wind | WT | WND | 1309 | 1309 | 1309 | NA | MA | 2030-09-27 | 2029-12-27 | 2024-07-30 | Primary: Pottersville 115kV Substation, Secondary: Bridgewater 345kV Substation | CNR | FALSE | FALSE |  | PD | SEMA | Not Started |  |  |  |  | Under Study
| 1452 | 2024-08-12 10:26 | G | 2023-10-05 | Battery Storage | OT | BAT | 151.286 | 151.286 | 151.286 | Worcester | MA | 2027-05-28 | 2027-03-26 | 2024-08-08 | The Primary Point of Interconnection will be a new 3-breaker-ring bus located on the IC’s property (Lat, long: 42.322909, -71.984654) which connects to T line A127-4 at 115 KV (Barre Substation to Paxton Substation). The POI distance following the T Line is approximately 7.66 miles from the Barre Substation and approximately 3.04 miles from the Paxton Substation. The Alternative Point of Interconnection will be a new 3-breaker ring bus located on the IC’s property (Lat, long: 42.322909, -71.984654) which connects to T line B128-5 at 115 KV (Treasure Valley Substation to Barre Substation). The POI distance following the T Line is approximately 0.2 miles from the Treasure Valley Substation and 7.66 miles from the Barre Substation. | CNR | FALSE | FALSE |  | PD | CMA | In Progress |  |  |  |  | Under Study
| 1453 | 2025-01-08 09:40 | G | 2023-10-02 | Coopers Mills 115 kV SS - Midcoast Area DG Study | PV | SUN | 2.88 | 2.88 | 2.88 | Lincoln | ME | 2024-12-31 | 2024-12-31 | 2025-01-07 | CMP Coopers Mills 115 kV Substation | NA | FALSE | TRUE | CMP | PD | ME
| 1454 | 2025-06-16 16:34 | G | 2023-10-02 | Newcastle 115 kV SS - Midcoast Area DG Study | PV | SUN | 11.65 | 11.65 | 11.65 | Cumberland/Kennedbec/Sagadahoc/Lincoln | ME | 2024-12-31 | 2024-12-31 | 2025-06-13 | CMP Newcastle 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
| 1455 | 2025-01-08 09:43 | G | 2023-10-02 | Highland/Park St 115 kV SS - Midcoast Area DG Study | PV | SUN | 2 | 2 | 2 | Knox | ME | 2024-12-31 | 2024-12-31 | 2025-01-07 | CMP Highland/Park St 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
| 1456 | 2025-06-16 16:35 | G | 2023-10-02 | Topsham 115 kV SS - Midcoast Area DG Study | PV | SUN | 1.98 | 1.98 | 1.98 | Waldo/Sagadahoc | ME | 2024-12-31 | 2024-12-31 | 2025-06-13 | CMP Topsham 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
| 1457 | 2025-06-16 16:36 | G | 2023-10-02 | Mason 115 kV SS - Midcoast Area DG Study | PV | SUN | 3.94 | 3.94 | 3.94 | Lincoln | ME | 2024-12-31 | 2024-12-31 | 2025-06-13 | CMP Mason 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
| 1458 | 2025-01-08 09:46 | G | 2023-10-02 | Lincolnville 115 kV SS - Midcoast Area DG Study | PV | SUN | 4.95 | 4.95 | 4.95 | Lincoln | ME | 2024-12-31 | 2024-12-31 | 2025-01-07 | CMP - Lincolnville 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
| 1459 | 2025-01-08 09:47 | G | 2023-10-02 | Bath 115 kV SS - Midcoast Area DG Study | PV | SUN | 3.43 | 3.43 | 3.43 | Lincoln | ME | 2024-12-31 | 2024-12-31 | 2025-01-07 | CMP Bath 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
| 1461 | 2025-10-17 15:12 | G | 2023-10-18 | Battery Addition | OT | KER BAT | 1.498 | 165.38 | 169.25 | Rockingham | NH | 2028-09-01 | 2028-08-01 | 2025-10-11 | 400 Gosling Road, Portsmouth, New Hampshire. The project will interconnect to the 115kV Bus 1 & 2 at Schiller Substation, directly adjacent to the project’s proposed location on the former coal storage space directly to the southeast of Schiller Substation. | CNR | FALSE | FALSE |  | PD | NH
| 1462 | 2024-02-20 09:44 | G | 2023-11-27 | Battery Storage | OT | BAT | 115 | 115 | 115 | Norfolk | MA | 2029-12-20 | 2029-11-25 | 2024-02-20 | Tap on Belmont 115 kV - Stoughton Tap 115 kV Line with three breaker ring bus scheme. POI is located at the 1.75 miles from Stoughton 115kV substation and the 2.8 miles from Belmont Substation. Latitude: 42.09564, Longitude: -71.08200 | CNR | FALSE | FALSE |  | PD | SEMA
| 1463 | 2025-06-16 16:37 | G | 2023-11-22 | EE Valley DG Group Study | PV | SUN | 8 | 8 | 8 | Plymouth | MA | 2026-12-31 | 2026-12-31 | 2025-06-13 | EE Valley 715 substation | NA | FALSE | FALSE |  | PD | SEMA
| 1464 | 2025-10-17 15:13 | G | 2023-12-05 | Wind Repower | WT | WND | 0 | 35.2 | 35.2 | Caledonia | VT | 2026-12-31 | 2026-11-16 | 2025-10-11 | VELCO, 115kV, Sheffield Substation 44.663509, -72.123160 | CNR | FALSE | FALSE |  | PD | VT
| 1465 | 2025-06-16 16:37 | G | 2023-12-05 | Augusta E/Puddledock/Bowman St 115 kV SS - Midcoast Area DG Study | OT | SUN BAT | 18.61 | 18.61 | 18.61 | Kennebec | ME | 2024-12-31 | 2024-12-31 | 2025-06-13 | CMP Augusta E/Puddledock/Bowman St 115 kV substation | NA | TRUE | TRUE | CMP | PD | ME
| 1466 | 2025-06-16 16:38 | G | 2023-12-05 | Winslow-County Rd Lakewood 115 kV SS - Winslow-County Rd-Lakewood 2 DG Study | PV | SUN | 20.97 | 20.97 | 20.97 | Kennebec/Somerset | ME | 2024-12-31 | 2024-12-31 | 2025-06-13 | CMP Winslow-County Rd Lakewood 115 kV substation | NA | TRUE | TRUE | CMP | PD | ME
| 1467 | 2025-10-06 14:59 | G | 2023-12-12 | Battery Storage | OT | BAT | 69.4 | 69.4 | 69.4 | Worcester | MA | 2026-10-31 | 2026-09-30 | 2025-10-06 | National Grid 69KV Meadow Street 552 Substation | CNR | FALSE | FALSE |  | PD | CMA | Document Posted
| 1468 | 2024-01-26 17:05 | G | 2023-12-12 | Battery Storage | OT | BAT | 76 | 76 | 76 | Plymouth | MA | 2027-01-31 | 2026-11-30 | 2024-01-26 | The Primary Point of Interconnection will be located on the IC’s property (Lat, long: 41°58'7.22"N, 71° 1'18.59"W) by tapping the 115-kV Line U6-4 (Bridgewater-Raynham) at approx. 7,87 Km from Bridgewater Substation. The Alternative Point of Interconnection will be a direct interconnection to the 115-kV bus at Bridgewater Substation owned by MA_NGRID. | CNR | FALSE | FALSE |  | PD | SEMA
| 1469 | 2024-02-15 10:30 | G | 2023-12-12 | Battery Storage | OT | BAT | 190 | 190 | 190 | Worcester | MA | 2027-01-31 | 2026-11-30 | 2024-02-15 | The Primary Point of Interconnection will be located on the IC’s property (Lat, long: 42°21'44.53"N, 72° 2'22.57"W) by tapping the 115-kV Line A127-4 (Barre-Paxton) at approx. 6km from Barre Substation owned by MA_NGRID. | CNR | FALSE | FALSE |  | PD | CMA
| 1470 | 2024-02-01 17:17 | G | 2023-12-12 | Battery Storage | OT | BAT | 237.6 | 237.6 | 237.6 | Hartford | CT | 2027-01-31 | 2026-11-30 | 2024-02-01 | The Primary Point of Interconnection will be located on the IC’s property (Lat, long: 41°49'19.50"N, 72°43'23.49"W) by tapping the 115-kV Line 1751 (Bloomfield_J-NW.Hartford) at approx. 0.98 km from Bloomfield Substation owned by CT_CL&P. The Alternative Point of Interconnection will be a direct interconnection to the 115-kV bus at Bloomfield Substation owned by CT_CL&P. | CNR | FALSE | FALSE |  | PD | CT
| 1471 | 2024-02-01 17:24 | G | 2023-12-12 | Battery Storage | OT | BAT | 134.7 | 134.7 | 134.7 | New Haven | CT | 2027-01-31 | 2026-11-30 | 2024-02-01 | The Primary Point of Interconnection will be located on the IC’s property (Lat, long: 41°28'9.40"N, 73° 7'52.44"W) by tapping the 115-kV Line 1619 (Towantic-Stevenson) at approx. 1.8 Km from Towantic Substation. The Alternative Point of Interconnection will be a direct interconnection to the 115-kV bus at Oxford Substation owned by CT_CL&P. | CNR | FALSE | FALSE |  | PD | CT
| 1472 | 2024-01-26 08:54 | G | 2023-12-12 | Battery Storage | OT | BAT | 108 | 108 | 108 | Providence | RI | 2027-01-31 | 2026-11-30 | 2024-01-09 | The Primary Point of Interconnection will be a direct interconnection to the 115-kV bus at Highland Park Substation owned by RI_NGRID. The Alternative Point of Interconnection will be located on the IC’s property (Lat, long: 41°59'46.60"N, 71°28'16.01"W) by tapping the 115-kV Line J16 (Riverside-Highland Park) at approx. 0.27 km from Highland Park Substation. | CNR | FALSE | FALSE |  | PD | RI
| 1473 | 2024-01-26 10:25 | G | 2023-12-14 | Battery Storage | OT | BAT | 202.07 | 202.07 | 202.07 | Hampden | MA | 2028-04-04 | 2028-02-23 | 2024-01-22 | MA_WMECO Blandford 115kV substation | CNR | FALSE | FALSE |  | PD | WMA
| 1474 | 2025-06-16 16:38 | G | 2023-12-18 | NG NEMA Group DER Study | OT | BAT | 9.982 | 9.982 | 9.982 | Essex | MA | 2025-12-31 | 2025-12-31 | 2025-06-13 | NG King St T3 | NA | FALSE | FALSE |  | PD | BOST
| 1475 | 2025-06-16 16:39 | G | 2023-12-18 | NG NEMA Group DER Study | OT | SUN BAT | 4.998 | 4.998 | 4.998 | Essex | MA | 2025-12-31 | 2025-12-31 | 2025-06-13 | NG Newbury 60-4T | NA | FALSE | FALSE |  | PD | BOST
| 1476 | 2025-06-16 16:40 | G | 2023-12-18 | NG NEMA Group DER Study | OT | BAT | 5 | 5 | 5 | Middlesex | MA | 2025-12-31 | 2025-12-31 | 2025-06-13 | NG East Tewksbury T1 | NA | FALSE | FALSE |  | PD | BOST
| 1477 | 2025-06-16 16:41 | G | 2023-12-19 | NG DG @ Sykes Road | OT | BAT | 9.998 | 9.998 | 9.998 | Bristol | MA | 2025-12-31 | 2025-12-31 | 2025-06-13 | NG Sykes Rd 282TR (M13N) | NA | FALSE | FALSE |  | PD | SEMA
| 1478 | 2025-10-10 10:04 | G | 2023-12-28 | Battery Storage | OT | BAT | 50 | 50 | 50 | Hampden | MA | 2028-05-25 | 2028-02-24 | 2025-10-10 | A new 115kV POI Station tie-in to the Pleasant-Blandford Line adjacent to the existing Eversource Blanford Substation | CNR | FALSE | FALSE |  | PD | WMA
| 1479 | 2025-01-08 09:52 | G | 2023-12-29 | CMP West Buxton 115 kV SS - Louden-Biddeford Area DG Study | PV | SUN | 4.5 | 4.5 | 4.5 | York | ME | 2024-12-31 | 2024-12-31 | 2025-01-07 | CMP West Buxton 115 kV Substation | NA | TRUE | TRUE | CMP |  | ME
| 1480 | 2025-06-16 16:44 | G | 2023-12-29 | CMP Biddeford IP 115 kV SS - Louden-Biddeford Area DG Study | PV | SUN | 4.95 | 4.95 | 4.95 | York | ME | 2024-12-31 | 2024-12-31 | 2025-06-13 | CMP Biddeford IP 115 kV Substation | NA | TRUE | TRUE | CMP |  | ME
| 1481 | 2025-06-16 16:44 | G | 2023-12-29 | CMP Vallee Lane 115 kV SS - Louden-Biddeford Area DG Study | PV | SUN | 1.99 | 1.99 | 1.99 | Cumberland | ME | 2024-12-31 | 2024-12-31 | 2025-06-13 | CMP Vallee Lane 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
| 1482 | 2025-06-16 16:45 | G | 2023-12-29 | CMP Spring St 115 kV SS - Greater Portland Area DG Study | PV | SUN | 4.98 | 4.98 | 4.98 | Cumberland | ME | 2024-12-31 | 2024-12-31 | 2025-06-13 | CMP Spring St 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
| 1483 | 2025-06-16 16:45 | G | 2023-12-29 | CMP Elm St 115 kV SS - Greater Portland Area DG Study | PV | SUN | 4.97 | 4.97 | 4.97 | Cumberland | ME | 2024-12-31 | 2024-12-31 | 2025-06-13 | CMP Elm St 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
| 1484 | 2025-06-16 16:46 | G | 2023-12-29 | CMP Moshers/Prides Corner 115 kV SS - Greater Portland Area DG Study | OT | SUN WAT | 3.99 | 3.99 | 3.99 | Cumberland | ME | 2024-12-31 | 2024-12-31 | 2025-06-13 | CMP Moshers/Prides Corner 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
| 1485 | 2024-08-07 16:19 | G | 2024-01-02 | Offshore Wind CNR | WT | WND | 0 | 1200 | 1200 | NA | CT | 2031-05-31 | 2031-01-31 | 2024-08-07 | Eversource (CL&P) 345kV Montville Substation | CNR | FALSE | FALSE |  |  | CT
| 1486 | 2025-01-24 13:57 | G | 2024-01-02 | Battery Storage | OT | BAT | 300 | 300 | 300 | New Haven | CT | 2027-06-30 | 2027-04-30 | 2025-01-24 | Bunker Hill 115kV substation | CNR | FALSE | FALSE |  | PD | SWCT | In Progress |  |  |  |  | Under Study
| 1487 | 2025-06-16 16:46 | G | 2024-01-09 | EE CT DG Group Study | PV | SUN | 5 | 5 | 5 | New Haven | CT | 2024-12-31 | 2024-12-31 | 2025-06-13 | EE Oxford 26N | NA | FALSE | FALSE |  | PD | CT
| 1488 | 2025-10-21 17:17 | G | 2024-01-11 | Offshore Wind | WT | WND | 1275 | 1275 | 1275 | NA | CT | 2031-09-01 | 2031-03-01 | 2025-10-09 | Intersection of 345 kV transmission lines 364, 371, 383, 310, and 348 | CNR | FALSE | FALSE |  | PD | CT
| 1489 | 2025-06-16 16:47 | G | 2024-01-17 | EE Mansfield Center DG Cluster | OT | SUN BAT | 10.799 | 10.799 | 10.799 | Tolland | CT | 2025-07-27 | 2024-12-29 | 2025-06-13 | EE Mansfield 12J | NA | FALSE | FALSE |  | PD | CT
| 1490 | 2025-06-16 16:47 | G | 2024-01-17 | EE Mansfield Center DG Cluster | PV | SUN | 19.975 | 19.975 | 19.975 | Tolland | CT | 2024-12-31 | 2024-06-30 | 2025-06-13 | EE Card St 11F | NA | FALSE | FALSE |  | PD | CT
| 1491 | 2025-06-16 16:48 | G | 2024-01-26 | Canton 470 110A - 2023 EE GB ASO | OT | BAT | 4.99 | 4.99 | 4.99 | Norfolk | MA | 2026-12-31 | 2026-12-31 | 2025-06-13 | Eversource Canton 470 110A | NA | FALSE | FALSE |  | PD | SEMA
| 1492 | 2025-06-16 16:49 | G | 2024-01-26 | Medway 65 110A - 2023 EE GB ASO | OT | BAT | 4.948 | 4.948 | 4.948 | Middlesex | MA | 2026-12-31 | 2026-12-31 | 2025-06-13 | Eversource Medway 65 110A | NA | FALSE | FALSE |  | PD | SEMA
| 1493 | 2025-06-16 16:51 | G | 2024-01-26 | Medway 65 110B - 2023 EE GB ASO | OT | SUN BAT | 3.9 | 3.9 | 3.9 | Middlesex | MA | 2026-12-31 | 2026-12-31 | 2025-06-13 | Eversource Medway 65 110B | NA | FALSE | FALSE |  | PD | SEMA
| 1494 | 2025-06-16 16:52 | G | 2024-01-26 | Walpole 146 110A - 2023 EE GB ASO | OT | SUN BAT | 4.99 | 4.99 | 4.99 | Norfolk | MA | 2026-12-31 | 2026-12-31 | 2025-06-13 | Eversource Walpole 146 110A | NA | FALSE | FALSE |  | PD | SEMA
| 1496 | 2025-10-17 15:13 | G | 2024-02-07 | Battery Storage addition(QP1192) | OT | SUN BAT | 101.1158 | 202.2316 | 202.2316 | Hartford | CT | 2027-12-15 | 2027-10-15 | 2025-10-11 | To interconnect at the POI of Broadleaf Storage, via a shared facility. It is connected as a tap at existing 345 kV line between N. Bloomfield to Agawam Line. POI is approximately 3.6 mi north of N. Bloomfield and 11.5 mi south of Agawam. | CNR | FALSE | FALSE |  | PD | CT
| 1497 | 2024-05-14 14:31 | G | 2024-02-07 | Solar | PV | SUN | 68 | 68 | 68 | Penobscot | ME | 2028-07-15 | 2028-04-15 | 2024-05-14 | Tap on Enfield ME – Passadumkeag 115kV line | CNR | FALSE | FALSE |  | PD | BHE
| 1498 | 2025-08-21 15:36 | G | 2024-02-08 | Battery Storage | OT | BAT | 109.52 | 109.52 | 110.87 | Fairfield | CT | 2027-12-31 | 2027-12-15 | 2025-08-21 | Direct tap into the Pequonnock 115kV substation in Bridgeport, CT | CNR | FALSE | FALSE |  | PD | SWCT
| 1499 | 2025-06-12 13:40 | G | 2024-02-13 | Battery Storage | OT | BAT | 115.6 | 115.6 | 115.6 | Hampden | MA | 2026-10-31 | 2026-09-30 | 2025-06-12 | Palmer 503 Substation new 115 kV line | CNR | FALSE | FALSE |  | PD | WMA
| 1500 | 2025-10-17 15:13 | G | 2024-02-20 | Offshore Wind CNR only | WT | WND | 0 | 1249.5 | 1249.5 | NA | MA | 2033-11-04 | 2033-03-27 | 2025-10-11 | National Grid Brayton Point 345kV Substation | CNR | FALSE | FALSE |  |  | RI
| 1501 | 2025-06-18 16:50 | G | 2024-02-29 | Battery Storage | OT | BAT | 167.1 | 167.1 | 167.1 | New London | CT | 2028-04-01 | 2028-03-20 | 2024-12-11 | Primary POI: 115kV line 1080 (41.5515028, -72.1253556) , Alternate POI: 115kV line 1000 (41.551478, -72.125294) | CNR | FALSE | FALSE |  | PD | CT |  | Not Started
| 1503 | 2024-03-20 16:55 | G | 2024-03-13 | EE Lost Nation Group DG Study | PV | SUN | 9.98 | 9.98 | 9.98 | Coos | NH | 2025-12-31 | 2025-12-01 | 2024-03-20 | EE Lost Nation substation | NA | FALSE | FALSE |  | PD | NH
| 1504 | 2024-03-20 16:55 | G | 2024-03-13 | Solar | PV | SUN | 10 | 10 | 10 | Belknap | NH | 2025-12-31 | 2025-12-01 | 2024-03-20 | EE Laconia substation | NA | FALSE | FALSE |  | PD | NH
| 1505 | 2025-10-21 17:17 | G | 2024-03-14 | Offshore Wind | WT | WND | 1275 | 1275 | 1275 | NA | CT | 2031-09-01 | 2031-03-01 | 2025-10-09 | Eversource 345kV Montville Substation | CNR | FALSE | FALSE |  | PD | CT
| 1506 | 2024-04-18 16:38 | G | 2024-03-22 | Battery Storage | OT | BAT | 152.656 | 152.656 | 152.656 | Middlesex | MA | 2028-06-01 | 2028-05-01 | 2024-04-18 | The proposed POI is tapping Eversource’s 115kV transmission line from Hudson to Sudbury. | NR | FALSE | FALSE |  | PD | BOST
| 1507 | 2025-10-17 15:13 | G | 2024-03-27 | Solar Increase | PV | SUN | 25 | 177.4113 | 177.4113 | Hartford | CT | 2028-12-15 | 2028-10-15 | 2025-10-11 | To interconnect at the POI of Gravel Pit Solar as an increase to (QP1030 + QP 1247 + QP 1357), the POI is the new Gravel Pit Solar substation at the new three-breaker ring bus on the 115 kV Connecticut Light & Power Company 1200 line between Barbour Hill and Windsor Locks. | CNR | FALSE | FALSE |  | PD | CT
| 1508 | 2024-09-26 13:16 | G | 2024-04-01 | Battery Storage | OT | BAT | 167.1 | 167.1 | 167.1 | Hartford | CT | 2028-04-01 | 2028-03-20 | 2024-09-26 | Primary POI: 345kV Line, Agawam to North Bloomfield Line, POI: 42.031254, -72.698516 Alternative POI: 115kV Line, Tap156253 to North Bloomfield, POI: 42.031274, -72.698830 | CNR | FALSE | FALSE |  | PD | CT
| 1509 | 2025-10-07 17:16 | G | 2024-04-03 | Battery Storage | OT | BAT | 152.7552 | 152.7552 | 152.7552 | Worcester | MA | 2027-12-31 | 2027-12-31 | 2025-10-07 | 3-breaker ring bus tapping the W175 line. ESA sub located approximately 0.23 miles from West Charlton 115 kV substation at current coordinates 42° 8'10.02"N 72° 1'30.37"W | CNR | FALSE | FALSE |  | PD | CMA
| 1510 | 2025-10-07 17:17 | G | 2024-04-03 | Battery Storage | OT | BAT | 152.7552 | 152.7552 | 152.7552 | Wocester | MA | 2027-12-31 | 2027-12-31 | 2025-10-07 | Carpenter Hill substation, 115 kV bus, National Grid at open bay | CNR | FALSE | FALSE |  | PD | CMA
| 1511 | 2024-05-15 08:54 | G | 2024-04-08 | Battery Storage | OT | BAT | 250.8939 | 250.8939 | 250.8939 | Hampden | MA | 2027-12-31 | 2027-08-01 | 2024-05-14 | Western Massachusetts Electric Company (Eversource Energy) 345kV Ludlow | CNR | FALSE | FALSE |  | PD | WMA
| 1512 | 2024-05-29 11:05 | G | 2024-04-08 | Battery Storage + Solar | OT | SUN BAT | 100.4637 | 100.4637 | 100.4637 | Franklin | MA | 2027-12-31 | 2027-08-31 | 2024-05-29 | New England Power Co, 115 kV, 2.25 miles from E131 TAP 113010 and 3.29 miles from HARRIMAN 113146) (115 kV) | CNR | FALSE | FALSE |  | PD | WMA
| 1514 | 2025-10-17 15:14 | G | 2024-04-08 | Battery Storage | OT | BAT | 408.1 | 408.1 | 408.1 | Worcester | MA | 2028-08-30 | 2028-05-31 | 2025-10-11 | National Grid Barre Tap-Wendell Depot Tap 115kV | CNR | FALSE | FALSE |  | PD | CMA
| 1516 | 2025-10-17 15:14 | G | 2024-04-09 | Battery Storage | OT | BAT | 114.7 | 114.7 | 114.7 | Windsor | VT | 2028-08-30 | 2028-05-31 | 2025-10-11 | Vermont Electric Power Company (VELCO) Ascutney 115 kV Substation | CNR | FALSE | FALSE |  | PD | VT
| 1517 | 2025-10-17 15:14 | G | 2024-04-09 | Battery Storage | OT | BAT | 365.8 | 365.8 | 365.8 | Franklin | MA | 2028-08-30 | 2028-05-31 | 2025-10-11 | National Grid 69kV Line E-5D Deerfeild-Shutesbury | CNR | FALSE | FALSE |  | PD | WMA
| 1519 | 2025-06-02 10:35 | G | 2024-04-12 | Offshore Wind | WT | WND | 1200 | 1200 | 1200 | NA | RI | 2031-04-10 | 2030-07-01 | 2025-06-02 | Kent County 345kV | CNR | FALSE | FALSE |  | PD | RI
| 1520 | 2025-09-03 11:36 | G | 2024-04-16 | Battery Storage | OT | BAT | 125 | 125 | 125 | New Haven | CT | 2028-05-01 | 2028-03-01 | 2025-09-03 | Primary POI: Eversource Owned 115kV Line # 1142 Alternate POI 1: 115kV Express Feeder to Oxford 26N Substation Alternate POI 2: Eversource Owned 115kV Line # 1403 | CNR | FALSE | FALSE |  | PD | CT